## SCHEDULE
MASTER Training Schedule for SMIP process & tool training
Note: This schedule will be updated as appropriate during the training delivery period (check current date in the footer). Please contact Chris Wright on 3636 2034 for updates or information.
LEGEND | HP TRAINERS
Process Training | Neil | Glen | Muthu
Tool Training | Peter | Rose
Total of 33 ID Super Users who train the End Users in processes
Total of 84 Champions (managers/senior staff) who communicate and reinforce the 'new way of working'
5 HP Trainers who train the Super and End Users in the tool
1 Process Instructional Designer (Chris Wright) who trains the Super Users in processes
Super User training takes 3 weeks prior to End User training
End User training takes 6 weeks : starts on 17 July and finishes on Fri 25 August 2006
INFOSERVICE CENTRE | WEEK 1: 17 - 21 July 2006 |  |  |  |  | WEEK 2: 24 - 28 July 2006 |  |  |  |  | WEEK 3: 31 July - 4 August 2006 |  |  |  |  | WEEK 4: 7 - 11 August 2006 |  |  |  |  | WEEK 5: 14 - 18 August 2006 |  |  |  |  | WEEK 6: 21 - 25 August 2006 |  |  |  |  | WEEK 7: 28 August - 1 September 2006
37 | Mon 17 | Tue 18 | Wed 19 | Thu 20 | Fri 21 | Mon 24 | Tue 25 | Wed 26 | Thu 27 | Fri 28 | Mon 31 | Tue 1 | Wed 2 | Thu 3 | Fri 4 | Mon 7 | Tue 8 | Wed 9 | Thu 10 | Fri 11 | Mon 14 | Tue 15 | Wed 16 | Thu 17 | Fri 18 | Mon 21 | Tue 22 | Wed 23 | Thu 24 | Fri 25 | Mon 28 | Tue 29 | Wed 30 | Thu 31 | Fri 1
Group 1 | SERVICE 1 | SERVICE 1
| Pallavi/Peter | Peter (HP)
| CTC 1 | CTC 4 | [10 empty] | ?
Group 2 & 5 & 8 |  |  | SERVICE 2 |  |  |  |  | SERVICE 2 |  |  |  |  | SERVICE 5 |  |  |  |  | SERVICE 5 |  |  |  | SERVICE 8 | [5 empty] | See next week |  |  |  |  | SERVICE 8
|  |  | Joy/Lee |  |  |  |  | Neil |  |  |  |  | Joy/Lee |  |  |  |  | Muthu |  |  |  | Pallavi/Peter | [10 empty] | Peter (HP)
|  |  | Rm 70 |  |  |  |  | Rm 70 |  |  | 4 |  | Rm 70 |  |  |  |  | Rm 70 |  |  |  | Rm 70 | [10 empty] | Rm 70
Group 3 & 6 & 9 |  |  |  | SERVICE 3 |  |  |  |  | SERVICE 3 |  | SERVICE 6 | [7 empty] | SERVICE 6 |  |  |  |  | SERVICE 9 |  |  |  |  | SERVICE 9
| Rm 70 | Block 7/Level 9 Room 70 |  | Pallavi/Peter |  |  |  |  | Rose |  | Pallavi/Peter | [7 empty] | Peter (HP) |  |  |  |  | Joy/Lee |  |  |  |  | Rose (HP)
| HTN 3 | Herston Training Room 3 |  | Rm 70 |  |  |  |  | Rm 70 |  | Rm 70 | 4 | [6 empty] | CTC 4 |  |  |  |  | Rm 70 |  |  |  |  | CTC 4
Group 4 & 7 & 10 | CTC 1 | B7/Level 9 - Computer Training Centre, rm 1 |  |  | SERVICE 4 |  |  |  |  | SERVICE 4 |  | SERVICE 7 | [7 empty] | SERVICE 7 |  |  |  |  | SERVICE 10 |  |  |  |  | SERVICE 10
| CTC 4 | B7/Level 9 - Computer Training Centre, rm 4 |  |  | Joy/Lee |  |  |  |  | Neil |  | Joy/Lee | [7 empty] | Peter (HP) |  |  |  |  | Pallavi/Peter |  |  |  |  | Rose
[5 empty] | Rm 70 |  |  |  |  | Rm 70 |  | HTN 3 | [7 empty] | CTC 4 |  |  |  |  | Rm 70 |  |  |  |  | CTC 4
TECHNICAL OPERATIONS | WEEK 1: 17 - 21 July 2006 |  |  |  |  | WEEK 2: 24 - 28 July 2006 |  |  |  |  | WEEK 3: 31 July - 4 August 2006 |  |  |  |  | WEEK 4: 7 - 11 August 2006 |  |  |  |  | WEEK 5: 14 - 18 August 2006 |  |  |  |  | WEEK 6: 21 - 25 August 2006 |  |  |  |  | WEEK 6: 21 - 25 August 2006
64 | Mon 17 | Tue 18 | Wed 19 | Thu 20 | Fri 21 | Mon 24 | Tue 25 | Wed 26 | Thu 27 | Fri 28 | Mon 31 | Tue 1 | Wed 2 | Thu 3 | Fri 4 | Mon 7 | Tue 8 | Wed 9 | Thu 10 | Fri 11 | Mon 14 | Tue 15 | Wed 16 | Thu 17 | Fri 18 | Mon 21 | Tue 22 | Wed 23 | Thu 24 | Fri 25 | Mon 21 | Tue 22 | Wed 23 | Thu 24 | Fri 25
Group 1 | TO 1 | TO 1 | TO 1
| Peter/David | Peter/David | Peter
| JM 1061 | JM 1061 | CTC 4
Group 2 |  |  |  | TO 2 | TO 2 |  | TO 2
|  |  |  | Peter | Peter |  | Neil
|  |  |  | CLlo2le2rm2 | CLlo2le2rm2 |  | CTC 4
Group 3 | [5 empty] | TO 3 | TO 3 |  | TO 3
[6 empty] | David | David |  | Glenn
[6 empty] | JM 2043 | JM 2043 |  | CTC 4
Group 4 | [7 empty] | TO 4 | TO 4 | TO 4
[8 empty] | Peter/David | Peter/David | Glenn
[8 empty] | CTC 1 | CTC 1 | CTC 4 | ? | ? | ?
Group 5 | [10 empty] | TO 5 | TO 5 | TO 5
[11 empty] | David | David | Rose
[11 empty] | TPCH 6 | TPCH 6 | CTC 4 | ? | ?
Group 6 | CTC 1 | Block 7/Level 9 - Computer Training Centre, room 1 | [11 empty] | TO 6 | TO 6 |  | TO 6
| CTC 4 | Block 7/Level 9 - Computer Training Centre, room 4 | [11 empty] | Peter | Peter |  | Neil
| JM 1061 | RBWH/James Main Building, level 1 room 1061 | [11 empty] | CTC 1 | CTC 1 |  | CTC 4
Group 7 | JM 2043 | PBWH/James Mayne Building, level 1 room 2043 | [16 empty] | TO 7 | TO 7 |  | TO 7
| TPCH 6 | Prince Charles Hospital, Education Centre, Building 14, room 6 | [16 empty] | David | David |  | Rose
| CLlo2le2rm2 | Citilink Lobby 2 Level 2 Room 2 | [16 empty] | CLlo2le2rm3 | CLlo2le2rm3 |  | CTC 4
Group 8 | CLlo2le2rm3 | Citlink Lobby 2 Level 2 Room 3 | [18 empty] | TO 8 | TO 8 |  |  |  | TO 8
[21 empty] | Peter | Peter |  |  |  | Rose
[21 empty] | JM 1061 | JM 1061 |  |  |  | CTC 4
TECHNICAL ASSURANCE | WEEK 1: 17 - 21 July 2006 |  |  |  |  | WEEK 2: 24 - 28 July 2006 |  |  |  |  | WEEK 3: 31 July - 4 August 2006 |  |  |  |  | WEEK 4: 7 - 11 August 2006 |  |  |  |  | WEEK 5: 14 - 18 August 2006 |  |  |  |  | WEEK 6: 21 - 25 August 2006 |  |  |  |  | WEEK 6: 21 - 25 August 2006
21 | Mon 17 | Tue 18 | Wed 19 | Thu 20 | Fri 21 | Mon 24 | Tue 25 | Wed 26 | Thu 27 | Fri 28 | Mon 31 | Tue 1 | Wed 2 | Thu 3 | Fri 4 | Mon 7 | Tue 8 | Wed 9 | Thu 10 | Fri 11 | Mon 14 | Tue 15 | Wed 16 | Thu 17 | Fri 18 | Mon 21 | Tue 22 | Wed 23 | Thu 24 | Fri 25 | Mon 21 | Tue 22 | Wed 23 | Thu 24 | Fri 25
Group 1 | [5 empty] | TA 1 | TA 1 |  |  |  | TA 1
[6 empty] | Carl | Carl |  |  |  | Peter
[6 empty] | JM 1061 | JM 2200 |  |  |  | HP
Group 2 | JM 1061 | RBWH/James Main Building, level 1 room 1061 | [7 empty] | TA 2 | TA 2 | TA 2
| JM 2200 | RBWH/James Main Building, level 2 room 2200 | [7 empty] | Carl | Carl | Peter
| CTC | Block 7/Level 9 - Computer Training Centre, rooms 1 or 4 | [7 empty] | CTC 1 | CTC 1 | HP |  | 8 | 8 | 8
Group 3 | HP | HP Office, 18 Little Crib St, Milton | [8 empty] | 8 | 8 |  | TA 3 | TA 3 | TA 3
| Cllob1lev3 | RWBH/Citilink building, lobby 1, level 3, conference rooms 1&2 | [11 empty] | Carl | Carl | Neil
[14 empty] | CL lob1 lev3 | CL lob1 lev 3 | CTC 4
BRISBANE CITY CLUSTER | WEEK 1: 17 - 21 July 2006 |  |  |  |  | WEEK 2: 24 - 28 July 2006 |  |  |  |  | WEEK 3: 31 July - 4 August 2006 |  |  |  |  | WEEK 4: 7 - 11 August 2006 |  |  |  |  | WEEK 5: 14 - 18 August 2006 |  |  |  |  | WEEK 6: 21 - 25 August 2006 |  |  |  |  | WEEK 6: 21 - 25 August 2006
20 | Mon 17 | Tue 18 | Wed 19 | Thu 20 | Fri 21 | Mon 24 | Tue 25 | Wed 26 | Thu 27 | Fri 28 | Mon 31 | Tue 1 | Wed 2 | Thu 3 | Fri 4 | Mon 7 | Tue 8 | Wed 9 | Thu 10 | Fri 11 | Mon 14 | Tue 15 | Wed 16 | Thu 17 | Fri 18 | Mon 21 | Tue 22 | Wed 23 | Thu 24 | Fri 25 | Mon 21 | Tue 22 | Wed 23 | Thu 24 | Fri 25
Group 1 | [15 empty] | B CITY 1 | B CITY 1 |  | B CITY 1
[16 empty] | Claire/Glen | Claire/Glen |  | Neil
[16 empty] | Charlotte St | Charlotte St |  | Charlotte St
Group 2 | [20 empty] | B CITY 2 | B CITY 2 |  |  |  |  | B CITY 2
[21 empty] | Claire/Glen | Claire/Glen |  |  |  |  | Neil
[21 empty] | Charlotte St | Charlotte St |  |  |  |  | HP
Group 3 | [23 empty] | B CITY 3 | B CITY 3 | B CITY 3
[24 empty] | Claire/Glen | Claire/Glen | Neil
[24 empty] | Charlotte St | Charlotte St | Charlotte St
GOLD COAST CLUSTER | WEEK 1: 17 - 21 July 2006 |  |  |  |  | WEEK 2: 24 - 28 July 2006 |  |  |  |  | WEEK 3: 31 July - 4 August 2006 |  |  |  |  | WEEK 4: 7 - 11 August 2006 |  |  |  |  | WEEK 5: 14 - 18 August 2006 |  |  |  |  | WEEK 6: 21 - 25 August 2006 |  |  |  |  | WEEK 6: 21 - 25 August 2006
24 | Mon 17 | Tue 18 | Wed 19 | Thu 20 | Fri 21 | Mon 24 | Tue 25 | Wed 26 | Thu 27 | Fri 28 | Mon 31 | Tue 1 | Wed 2 | Thu 3 | Fri 4 | Mon 7 | Tue 8 | Wed 9 | Thu 10 | Fri 11 | Mon 14 | Tue 15 | Wed 16 | Thu 17 | Fri 18 | Mon 21 | Tue 22 | Wed 23 | Thu 24 | Fri 25 | Mon 21 | Tue 22 | Wed 23 | Thu 24 | Fri 25
Group 1 | [5 empty] | GOLD 1 | GOLD 1 | GOLD 1
[6 empty] | Paul | Paul | Glenn
[6 empty] | LO TR lev1 | LO TR lev1 | LO TR lev1 |  |  | 9 | 9 |  | 9
Group 2 | [10 empty] | GOLD 2 | GOLD 2 |  | GOLD 2
| GC TR lev3 | Hot Tomato House Training Room Level 2 | [8 empty] | Glenn | Glenn |  | Peter
| LO TR lev1 | Logan Hospital Training Room Level 1 | [8 empty] | GC TR lev3 | GC TR lev3 |  | GC TR lev3
Group 3 | [15 empty] | GOLD 3 | GOLD 3 | GOLD 3
[16 empty] | Glenn | Glenn | Peter
[16 empty] | GC TR lev3 | GC TR lev3 | GC TR lev3
BRISBANE SOUTH CLUSTER | WEEK 1: 17 - 21 July 2006 |  |  |  |  | WEEK 2: 24 - 28 July 2006 |  |  |  |  | WEEK 3: 31 July - 4 August 2006 |  |  |  |  | WEEK 4: 7 - 11 August 2006 |  |  |  |  | WEEK 5: 14 - 18 August 2006 |  |  |  |  | WEEK 6: 21 - 25 August 2006 |  |  |  |  | WEEK 6: 21 - 25 August 2006
42 | Mon 17 | Tue 18 | Wed 19 | Thu 20 | Fri 21 | Mon 24 | Tue 25 | Wed 26 | Thu 27 | Fri 28 | Mon 31 | Tue 1 | Wed 2 | Thu 3 | Fri 4 | Mon 7 | Tue 8 | Wed 9 | Thu 10 | Fri 11 | Mon 14 | Tue 15 | Wed 16 | Thu 17 | Fri 18 | Mon 21 | Tue 22 | Wed 23 | Thu 24 | Fri 25 | Mon 21 | Tue 22 | Wed 23 | Thu 24 | Fri 25
Group 1 | [12 empty] | B SOUTH 1 | B SOUTH 1 | B SOUTH 1
[13 empty] | Rob/Cath/Cor | Rob/Cath/Cor | Peter
[13 empty] | PAH 1 | PAH 2 | PAH 3
Group 2 | [18 empty] | B SOUTH 2 | B SOUTH 2 | B SOUTH 2
[19 empty] | Rob/Cath/Cor | Rob/Cath/Cor | Glenn
| PAH 1 | PAH - 1.4L.3B Bryan Emmerson Seminar Room B, 4th Floor, Building 1 | [16 empty] | PAH 4 | PAH 4 | PAH 3
Group 3 | PAH 2 | PAH - 1.GL.1 Training Room, Ground Floor, Building 1 | [18 empty] | B SOUTH 3 | B SOUTH 3 |  | B SOUTH 3
| PAH 3 | PAH - Training Room 2, Basement, Building 15 | [18 empty] | Rob/Cath/Cor | Rob/Ctah/Cor |  | Glenn
| PAH 4 | PAH - 1.GL.1 Training Room, Ground Floor, Building 1 | [18 empty] | QEII | QEII |  | PAH 3
Group 4 | QEII | QEII - 3A Computer Room, 3rd Floor | [23 empty] | B SOUTH 4 | B SOUTH 4 | B SOUTH 4
[26 empty] | Rob/Cath/Cor | Rob/Ctah/Cor | Rose
[26 empty] | QEII | QEII | PAH 3
SERVICE INTEGRATION | WEEK 1: 17 - 21 July 2006 |  |  |  |  | WEEK 2: 24 - 28 July 2006 |  |  |  |  | WEEK 3: 31 July - 4 August 2006 |  |  |  |  | WEEK 4: 7 - 11 August 2006 |  |  |  |  | WEEK 5: 14 - 18 August 2006 |  |  |  |  | WEEK 6: 21 - 25 August 2006 |  |  |  |  | WEEK 6: 21 - 25 August 2006
80 staff | Mon 17 | Tue 18 | Wed 19 | Thu 20 | Fri 21 | Mon 24 | Tue 25 | Wed 26 | Thu 27 | Fri 28 | Mon 31 | Tue 1 | Wed 2 | Thu 3 | Fri 4 | Mon 7 | Tue 8 | Wed 9 | Thu 10 | Fri 11 | Mon 14 | Tue 15 | Wed 16 | Thu 17 | Fri 18 | Mon 21 | Tue 22 | Wed 23 | Thu 24 | Fri 25 | Mon 21 | Tue 22 | Wed 23 | Thu 24 | Fri 25
Group 1 | SI 1 | SI 1 | SI 1
| Tanya/Chris | Tanya/Chris | Glenn
| B7 Lev 12 Rm 29 | B7 Lev 12 Rm 29 | PAH 2
Group 2 |  |  |  | SI 2 | SI 2 | SI 2
|  |  |  | Tanya/? | Tanya/Chris | Glenn
|  |  |  | CTC 1 | CTC 1 | CTC 4
Group 3 | [7 empty] | SI 3 | SI 3 |  |  | SI 3
[8 empty] | Tanya/Chris | Tanya/Chris |  |  | Rose
[8 empty] | B7 | B7 |  |  | CTC 4
Group 4 | [12 empty] | SI 4 | SI 4 | SI 4
[13 empty] | David/Adam | David/Adam | Muthu
[13 empty] | TPCH 6 | TPCH 6 | HP
Group 5 | [14 empty] | SI 5 | SI 5 | SI 5
[15 empty] | David/Adam | David/Adam | Glenn
[15 empty] | CLlo2le2rm2 | CLlo2le2rm2 | HP
Group 6 | [17 empty] | SI 6 | SI 6 | SI 6
| CTC | Block 7/Level 9 - Computer Training Centre, rooms 1 or 4 | [15 empty] | David/Adam | David/Adam | Neil
| JM 1060 | RBWH/James Mayne Building, level 1, room 1060 | [15 empty] | CTC 1 | CTC 1 | HP
Group 7 | B7 | RBWH/Block 7, level 12, room 29 | [16 empty] | SI 7 | SI 7 |  | SI 7
| B7 | RWBH/Block 7, level 11, room 101 | [16 empty] | Colin/MarieL | Colin/MarieL |  | Muthu
| TPCH 6 | Prince Charles Hospital, Education Centre, Building 14, room 6 | [16 empty] | JM 1060 | CTC 1 |  | PAH 2
Group 8 | HP | HP Office, 18 Little Crib St, Milton | [18 empty] | SI 8 | SI 8 |  |  | SI 8
| PAH 2 | Lower Ground floor, Building 15, room 2 | [18 empty] | Colin/MarieL | Colin/MarieL |  |  | Rose
| CLlo2le2rm2 | Citilink Lobby 2 Level 2 Room 2 | [18 empty] | JM 1062 | JM 1062 |  |  | HP
Group 9 | [25 empty] | SI 9 | SI 9 | SI 9
[26 empty] | ?/MarieL | ?/MarieL | Neil
[26 empty] | CTC 1 | CTC 1 | CTC 4
Group 10 | [27 empty] | SI 10 | SI 10 | SI 10
[28 empty] | ?/MarieL | MarieL | Peter (HP)
[28 empty] | CLlo2le2rm2 | CTC 1 | HP
OPERATIONS CONSULTING | WEEK 1: 17 - 21 July 2006 |  |  |  |  | WEEK 2: 24 - 28 July 2006 |  |  |  |  | WEEK 3: 31 July - 4 August 2006 |  |  |  |  | WEEK 4: 7 - 11 August 2006 |  |  |  |  | WEEK 5: 14 - 18 August 2006 |  |  |  |  | WEEK 6: 21 - 25 August 2006 |  |  |  |  | WEEK 6: 21 - 25 August 2006
20 | Mon 17 | Tue 18 | Wed 19 | Thu 20 | Fri 21 | Mon 24 | Tue 25 | Wed 26 | Thu 27 | Fri 28 | Mon 31 | Tue 1 | Wed 2 | Thu 3 | Fri 4 | Mon 7 | Tue 8 | Wed 9 | Thu 10 | Fri 11 | Mon 14 | Tue 15 | Wed 16 | Thu 17 | Fri 18 | Mon 21 | Tue 22 | Wed 23 | Thu 24 | Fri 25 | Mon 21 | Tue 22 | Wed 23 | Thu 24 | Fri 25
Group 1 | [5 empty] | OC 1 | OC 1 |  |  |  | OC 1
[6 empty] | Peter Eberle | Peter Eberle |  |  |  | Rose
[6 empty] | CTC 1 | CTC 1 |  |  |  | HP
Group 2 | CTC | Block 7/Level 9 - Computer Training Centre, rooms 1 and 4 | [18 empty] | OC 3 | OC 3 |  |  |  |  | OC 3
| HP | HP Office, 18 Little Crib St, Milton | [18 empty] | Peter Eberle | Peter Eberle |  |  |  |  | Peter
[21 empty] | CTC 1 | CTC 1 |  |  |  |  | CTC 4
BRISBANE NORTH CLUSTER | WEEK 1: 17 - 21 July 2006 |  |  |  |  | WEEK 2: 24 - 28 July 2006 |  |  |  |  | WEEK 3: 31 July - 4 August 2006 |  |  |  |  | WEEK 4: 7 - 11 August 2006 |  |  |  |  | WEEK 5: 14 - 18 August 2006 |  |  |  |  | WEEK 6: 21 - 25 August 2006 |  |  |  |  | WEEK 6: 21 - 25 August 2006
62 staff | Mon 17 | Tue 18 | Wed 19 | Thu 20 | Fri 21 | Mon 24 | Tue 25 | Wed 26 | Thu 27 | Fri 28 | Mon 31 | Tue 1 | Wed 2 | Thu 3 | Fri 4 | Mon 7 | Tue 8 | Wed 9 | Thu 10 | Fri 11 | Mon 14 | Tue 15 | Wed 16 | Thu 17 | Fri 18 | Mon 21 | Tue 22 | Wed 23 | Thu 24 | Fri 25 | Mon 21 | Tue 22 | Wed 23 | Thu 24 | Fri 25
Group 1 |  | B NORTH 1 | B NORTH 1 | B NORTH 1
|  | John/Johan | John/Johan | Peter
|  | CLlo2le2rm2 | CLlo2le2rm2 | CTC 4
Group 2 | [5 empty] | B NORTH 2 | B NORTH 2 | B NORTH 2
[6 empty] | John/Johan | John/Johan | Rose
[6 empty] | JM 1062 | JM 1062 | CTC 4
Group 3 | [8 empty] | B NORTH 3 | B NORTH 3 | B NORTH 3
[9 empty] | Peter Eberle | Peter Eberle | Rose
[9 empty] | TPCH 9 | TPCH 6 | CTC 4
Group 4 | [11 empty] | B NORTH 4 | B NORTH 4 | B NORTH 4
[12 empty] | John/Johan | John/Johan | Muthu
| JM 1062 | RBWH/James Main Building, level 1 room 1062 | [9 empty] | CTC 1 | CTC 1 | HP
Group 5 | TPCH 6 | Prince Charles Hospital, Education Centre, Building 14, room 6 | [13 empty] | B NORTH 5 | B NORTH 5 | B NORTH 5
| TPCH 9 | Prince Charles Hospital, Education Centre, Building 14, room 9 | [13 empty] | Peter Eberle | Peter Eberle | Neil
| CTC | Block 7/Level 9 - Computer Training Centre, rooms 1 and 4 | [13 empty] | CTC 1 | CTC 1 | HP
Group 6 | HP | HP Office, 18 Little Crib St, Milton | [16 empty] | B NORTH 6 | B NORTH 6 | B NORTH 6
| CLlo2le2rm2 | Citilink Lobby 2 Level 2 Room 2 | [16 empty] | John/Johan | John/Johan | Rose
| Cllob1lev3rm1 | Citilink building, lobby 1, level 3, conference rooms 1&2 | [16 empty] | CLlo2le2rm2 | CLlo2le2rm2 | CTC 4
Group 7 | [20 empty] | B NORTH 7 | B NORTH 7 |  | B NORTH 7
[21 empty] | John/Johan | John/Johan |  | Rose
[21 empty] | CLlo1le3rm1 | CLlo1le3rm1 |  | HP
Group 8 | [23 empty] | B NORTH 8 | B NORTH 8 | B NORTH 8
[24 empty] | John/Johan | John/Johan | Glenn
[24 empty] | CTC 1 | CTC 1 | HP
SOUTH WEST CLUSTER | WEEK 1: 17 - 21 July 2006 |  |  |  |  | WEEK 2: 24 - 28 July 2006 |  |  |  |  | WEEK 3: 31 July - 4 August 2006 |  |  |  |  | WEEK 4: 7 - 11 August 2006 |  |  |  |  | WEEK 5: 14 - 18 August 2006 |  |  |  |  | WEEK 6: 21 - 25 August 2006 |  |  |  |  | WEEK 6: 21 - 25 August 2006
32 | Mon 17 | Tue 18 | Wed 19 | Thu 20 | Fri 21 | Mon 24 | Tue 25 | Wed 26 | Thu 27 | Fri 28 | Mon 31 | Tue 1 | Wed 2 | Thu 3 | Fri 4 | Mon 7 | Tue 8 | Wed 9 | Thu 10 | Fri 11 | Mon 14 | Tue 15 | Wed 16 | Thu 17 | Fri 18 | Mon 21 | Tue 22 | Wed 23 | Thu 24 | Fri 25 | Mon 21 | Tue 22 | Wed 23 | Thu 24 | Fri 25
Group 1 | [6 empty] | STHWEST 1 | STHWEST 1 | STHWEST 1
[7 empty] | Jon/Scott | Jon/Scott | Neil
[7 empty] | Ipswich | Ipswich | Ipswich
Group 2 | [10 empty] | STHWEST 2 | STHWEST 2 | STHWEST 2
[11 empty] | Jon/Scott | Jon/Scott | Peter
[11 empty] | Ipswich | Ipswich | Ipswich
Group 3 | IPSW | Ipswich Hospital - Tower block, Chelmsford Ave, level 9, Computer Room | [14 empty] | STHWEST 3 | STHWEST 3 |  |  |  | STHWEST 3
| TOO 1 | Toowoomba - Cossart House room 2 | [14 empty] | Scott/Jon | Scott/Jon |  |  |  | Glenn
| TOO 2 | Toowoomba - Cossart House computer room | [14 empty] | TOO 1 | TOO 1 |  |  |  | TOO 2
Group 4 | TOO 3 | Toowoomba - Freshney Suite 1 | [18 empty] | STHWEST 4 | STHWEST 4 |  |  | STHWEST 4
[21 empty] | Scott/Jon | Scott/Jon |  |  | Glenn
[21 empty] | TOO 3 | TOO 3 |  |  | TOO 2
SUNSHINE COAST CLUSTER | WEEK 1: 17 - 21 July 2006 |  |  |  |  | WEEK 2: 24 - 28 July 2006 |  |  |  |  | WEEK 3: 31 July - 4 August 2006 |  |  |  |  | WEEK 4: 7 - 11 August 2006 |  |  |  |  | WEEK 5: 14 - 18 August 2006 |  |  |  |  | WEEK 6: 21 - 25 August 2006 |  |  |  |  | WEEK 6: 21 - 25 August 2006
24 | Mon 17 | Tue 18 | Wed 19 | Thu 20 | Fri 21 | Mon 24 | Tue 25 | Wed 26 | Thu 27 | Fri 28 | Mon 31 | Tue 1 | Wed 2 | Thu 3 | Fri 4 | Mon 7 | Tue 8 | Wed 9 | Thu 10 | Fri 11 | Mon 14 | Tue 15 | Wed 16 | Thu 17 | Fri 18 | Mon 21 | Tue 22 | Wed 23 | Thu 24 | Fri 25 | Mon 21 | Tue 22 | Wed 23 | Thu 24 | Fri 25
Group 1 | [13 empty] | SUN 1 | SUN 1 | SUN 1
[14 empty] | Andrew/Steve | Andrew/Steve | Peter
[14 empty] | Caboolture | Caboolture | Caboolture
Group 2 | [18 empty] | SUN 2 | SUN 2 |  |  | SUN 2
[19 empty] | Andrew/Steve | Andrew/Steve |  |  | Rose
[19 empty] | Caloundra | Caloundra |  |  | Caloundra
Group 3 | Caboolture | Level 3, Lecture Room 5 | [21 empty] | SUN 3 | SUN 3 |  |  |  | SUN 3
[24 empty] | Andrew/Steve | Andrew/Steve |  |  |  | Peter
[24 empty] | Caboolture | Caboolture |  |  |  | Caboolture
Group 4 | [26 empty] | SUN 4 | SUN 4 |  | SUN 4
[27 empty] | Andrew/Steve | Andrew/Steve |  | Glenn
[27 empty] | Caloundra | Caloundra |  | Caloundra
CENTRAL CLUSTER | WEEK 1: 17 - 21 July 2006 |  |  |  |  | WEEK 2: 24 - 28 July 2006 |  |  |  |  | WEEK 3: 31 July - 4 August 2006 |  |  |  |  | WEEK 4: 7 - 11 August 2006 |  |  |  |  | WEEK 5: 14 - 18 August 2006 |  |  |  |  | WEEK 6: 21 - 25 August 2006 |  |  |  |  | WEEK 6: 21 - 25 August 2006
34 | Mon 17 | Tue 18 | Wed 19 | Thu 20 | Fri 21 | Mon 24 | Tue 25 | Wed 26 | Thu 27 | Fri 28 | Mon 31 | Tue 1 | Wed 2 | Thu 3 | Fri 4 | Mon 7 | Tue 8 | Wed 9 | Thu 10 | Fri 11 | Mon 14 | Tue 15 | Wed 16 | Thu 17 | Fri 18 | Mon 21 | Tue 22 | Wed 23 | Thu 24 | Fri 25 | Mon 21 | Tue 22 | Wed 23 | Thu 24 | Fri 25
Group 1 |  |  | CENTRAL 1 | CENTRAL 1 | CENTRAL 1
|  |  | Chris/Scott | Chris/Scott | Muthu
|  |  | ROK TR | ROK TR | ROK TR
Group 2 | [5 empty] | CENTRAL 2 | CENTRAL 2 | CENTRAL 2
| ROK TR | Yangulla Training Room |  |  |  | Chris/Scott | Chris/Scott | Muthu
[6 empty] | ROK TR | ROK TR | ROK TR
Group 3 | [7 empty] | CENTRAL 3 | CENTRAL 3 | CENTRAL 3
[8 empty] | Lisa Carter | Lisa Carter | Muthu
[8 empty] | Maryborough | Maryborough | Maryborough
Group 4 | [10 empty] | CENTRAL 4 | CENTRAL 4 | CENTRAL 4
[11 empty] | Lisa Carter | Lisa Carter | Glenn
[11 empty] | Maryborough | Maryborough | Maryborough
Group 5 | [12 empty] | CENTRAL 5 | CENTRAL 5 | CENTRAL 5
[13 empty] | Chris/Scott | Chris/Scott | Glenn
[13 empty] | ROK TR | ROK TR | ROK TR
NORTHERN CLUSTER | WEEK 1: 17 - 21 July 2006 |  |  |  |  | WEEK 2: 24 - 28 July 2006 |  |  |  |  | WEEK 3: 31 July - 4 August 2006 |  |  |  |  | WEEK 4: 7 - 11 August 2006 |  |  |  |  | WEEK 5: 14 - 18 August 2006 |  |  |  |  | WEEK 6: 21 - 25 August 2006 |  |  |  |  | WEEK 6: 21 - 25 August 2006
41 | Mon 17 | Tue 18 | Wed 19 | Thu 20 | Fri 21 | Mon 24 | Tue 25 | Wed 26 | Thu 27 | Fri 28 | Mon 31 | Tue 1 | Wed 2 | Thu 3 | Fri 4 | Mon 7 | Tue 8 | Wed 9 | Thu 10 | Fri 11 | Mon 14 | Tue 15 | Wed 16 | Thu 17 | Fri 18 | Mon 21 | Tue 22 | Wed 23 | Thu 24 | Fri 25 | Mon 21 | Tue 22 | Wed 23 | Thu 24 | Fri 25
Group 1 | [10 empty] | NORTH 1 | NORTH 1 | NORTH 1
[11 empty] | Wynita | Wynita | Muthu
[11 empty] | Townsville | Townsville | Townsville
Group 2 | [17 empty] | NORTH 2 | NORTH 2 | NORTH 2
[18 empty] | Wynita | Wynita | Muthu
Group 3 | Townsville | Townsville Hospital, Eductaion Block, Ground Floor, TTH, Room EG0.65 | [18 empty] | NORTH 3 | NORTH 3 | NORTH 3
| Cairns 1 | Cairns Base Hospital, North Qld Workforce Unit, A Block,3rd floor, room 1 | [18 empty] | Wynita | Wynita | Muthu
| Cairns 2 | Cairns Base Hospital, North Qld Workforce Unit, A Block,3rd floor, room 2
Group 4 | [22 empty] | NORTH 4 | NORTH 4 | NORTH 4
[23 empty] | Scott | Scott | Muthu
[23 empty] | Cairns 1 | Cairns 1 | Cairns 2
Group 5 | [25 empty] | NORTH 5 | NORTH 5 | NORTH 5
[26 empty] | Scott | Scott | Glenn
[26 empty] | Cairns 1 | Cairns 1 | Ciarns 2
Note on L56: Chris Wright: Cancelled
Note on S217: Staff from Charters Towers and Longreach attend
Note on V220: Staff from Mt Isa attends
Note on X223: Staff from Weipa
Note on AA226: Staff from Torres

## ISC
Super Users
| Joy Jorgensen | 3636 6777
| Lee Newton | 3637 6777
| Pallavi Mohan | 3638 6777
| Peter Imecs | 3639 6777
Date | Monday 17 July 2006 |  |  | Tuesday 18 July 2006
Training Type | PROCESS TRAINING |  |  | TOOL TRAINING
Branch | InfoService Centre |  |  | InfoService Centre
Group | Group 1 - SERVICE 1 |  |  | Group 1 - SERVICE 1
Trainer | Pallavi Mohan & Peter Imecs |  |  | Peter
Location | Block 7, Level 9, Computer Training Unit, Room 1 |  |  | Block 7, Level 9, Computer Training Unit, Room 4
|  | Name | Confirmed |  | Name | Confirmed
| 1 | Wendy Balachandran |  | 1 | Wendy Balachandran
| 2 | Rowan Salt |  | 2 | Rowan Salt
| 3 | Michael Ruge |  | 3 | Michael Ruge
| 4 | Patricia Burow |  | 4 | Patricia Burow
| 5 | Michael Hodges-Jones |  | 5 | Michael Hodges-Jones
| 6 | Axel Skrandies |  | 6 | Axel Skrandies
Date | Wednesday 19 July 2006 |  |  | Wednesday 26 July 2006
Training Type | PROCESS TRAINING |  |  | TOOL TRAINING
Branch | InfoService Centre |  |  | InfoService Centre
Group | Group 2 - SERVICE 2 |  |  | Group 2 - SERVICE 2
Trainer | Joy Jorgensen & Lee Newton |  |  | Peter
Location | Block 7, Level 9, Room 70 |  |  | Block 7, Level 9, Room 70
|  | Name | Confirmed |  | Name | Confirmed
| 1 | Kim Dean |  | 1 | Kim Dean
| 2 | Jesse Sullivan |  | 2 | Jesse Sullivan
| 3 | Francis Dowling |  | 3 | Francis Dowling
| 4 | Yancey Norris |  | 4 | Yancey Norris
| 5 | Linda Stubbin |  | 5 | Linda Stubbin
Date | Thursday 20 July 2006 |  |  | Thursday 27 July 2006
Training Type | PROCESS TRAINING |  |  | TOOL TRAINING
Branch | InfoService Centre |  |  | InfoService Centre
Group | Group 3 - SERVICE 3 |  |  | Group 3 - SERVICE 3
Trainer | Pallavi Mohan & Peter Imecs |  |  | Peter
Location | Block 7, Level 9, Room 70 |  |  | Block 7, Level 9, Room 70
|  | Name | Confirmed |  | Name | Confirmed
| 1 | Simon James |  | 1 | Simon James
| 2 | Jacques Rault |  | 2 | Jacques Rault
| 3 | Mark Page |  | 3 | Mark Page
| 4 | Chad Stelmach |  | 4 | Chad Stelmach
Date | Friday 21 July |  |  | Friday 28 July 2006
Training Type | PROCESS TRAINING |  |  | TOOL TRAINING
Branch | InfoService Centre |  |  | InfoService Centre
Group | Group 4 - SERVICE 4 |  |  | Group 4 - SERVICE 4
Trainer | Joy Jorgensen & Lee Newton |  |  | Rose
Location | Block 7, Level 9, Room 70 |  |  | Block 7, Level 9, Room 70
|  | Name | Confirmed |  | Name | Confirmed
| 1 | Sean Taylor-Leech |  | 1 | Sean Taylor-Leech
| 2 | Justin Signal |  | 2 | Justin Signal
| 3 | Michael Diaz |  | 3 | Michael Diaz
| 4 | Di Parikka |  | 4 | Di Parikka
Date | Wednesday 2 August 2006 |  |  | Wednesday 9 August 2006
Training Type | PROCESS TRAINING |  |  | TOOL TRAINING
Branch | InfoService Centre |  |  | InfoService Centre
Group | Group 5 - SERVICE 5 |  |  | Group 5 - SERVICE 5
Trainer | Joy Jorgensen & Lee Newton |  |  | Peter
Location | Block 7, Level 9, Room 70 |  |  | Block 7, Level 9, Room 70
|  | Name | Confirmed |  | Name | Confirmed
| 1 | David Poll |  | 1 | David Poll
| 2 | Kayley Dunstan |  | 2 | Kayley Dunstan
| 3 | Kim Maclure |  | 3 | Kim Maclure
| 4 | Melissa Gray |  | 4 | Melissa Gray
Date | Monday 31 July 2006 |  |  | Thursday 10 August 2006
Training Type | PROCESS TRAINING |  |  | TOOL TRAINING
Branch | InfoService Centre |  |  | InfoService Centre
Group | Group 6 - SERVICE 6 |  |  | Group 6 - SERVICE 6
Trainer | Pallavi Mohan & Peter Imecs |  |  | Peter
Location | Block 7, Level 9, Room 70 |  |  | Block 7, Level 9, Computer Training Unit, Room 4
|  | Name | Confirmed |  | Name | Confirmed
| 1 | Peter Turner |  | 1 | Peter Turner
| 2 | Victor Pillay |  | 2 | Victor Pillay
| 3 | Eleanor Jayasekera |  | 3 | Eleanor Jayasekera
| 4 | Evan Kouklinos |  | 4 | Evan Kouklinos
Date | Tuesday 1 August 2006 |  |  | Friday 11 August 2006
Training Type | PROCESS TRAINING |  |  | TOOL TRAINING
Branch | InfoService Centre |  |  | InfoService Centre
Group | Group 7 - SERVICE 7 |  |  | Group 7 - SERVICE 7
Trainer | Joy Jorgensen & Lee Newton |  |  | Peter
Location | Block 7, Level 9, Computer Training Unit, Room 3 |  |  | Block 7, Level 9, Computer Training Unit, Room 4
|  | Name | Confirmed |  | Name | Confirmed
| 1 | Lexie Varney |  | 1 | Lexie Varney
| 2 | Gavin Heywood |  | 2 | Gavin Heywood
| 3 | Stuart Adelssee |  | 3 | Stuart Adelssee
| 4 | David Roberts |  | 4 | David Roberts
Date | Tuesday 15 August 2006 |  |  | Wednesday 23 August 2006 |  |  | This session to be transferred to Wed 30 Aug
Training Type | PROCESS TRAINING |  |  | TOOL TRAINING
Branch | InfoService Centre |  |  | InfoService Centre
Group | Group 8 - SERVICE 8 |  |  | Group 8 - SERVICE 8
Trainer | Pallavi Mohan & Peter Imecs |  |  | Peter
Location | Block 7, Level 9, Room 56 |  |  | Block 7, Level 9, Room 70
|  | Name | Confirmed |  | Name | Confirmed
| 1 | Daymon Follett |  | 1 | Daymon Follett
| 2 | Anthony Vaughn |  | 2 | Anthony Vaughn
| 3 | Adam Graham |  | 3 | Adam Graham
| 4 | Keith Liversidge |  | 4 | Keith Liversidge
| 5 | Colleen Reis |  | 5 | Colleen Reis
Date | Thursday 17 August 2006 |  |  | Thursday 24 August 2006
Training Type | PROCESS TRAINING |  |  | TOOL TRAINING
Branch | InfoService Centre |  |  | InfoService Centre
Group | Group 9 - SERVICE 9 |  |  | Group 9 - SERVICE 9
Trainer | Joy Jorgensen & Lee Newton |  |  | Peter
Location | Block 7, Level 9, Room 70 |  |  | Block 7, Level 9, Computer Training Unit, Room 4
|  | Name | Confirmed |  | Name | Confirmed
| 1 | Steve Powell |  | 1 | Steve Powell
| 2 | Ben Pasfield |  | 2 | Ben Pasfield
| 3 | Ben Sandiego |  | 3 | Ben Sandiego
| 4 | Craig Dempsey |  | 4 | Craig Dempsey
Date | Friday 18 August 2006 |  |  | Friday 25 August 2006
Training Type | PROCESS TRAINING |  |  | TOOL TRAINING
Branch | InfoService Centre |  |  | InfoService Centre
Group | Group 10 - SERVICE 10 |  |  | Group 10 - SERVICE 10
Trainer | Pallavi Mohan & Peter Imecs |  |  | Peter
Location | Block 7, Level 9, Room 70 |  |  | Block 7, Level 9, Computer Training Unit, Room 4
|  | Name | Confirmed |  | Name | Confirmed
| 1 | Kim Nash |  | 1 | Kim Nash
| 2 | Corrie Macdonald |  | 2 | Corrie Macdonald
| 3 | Left free in case of sickies |  | 3 | Left free in case of sickies
| 4 |  |  | 4
| 5 |  |  | 5

## SIM
| SIM Participants |  |  | Please Enter your name in preferred Session
The Training goes for 3 Days - 2 x Qld Health End to End Service Level Management and 1 x HP Overview Tool (will replace Infra and HELPDESK)
Check Training Room Details on the Main Schedule above
| Session 1 |  | Mon 17 - Wed 19 July |  | Session 5 |  | Fri 4 Aug and Mon 7, Tue 8 August | Session 9 |  | Mon 21, Tues 22, Wed 23 August
| Trainers |  | Tanya/Chris/Neil |  | Trainers |  | David/Adam/Neil | Trainers |  | David/Marie-Louise/Neil
| Confirmed |  | B7L12RM029 & PAH2 |  | Room location |  | CLlo2le2rm2 & HP | TR Rooms |  | CTC1 & CTC4
| 1 | Ron | Brown |  | 1 | Fiona | Am es | 1 | Catherine | Fox
| 2 | Marcus | Driessen |  | 2 | Sioban | Cusack | 2 | Rod | Glover
| 3 | Andrew | Jackson |  | 3 | Michael | Davis | 3 | Ruth | Jorgensen
| 4 | Peter | Nicolls |  | 4 | Karen | Giuffrida | 4 | Leanne | Kent
| 5 | Mick | Rye |  | 5 | Fahad | Khamissa | 5 | Charmaine | Ludlow
| 6 | Lindy | Silato |  | 6 | Peter | Miller | 6 | Chris | McDonald, Paul Rodman
| 7 | Sandy | Warren |  | 7 | Ilyaaz | Shah | 7 | Brett | McLeod, Maria Paulo day 3 HP training
| 8 |  |  |  | 8 | Mathew | Wright | 8 | Elisabeth | Skubis
| Session 2 |  | Thur 20, Fri 21 and Mon 24 July |  | Session 6 |  | Wed 9, Thurs 10, Fri 11 August | Session 10 |  | Wed 23,Thurs 24, Fri 25 August
| Trainers |  | Tanya |  | Trainers |  | David/Adam/Neil | Trainers |  | David/Marie-Louise/Peter
| Confirmed |  | CTC1 & 4 |  | Room |  | CTC1 & HP | Tr Rooms |  | CLlo2le2rm2, CTC1 & HP
| 1 | Diane | Brown |  | 1 | Jeremy | Scutt | 1 | Peter | Bruback
| 2 | Kevin | Cross |  | 2 | Sharon | Allen | 2 | Russell | Dignam
| 3 | Gosia | Cyranowicz |  | 3 | Michael | Cruden | 3 | Renee | Dziopa
| 4 | Adam | Hannam |  | 4 | Marcus | Driessen | 4 | Heather | Enright
| 5 | Leslie | Hunt |  | 5 | Stu | McKenzie | 5 | Rona | Evans
| 6 | Melanie | Joyce |  | 6 | Manmohan | Minhas | 6 | Adrian | Horth
| 7 | Ramon | Toro |  | 7 | Jeff | Murray | 7 | Anne | McMahon
| 8 | Upul | Weekasewa |  | 8 | Lloyd | Robins, | 8 | Jade
| Session 3 |  | Wed 26,Thur 27 July and Tue 1 August |  | Session 7 |  | Thurs 10, Fri11 and Tues 15 August |  | TRAINING ROOM LOCATIONS
| Trainers |  | Tanya/Chris/Rose |  | Trainers |  | Colin/Marie-Louise/Muthu |  | B7L11RM101 | RWBH/Block 7, level 11, room 101
| Confirmed |  | B7L11RM101 |  | TR Room |  | JM1060, CTC1 & PAH2 |  | B7L12RM029 | RWBH/Block 7, level 12, room 029 | TRAINING ROOM LOCATIONS
| 1 | Rachel | Comben |  | 1 | Greg | Callaghan |  | CLlo2le2rm2 | Citilink Lobby 2 Level 2 Room 2 | JM 1062 | RBWH/James Mayne Building, level 1, room 1062
| 2 | Glenn | Dalton |  | 2 | Troy | Conlan |  | CTC | Block 7/Level 9 - Computer Training Centre, rooms 1 or 4 | HP | HP Office, 18 Little Crib St, Milton
| 3 |  |  |  | 3 | Richard | Eckersley |  | HP | HP Office, 18 Little Crib St, Milton
| 4 | Doug | Frost |  | 4 | David | Gray |  | JM 1060 | RBWH/James Mayne Building, level 1, room 1060 | CTC | Block 7/Level 9 - Computer Training Centre, rooms 1 or 4
| 5 | Anthony | Pink |  | 5 | Daniel | Lanza |  | JM 1062 | RBWH/James Main Building, level 1 room 1062
| 6 | Ryan | Spain |  | 6 | Rob | Lawes |  | PAH 2 | Lower Ground floor, Building 15, room 2
| 7 |  |  |  | 7 | Maria | Paulo |  | TPCH 6 | Prince Charles Hospital, Education Centre, Building 14, room 6
| 8 |  |  |  | 8 | Vu | Pham |  | N.B.
| Session 4 |  | Wed 2, Thur 3, Fri 4 August |  | Session 8 |  | Mon 14, Tues 15 and Fri 18 August |  | 1. Please Book your own Diaries, and note the training room locations
| Trainers |  | David/Adam/Muthu |  | Trainers |  | Colin/Marie-Louise/Rose
| Confirmed |  | TPCH6 & HP |  | Training Room |  | JM1062 & HP |  |  |  | N.B.
| 1 | Tony | Blore |  | 1 | Jan | Bennett |  | 2. Training will begin at 9:00 each day until 4:30
| 2 | Matthew | Coleman |  | 2 | Catherine | Hall |  |  |  | 1. Please Book your own Diaries, and note the training room locations
| 3 | Kevin | Cross |  | 3 | Glenda | Brown |  | 3. Please BYO Lunch, all facilities will have tea/coffee, fridges, micorwaves
| 4 | Michael | Gifford |  | 4 | Chris | Hughes
| 5 | Davin | Krause |  | 5 | Dianne | Humes |  |  |  | 2. Training will begin at 9:00 each day until 4:30
| 6 | Geoff | Rixo n |  | 6 | Roy | James
| 7 | Bryn | Samuel |  | 7 | Marika | Miller |  |  |  | 3. On days 1 and 2 please BYO Lunch, all facilities will have tea/coffee, fridges, micorwaves On day 3 at HP in Milton - HP will provide lunch
| 8 | Mark | Worthington |  | 8 | Steve | Shackcloth

## InfoOps
| SIM Participants |  |  | Please Enter your name in preferred Session
The Training goes for 3 Days - 2 x Qld Health End to End Service Level Management and 1 x HP Overview Tool (will replace Infra and HELPDESK)
Check Training Room Details on the Main Schedule above
| Session 1 |  | Session 2 |  | Session 5 |  | Session 6 | Session 9 |  | Session 10
| Trainers |  | 8 staff |  | Trainers |  | 8 staff | Trainers |  | 8 staff
| Confirmed |  | B7L12RM029 & PAH2 |  | Confirmed |  | CLlo2le2rm2 & HP | Confirmed |  | CTC1 & CTC4
| 1 | Ron | Brown |  | 1 | Fiona | Am es | 1 | Catherine | Fox
| 2 | Marcus | Driessen |  | 2 | Sioban | Cusack | 2 | Rod | Glover
| 3 | Andrew | Jackson |  | 3 | Michael | Davis | 3 | Ruth | Jorgensen
| 4 | Peter | Nicolls |  | 4 | Fahad | Khamissa | 4 | Leanne | Kent
| 5 | Mick | Rye |  | 5 | Peter | Miller | 5 | Charmaine | Ludlow
| 6 | Lindy | Silato |  | 6 | Jeremy | Scutt | 6 | Chris | McDonald
| 7 | Sandy | Warren |  | 7 | Ilyaaz | Shah | 7 | Brett | McLeod
| 8 |  |  |  | 8 | Mathew | Wright | 8 | Elisabeth | Skubis
| Session 2 |  | Session 3 |  | Session 6 |  | Session 7 | Session 10 |  | 0
| Trainers |  | 0 |  | Trainers |  | 8 staff | Trainers |  | 0
| Confirmed |  | CTC1 & 4 |  | Confirmed |  | CTC1 & HP | Confirmed |  | CLlo2le2rm2, CTC1 & HP
| 1 | Diane | Brown |  | 1 | David | Cervenjak | 1 | Peter | Bruback
| 2 | Kevin | Cross |  | 2 | Stu | McKenzie | 2 | Michael | Cruden
| 3 | Gosia | Cyranowicz |  | 3 | Manmohan | Minhas | 3 | Russell | Dignam
| 4 | Adam | Hannam |  | 4 | Jeff | Murray | 4 | Heather | Enright
| 5 | Leslie | Hunt |  | 5 | Lloyd | Robins | 5 | Roy | James
| 6 | Melanie | Joyce |  | 6 | Ryan | Spain | 6 | Anne | McMahon
| 7 | Ramon | Toro |  | 7 |  |  | 7
| 8 | Upul | Weekasewa |  | 8 |  |  | 8
| Session 3 |  | Session 4 |  | Session 7 |  | Session 8 |  | TRAINING ROOM LOCATIONS
| Trainers |  | 8 staff |  | Trainers |  | 8 staff |  | B7L11RM101 | RWBH/Block 7, level 11, room 101
| Confirmed |  | B7L11RM101 |  | Confirmed |  | JM1060, CTC1 & PAH2 |  | B7L12RM029 | RWBH/Block 7, level 12, room 029
| 1 | Rachel | Comben |  | 1 | Troy | Conlan |  | CLlo2le2rm2 | Citilink Lobby 2 Level 2 Room 2
| 2 | Glenn | Dalton |  | 2 | Richard | Eckersley |  | CTC | Block 7/Level 9 - Computer Training Centre, rooms 1 or 4
| 3 | David | Evans |  | 3 | David | Gray |  | HP | HP Office, 18 Little Crib St, Milton
| 4 | Doug | Frost |  | 4 | Daniel | Lanza |  | JM 1060 | RBWH/James Mayne Building, level 1, room 1060
| 5 | Catherine | Hall |  | 5 | Rob | Lawes |  | JM 1062 | RBWH/James Main Building, level 1 room 1062
| 6 | Sharon | Holloway |  | 6 | Maria | Paulo |  | PAH 2 | Lower Ground floor, Building 15, room 2
| 7 | Anthony | Pink |  | 7 | Vu | Pham |  | TPCH 6 | Prince Charles Hospital, Education Centre, Building 14, room 6
| 8 | Ryan | Spain |  | 8 | Heidi | Wilson |  | N.B.
| Session 4 |  | Session 5 |  | Session 8 |  | Session 9 |  | 1. Please Book your own Diaries, and note the training room locations
| Trainers |  | 8 staff |  | Trainers |  | 8 staff
| Confirmed |  | TPCH6 & HP |  | Confirmed |  | JM1062 & HP
| 1 | Tony | Blore |  | 1 | Jan | Bennett |  | 2. Training will begin at 8:30 each day until 4:30
| 2 | Matthew | Coleman |  | 2 | Chris | Hughes
| 3 | Michael | Gifford |  | 3 | Marika | Miller |  | 3. For the two days of QH Process Training please BYO Lunch, all facilities will have tea/coffee, fridges, micorwaves
| 4 | Karen | Giuffrida |  | 4 | Jill | Perkins
| 5 | Dianne | Humes |  | 5 | Steve | Shackcloth
| 6 | Bryn | Samuel |  | 6 |  |  |  | 4. For the one day on HP Tool Training - Lunch will be provided for you by HP.
| 7 |  |  |  | 7
| 8 |  |  |  | 8

## TechAss
GROUP 2 28th,31st July & 1st Aug | GROUP 3 3rd,4th,7th August
Shaun Caddell | Adam Bulloch
David Armstrong | Andrew Kriedemann
Carl Page | Darryl Wynne
Ben Stanley | Brent Summerville
Alan Brown | Rob Hendry
Sean O'Brien | Donna Knox
Scott Stewart | Jason Sinnamon
Sharon Johnson | Antonio Padilha

## OpsCons
Monday 24 July 2006 |  |  | Tuesday 25 july 2006 |  |  | Friday 28 July 2006
PROCESS TRAINING |  |  | PROCESS TRAINING |  |  | TOOL TRAINING
Operations Consulting |  |  | Operations Consulting |  |  | Operations Consulting
Group 1 - OC1 |  |  | Group 1 - OC1 |  |  | Group 1 - OC1
Peter Eberle |  |  | Peter Eberle |  |  | Rose
Block 7, Level 9, Computer Training Centre, Room 1 |  |  | Block 7, Level 9, Computer Training Centre, Room 1 |  |  | HP Office
| Name | Confirmed |  | Name | Confirmed |  | Name | Confirmed
1 | Nick Bragg |  | 1 | Nick Bragg |  | 1 | Nick Bragg
2 | Vaya Wang |  | 2 | Vaya Wang |  | 2 | Vaya Wang
3 | Siegy Stahl |  | 3 | Siegy Stahl |  | 3 | Siegy Stahl
4 | John McDonnell |  | 4 | John McDonnell |  | 4 | John McDonnell
5 | Trudy Wilson |  | 5 | Trudy Wilson |  | 5 | Trudy Wilson
6 | Colleen Prideaux |  | 6 | Colleen Prideaux |  | 6 | Colleen Prideaux
7 | Mark Sanderson |  | 7 | Mark Sanderson |  | 7 | Mark Sanderson
8 |  |  | 8 |  |  | 8
Monday 14 August 2006 |  |  | Tuesday 15 August 2006 |  |  | Friday 28 July 2006
PROCESS TRAINING |  |  | PROCESS TRAINING |  |  | TOOL TRAINING
Operations Consulting |  |  | Operations Consulting |  |  | Operations Consulting
Group 2 - OC2 |  |  | Group 2 - OC2 |  |  | Group 2 - OC2
Peter Eberle |  |  | Peter Eberle |  |  | Rose
Block 7, Level 9, Computer Training Centre, Room 1 |  |  | Block 7, Level 9, Computer Training Centre, Room 1 |  |  | Block 7, Level 9, Computer Training Centre, Room 4
| Name | Confirmed |  | Name | Confirmed |  | Name | Confirmed
1 | Suzanne Broderick |  | 1 | Suzanne Broderick |  | 1 | Suzanne Broderick
2 | Peter Lloyd |  | 2 | Peter Lloyd |  | 2 | Peter Lloyd
3 | Mark Waters |  | 3 | Mark Waters |  | 3 | Mark Waters
4 | Phil Lingard |  | 4 | Phil Lingard |  | 4 | Phil Lingard
5 | Ian Cruickshank |  | 5 | Ian Cruickshank |  | 5 | Ian Cruickshank
6 | Therese Tobin |  | 6 | Therese Tobin |  | 6 | Therese Tobin
7 | Natalie Smith |  | 7 | Natalie Smith |  | 7 | Natalie Smith
8 |  |  | 8 |  |  | 8

## BneCity
Mike Ball (Pathology Service Coopers Plains) needs to be scheduled for tool training
Special Session - BC3 - 17, 18 & 22 Aug
Trainer: Dave Lowe
1 | Dzung Ho
2 | Martin Heffernan
3 | Graham Stocks
4 | Ian Vowles
5 | Len Farlow
6
7
8
SMIP Training Program for Brisbane City Cluster
Process Training |  | Tools Training
Date | Name | Date | Name
Monday 7/8 | Lesley | Thursday 10/8 | Lesley
Tuesday 8/8 | Cassandra |  | Cassandra
| Paul |  | Paul
| John |  | John
| Trish |  | Trish
| Beng |  | Beng
| Rob |  | Rob | Sick on day of training
| Glen B |  | Glen B | Unable to attend day
Monday 14/8 | Julie | Monday 21/8 | Julie
Tuesday 15/8 | Karen |  | Karen
| Mick |  | Mick
| Tom |  | Tom
| Amanda |  | Amanda
| Mark |  | Mark
| Matt |  | Matt
|  |  | Glen B | See above
|  |  | Rob | See above

## BneSouth
SMIP - Training Schedule
PAH | Process Training | Process Training | Tool Training | Process Training | Process Training | Tool Training | Process Training | Process Training | Tool Training | Process Training | Process Training | Tool Training
SUPERUSERS: Robbie, Cathi | Thursday | Friday | Monday | Monday | Tuesday | Thurdsay | Monday | Tuesday | Wednesday | Wednesday | Thursday | Friday
| 2006-08-03 | 2006-08-04 | 2006-08-07 | 2006-08-14 | 2006-08-15 | 2006-08-17 | 2006-08-21 | 2006-08-22 | 2006-08-23 | 2006-08-30 | 2006-08-31 | 2006-09-01
ALISTAIR BURTON
BEN TOUSSAINT
BILL FARRANT
CAROL JEFFELS
CHRIS UPTON
CHRISTINE SCHAFER
COREY NUSSEY
HAYDEN KING
JASON NG
JUDY POLL
LARRY TURNER
LISA BUTCHARD
LYN SEHL
MATTHEW LARSEN
MICHAEL FLEMING
MICHAEL SHAWN
MIKE QUINN
NORM RINALDI
PETER HECKMANN
RICHARD GAULT
RON LEWIS
SCOTT FRASER
SCOTT HOCKINGS
STEVEN WHEELER
STUART HILL
TERRY MAY
TIM SEETO
TROY STEWART
QE2 | Process Training | Process Training | Tool Training | Process Training | Process Training | Tool Training | Process Training | Process Training | Tool Training | Process Training | Process Training | Tool Training
SUPERUSERS: Robbie, Cathi | Thursday | Friday | Monday | Monday | Tuesday | Thursday | Monday | Tuesday | Wednesday | Monday | Tuesday | Wednesday
| 2006-08-03 | 2006-08-04 | 2006-08-07 | 2006-08-14 | 2006-08-15 | 2006-08-17 | 2006-08-21 | 2006-08-22 | 2006-08-23 | 2006-08-30 | 2006-08-31 | 2006-09-01
ANNA CHOI
AARON STONE
JESSICA PRENTICE
ROB GREEN
BAYSIDE
GLYNN BROWN
KARIS LABAN
MARINUS LATHOUWERS
NEIL BULGER
THEO WRIGHT
ULF WINKELS
Chris Bedford (pathology Services Coopers Plains) needs to be scheduled for tool training

## BneNorth
ALL SESSIONS FULL |  | 2006-08-08
Super Users
John Williams
Johan Malherbe
GROUP 1 (B North 1)
Tuesday 18 July 2006 |  | Wednesday 19 July 2006 |  |  | Thursday 20 July 2006
Group 1, Session 1 - SMIP Process Theory |  | Group 1, Session 2 - SMIP Process Practical |  |  | Group 1, Session 3 - SMIP HP Tool training
John Williams & Johan Malherbe |  | John Williams & Johan Malherbe |  |  | HP trainer - Peter
Citilink Lobby 2 Level 2 Room 2 |  | Citilink Lobby 2 Level 2 Room 2 |  |  | Block 7, Level 9, Computer Training Unit, Room 4
|  | Name | Bussiness Unit | Location | Confirmed
| 1 | Joe Ahern | SDC | TPCH
| 2 | Janice MacKenzie | SDC | TPCH
| 3 | Steve O'Rourke | SDC | HTN
| 4 | Darren Keating | SDC | HTN
| 5 | Rhys Tan | SDC | HTN
| 6 | Darryl Gilbert | C&N | HTN
| 7 | Mark Genrich | SDC | HTN
| 8 | Amer Ali | ServOps | HTN
GROUP 2 (B North 2)
Monday 24 July 2006 |  | Tuesday 25 July 2006 |  |  |  | Wednesday 26 July 2006
Group 2, Session 1 - SMIP Process Theory |  | Group 2, Session 2 - SMIP Process Practical |  |  |  | Group 2, Session 3 - SMIP HP Tool training
John Williams & Johan Malherbe |  | John Williams & Johan Malherbe |  |  |  | HP trainer - Rose
RBWH, James Main Building, Room 1062 |  | RBWH, James Main Building, Room 1062 |  |  |  | Block 7, Level 9, Computer Training Unit, Room 4
|  | Name | Bussiness Unit | Location | Confirmed
| 1 | Mark Perrett | SDC | HTN
| 2 | Michael Bishop | SDC | TPCH
| 3 | Cameron Rowlatt | SDC | HTN
| 4 | Peter Stewart | SDC | HTN
| 5 | Valentino Steinberg | SDC | HTN
| 6 | Bev Brazier | C&N | HTN
| 7 | Mark Bibo | ServOps | TPCH
8
GROUP 3 (B North 3)
Thursday 27 July 2006 |  | Friday 28 July 2006 |  |  |  | Monday 31 July 2006
Group 3, Session 1 - SMIP Process Theory |  | Group 3, Session 2 - SMIP Process Practical |  |  |  | Group 3, Session 3 - SMIP HP Tool training
Peter Eberle |  | Peter Eberle |  |  |  | HP trainer - Rose
TPCH, Building 14 (Education Centre), Room 9 |  | TPCH, Building 14 (Education Centre), Room 6 |  |  |  | Block 7, Level 9, Computer Training Unit, Room 4
|  | Name | Bussiness Unit | Location | Confirmed
| 1 | Charmaine Carr | Assist SDC | TPCH
| 2 | Nigel Finn | SDC | TPCH
| 3 | Kevin Welch | SDC | HTN
| 4 | Graeme Johnstone | SDC | HTN
| 5 | Cuong Luu | C&N | TPCH
| 6 | Trevor Forno | ServOps | HTN
| 7 | Mike Allen | ServOps | HTN
8
GROUP 4 (B North 4)
Tuesday 1 August 2006 |  | Wednesday 2 August 2006 |  |  |  | Thursday 3 August 2006
Group 4, Session 1 - SMIP Process Theory |  | Group 4, Session 2 - SMIP Process Practical |  |  |  | Group 4, Session 3 - SMIP HP Tool training
John Williams & Johan Malherbe |  | John Williams & Johan Malherbe |  |  |  | HP trainer - Muthu
Block 7, Level 9, Computer Training Unit, Room 1 |  | Block 7, Level 9, Computer Training Unit, Room 1 |  |  |  | HP Office, 18 Little Cribb street, Milton
|  | Name | Bussiness Unit | Location | Confirmed
| 1 | Deb Wilson-Parsons | Admin | HTN
| 2 | Simon Patmore | SDC | TPCH
| 3 | Lucas Balucinski | SDC | HTN
| 4 | David Shaw | SDC | HTN
| 5 | Marion Grinlinton | ServOps | HTN
| 6 | David McGovern | ServOps | HTN
| 7 | Gareth Hughes | ServOps | TPCH
| 8 | Andre Steenberg | ServOps | TPCH
GROUP 5 (B North 5)
Monday 7 August 2006 |  | Tuesday 8 August 2006 |  |  |  | Wednesday 9 August 2006
Group 5, Session 1 - SMIP Process Theory |  | Group 5, Session 2 - SMIP Process Practical |  |  |  | Group 5, Session 3 - SMIP HP Tool training
Peter Eberle |  | Peter Eberle |  |  |  | HP trainer - Neil
Block 7, Level 9, Computer Training Unit, Room 1 |  | Block 7, Level 9, Computer Training Unit, Room 1 |  |  |  | HP Office, 18 Little Cribb street, Milton
|  | Name | Bussiness Unit | Location | Confirmed
| 1 | Bec Thompson | Admin | HTN
| 2 | Fiona Reed | SDC | TPCH
| 3 | Catherine Cambie | SDC | HTN
| 4 | Stephen Thomas | SDC | HTN
| 5 | Robert Holdsworth | SDC | HTN
| 6 | Michael Devries | C&N | HTN
| 7 | Scott Mellon | ServOps | HTN
| 8 | Brett Tomes | ServOps | TPCH
GROUP 6 (B North 6)
Thursday 10 August 2006 |  | Friday 11 August 2006 |  |  |  | Monday 14 August 2006
Group 6, Session 1 - SMIP Process Theory |  | Group 6, Session 2 - SMIP Process Practical |  |  |  | Group 6, Session 3 - SMIP HP Tool training
John Williams & Johan Malherbe |  | John Williams & Johan Malherbe |  |  |  | HP trainer - Rose
Citilink Lobby 2, Level 2, Room 2 |  | Citilink Lobby 2, Level 2, Room 2 |  |  |  | Block 7, Level 9, Computer Training Unit, Room 4
|  | Name | Bussiness Unit | Location | Confirmed
| 1 | Erik Bilsten | SDC | TPCH
| 2 | Matthew Coyle | SDC | HTN
| 3 | Julie Hall | SDC | HTN
| 4 | Ian Neale | SDC | HTN
| 5 | Craig Verrall | C&N | HTN
| 6 | Brenda Ball | ServOps | HTN
| 7 | Mark Missenden | ServOps | HTN
| 8 | Alison McCall | ServOps | HTN
GROUP 7 (B North 7)
Monday 14 August 2006 |  | Tuesday 15 August 2006 |  |  |  | Thursday 17 August 2006
Group 7, Session 1 - SMIP Process Theory |  | Group 7, Session 2 - SMIP Process Practical |  |  |  | Group 7, Session 3 - SMIP HP Tool training
John Williams & Johan Malherbe |  | John Williams & Johan Malherbe |  |  |  | HP trainer - Rose
Citilink building, lobby 1, level 3, conference rooms 1&2 |  | Citilink building, lobby 1, level 3, conference rooms 1&2 |  |  |  | HP Office, 18 Little Cribb street, Milton
|  | Name | Bussiness Unit | Location | Confirmed
| 1 | Richard Carlos Torr | SDC | TPCH
| 2 | Shane Russell | SDC | HTN
| 3 | Huy huyn (Sonny) | SDC | HTN
| 4 | Trevor Parsons | SDC | HTN
| 5 | Admin Officer | C&N | HTN
| 6 | Rob Muir | ServOps | HTN
| 7 | Claire Hauville | ServOps | TPCH
| 8 | Julie Kessler | ServOps | HTN
GROUP 8 (B North 8)
Thursday 17 August 2006 |  | Friday 18 August 2006 |  |  |  | Monday 21 August 2006
Group 8, Session 1 - SMIP Process Theory |  | Group 8, Session 2 - SMIP Process Practical |  |  |  | Group 8, Session 3 - SMIP HP Tool training
John Williams & Johan Malherbe |  | John Williams & Johan Malherbe |  |  |  | HP trainer - Glen
Block 7, Level 9, Computer Training Unit, Room 1 |  | Block 7, Level 9, Computer Training Unit, Room 1 |  |  |  | HP Office, 18 Little Cribb street, Milton
|  | Name | Bussiness Unit | Location | Confirmed
| 1 | Ian Missenden | SDC | Both
| 2 | Mark Pryce-Davies | SDC | HTN
| 3 | Daniel Loughlan | SDC | HTN
| 4 | Morgan Pascoe | SDC | HTN
| 5 | Ewan Dawson | C&N | HTN
| 6 | Saul lethbridge | ServOps | HTN
| 7 | BNC - Cluster Manager | Clus Man | HTN
| 8 | Karly Missenden | Admin | TPCH

## GoldC
GOLD COAST
31st July – 1st August and 3rd August
Process training on 31st and 1st. HP Openview 3rd
Jess Mitchell
Shaun Clancy
Alicia Josey
James Kell
Ryan White
Chris Byrne
Rob Green
Chris Campion
Damian White
7th August – 9th August
Process training on 7th and 8th. HP Openview 9th
Chris McVeigh
Kevin Dicker
Peta Cunningham
Rob Geraghty
Adrian Strutton
Geoff Dowton
Andrew Brincat
Tim Galloway
Geoff Rhodes
Peter Riley

## Sunsh
Super Users
Andrew Lambton | 5470 6334
Steve Jorgensen | 3883 7003
SMIP Training
Session 1 Caboolture
Process Training | HP Tool Training
3-4 Aug | 2006-08-07
Louise Thorsen | Louise Thorsen
Robert Alker | Robert Alker
John Wildman | John Wildman
Sergey Zarenkov | Sergey Zarenkov
Session 2 Caloundra
Process Training | HP Tool Training
10-11 Aug | 2006-08-16
Brian Brodie | Brian Brodie
John Flemming | John Flemming
Steve Munro | Steve Munro
Tony Johnson | Tony Johnson
Lauren Reynolds | Lauren Reynolds
Marion Crowley | Marion Crowley
Session 3 Caboolture
Process Training | HP Tool Training
17-18 Aug | 2006-08-24
Neil Lintern | Neil Lintern
Craig McGuire | Craig McGuire
Barry Wedd | Barry Wedd
Darren Bonelli | Darren Bonelli
Jenni McCarthy | Jenni McCarthy
Session 4 Caloundra
Process Training | HP Tool Training
22-23 Aug | 2006-08-25
Allan Reid | Allan Reid
Scott Buckle | Scott Buckle
Luis Castro | Luis Castro
Ian Gebhard | Ian Gebhard
Andrew Simons | Andrew Simons
Jo Williams | Jo Williams
Evan Wallace | Evan Wallace
Trainers
Steve Jorgensen
Andrew Lambton

## SWest
Super Users
Scott Cybulski | 4616 6156
Jon Peel | 3810 1489 |  | SMIP TRAINING
|  |  | Group 1 | Ipswich Lv9 Training room | 25-26-27 July
SMIP TRAINING |  |  |  | Name | ID Unit
Group 1 | Ipswich Lv9 Training room | 25-26-27 July | 1 | Dinesh Galappaththi | IGH
| Name | ID Unit | 2 | Josh Smith | IGH
1 | Dinesh Galappaththi | IGH | 3 | Lorraine Gouldson | IGH
2 | Jackie Reibelt | SDD | 4 | Heath Brown | SDD
3 | Lorraine Gouldson | IGH | 5 | Lori Jordan | Tmba
4 | Josh Mackey | IGH | 6 | Travis Lord | Tmba
5 | Lori Jordan | Tmba | 7 | Graham Fitz | Tmba
6 | Travis Lord | Tmba | 8 | Mark Maloney | Tmba
7 | Graham Fitz | Tmba
8 | Mark Maloney | Tmba | Group 2 | Ipswich Lv9 Training room | 31 July 1-2 August
|  |  |  | Name | ID Unit
Group 2 | Ipswich Lv9 Training room | 31 July 1-2 August | 1 | James Carlson | IGH
| Name | ID Unit | 2 | Anthony Say | IGH
1 | James Carlson | IGH | 3 | Josh Mackey | IGH
2 | Anthony Say | IGH | 4 | Ida Parker | SDD
3 | Heath Brown | SDD | 5 | Cameron Daff | Tmba
4 | Ida Parker | SDD | 6 | Jo Taylor | Tmba
5 | Cameron Daff | Tmba | 7 | Gini | Tmba
6 | Jo Taylor | Tmba | 8 | Anne | Tmba
7 | Gini | Tmba | 9 | Mark Constable | IGH
8 | Anne | Tmba
9 | Mark C | IGH | Group 3 | Toowoomba | 8-9, 15 August
|  |  |  | Name | ID Unit
Group 3 | Toowoomba | 8-9, 15 August | 1 | David Luck | Tmba
| Name | ID Unit | 2 | David Haeusler | Tmba
1 | David Luck | Tmba | 3 | Ben Kennedy | IGH
2 | David Haeusler | Tmba | 4 | Chris C | Tmba
3 | Ben Kennedy | IGH | 5 | Jon Moller | IGH
4 | Chris C | Tmba | 6 | Jackie Reibelt | SDD
5 | Jon Moller | IGH | 7 | Clayton McAndrew | IGH
6 | Josh Smith | IGH | 8 | Kate Moller | IGH
7 | Clayton McAndrew | IGH | 9 | Lucy Oliver | Tmba
8 | Kate Moller | IGH
|  |  | Group 4 | Toowoomba | 14-15, 18 August
Group 4 | Toowoomba | 14-15, 18 August |  | Name | ID Unit
| Name | ID Unit | 1 | Kevin Ross | Roma
1 | Kevin Ross | Roma | 2 | Barry Hinz | C'Ville
2 | Barry Hinz | C'Ville | 3 | Howard Inskip | Ndowns
3 | Lucy Oliver | Tmba | 4 | Ming Yen Barthelot | Tmba
4 | Ming Yen Barthelot | Tmba | 5 | Andrew Dieckmann | IGH
5 | Andrew Dieckmann | IGH | 6 | Anissa Lee | IGH
6 | Anissa Lee | IGH | 7 | Ian Adcock | IGH
7 | Ian Adcock | IGH | 8 | Eric Hellyar | IGH
8 | Eric Hellyar | IGH | 9 | Mike Trott | IGH
9 | Mike Trott | IGH

## Central
Super Users
| Chris Wright | 4920 6206
| Scott Catterall | 4968 6486
| Lisa Carter | 4122 8387
Wednesday 19, Thursday 20 July 2006 |  |  | Friday 21 July 2006 |  |  |  | Key
InfoOperations |  |  | InfoOperations |  |  |  | Bundaberg
CENTRAL 1 |  |  | CENTRAL 1 |  |  |  | Gladstone
Scott Catterall, Chris Wright |  |  | Glenn Spicer |  |  |  | Kingaroy
Yangulla Training Room |  |  | Yangulla Training Room |  |  |  | Mackay
| Name | Confirmed |  | Name | Confirmed |  | Maryborough
1 | Judy Hansen | Y | 1 | Judy Hansen | Y |  | Rockhampton
2 | Barb Cowan | Y | 2 | Barb Cowan | Y
3 | Scott Catterall | Y | 3 | Scott Catterall | Y
4 | Mark Schalch | Y | 4 | Mark Schalch | Y
5 | Geoff Geddes | Y | 5 | Geoff Geddes | Y |  | Adam Bulloch | BNE has organised
6 | Brenda Horstman | Y | 6 | Brenda Horstman | Y |  | Bradley Raatz
7 |  |  | 7 |  |  |  | Brett Hayes
8 |  |  | 8 |  |  | Spare | Daniel Rye
David Williams
Monday 24, Tuesday 25 July 2006 |  |  | Wednesday 26 July 2006 |  |  |  | Gary Kneen
InfoOperations |  |  | InfoOperations |  |  |  | Geoff Geddes
CENTRAL 2 |  |  | CENTRAL 2 |  |  |  | Gordon Clark
Scott Catterall, Chris Wright |  |  | Glenn Spicer |  |  |  | Jake Simpson
Yangulla Training Room |  |  | Yangulla Training Room |  |  |  | Kathlene Richardson
| Name | Confirmed |  | Name | Confirmed |  | Linda Hiscox
1 | Doug Meiers | Y | 1 | Doug Meiers | Y |  | Mark Schalch
2 |  |  | 2 |  |  |  | Murray Scown
3 |  |  | 3 |  |  |  | Shane Wright
4 | Murray Scown | Y | 4 | Murray Scown | Y |  | Simon Cox
5 | Jake Simpson | Y | 5 | Jake Simpson | Y |  | Steve Rye
6 | Steve Rye | Y | 6 | Steve Rye | Y |  | Brenda Horstman
7 | Gary Kneen |  | 7 | Gary Kneen
8 |  |  | 8 |  |  | Spare
Wednesday 26, Thursday 27 July 2006 |  |  | Friday 28 July 2006
InfoOperations |  |  | InfoOperations
CENTRAL 3 |  |  | CENTRAL 3
Lisa Carter |  |  | Glenn Spicer
Maryborough |  |  | Maryborough
| Name | Confirmed |  | Name | Confirmed
1 | Russell Larsen | Y | 1 | Russell Larsen | Y
2 | Robert Seaman |  | 2 | Robert Seaman
3 | Martin Rollings |  | 3 | Martin Rollings
4 | Trudy McLean | Y | 4 | Trudy McLean | Y
5 | Kathlene Richardson | Y | 5 | Kathlene Richardson | Y
6 | Linda Hiscox | Y | 6 | Linda Hiscox | Y
7 | Andrew Murray |  | 7 | Andrew Murray
8 | Rod Fisher | Y | 8 | Rod Fisher | Y
Monday 31 July, Tuesday 1 August 2006 |  |  | Wednesday 2 August 2006
InfoOperations |  |  | InfoOperations
CENTRAL 4 |  |  | CENTRAL 4
Lisa Carter |  |  | Glenn Spicer
Maryborough |  |  | Maryborough
| Name | Confirmed |  | Name | Confirmed
1 | Darren Atkins | Y | 1 | Darren Atkins | Y
2 | Jason Luhrs |  | 2 | Jason Luhrs
3 | Adam Darcy | Y | 3 | Adam Darcy | Y
4 | Meghan Kennett | Y | 4 | Meghan Kennett | Y
5 | Hew Reid | Y | 5 | Hew Reid | Y
6 | Dan Rye | Y | 6 | Dan Rye | Y
7 | Brett Hayes | Y | 7 | Brett Hayes | Y
8 | Rick Henson | Y | 8 | Rick Henson | Y
Wednesday 2, Thursday 3 August 2006 |  |  | Friday 4 August 2006
InfoOperations |  |  | InfoOperations
CENTRAL 5 |  |  | CENTRAL 5
Scott Catterall |  |  | Glenn Spicer
Yangulla Training Room |  |  | Yangulla Training Room
| Name | Confirmed |  | Name | Confirmed
1 | Greg Weiss | Y | 1 | Greg Weiss | Y
2 | Chris Kenny | Y | 2 | Chris Kenny | Y
3 | Simon Cox |  | 3 | Simon Cox
4 | Gordon Clark | Y | 4 | Gordon Clark | Y
5 | Shane Wright | Y | 5 | Shane Wright | Y
6 | Dave Williams | Y | 6 | Dave Williams | Y
7 | Bradley Raatz |  | 7 | Bradley Raatz
8 |  |  | 8 |  |  | Spare
Updated Monday 19 June

## North
Super Users
Wynita Bode |  | 4796 1900
Kris Johns |  | 4050 8775
|  | Townsville Based Training | [7 empty] | HP ServDsk | Cairns Based Training
|  | Proc Trg | Proc Trg | HP ServDsk | Proc Trg | Proc Trg | HP ServDsk | Proc Trg | Proc Trg | Proc Trg | Proc Trg | HP ServDsk | Proc Trg | Proc Trg | HP ServDsk
CAIRNS (8 PC) | 2006-08-01 | Mon 31 | Tue 1 | Wed 2 | Wed 9th | Thur 10th | Frid 11th | Mon 14th | Tue 15th | Wed 16th | Thur 17th | Frid 18th | Mon 21st | Tues 22nd | Wed 23rd
Technology Officers | Staff Member | [14 empty] | Requires Travel
Senior Admin Officer | Lorraine Westley | [8 empty] | 1
Infrastructure Coordinator (Acting temp) | Warren Armstrong
Duty Tech (temp) | Richard Braithwaite | [11 empty] | 1
WSR tech (temp) | Daniel Hill | [11 empty] | 1
Senior Technology Officers | Staff Member
Telecoms | Carlo Chiarotto | [11 empty] | 1
Telecoms | Robert Newson |  |  |  | 1 | [10 empty] | 1
CNS-Regional (temp) | Vlad Andreski | 1 | [13 empty] | 1
CNS-Regional (temp) | James Forrest | [8 empty] | 1
CNS-Community (temp) | Scott Gilespie |  |  |  | 1 | [10 empty] | 1
CNS-CBH (temp) | Ashley Cooper | [8 empty] | 1
Principle Technology Officers | Staff Member
PTO Servers | Scott Peden | 1 | [13 empty] | 1
PTO Servers | Marty Webb |  |  |  | 1 | [10 empty] | 1
PTO Networks | Paul Brierley | 1 | [13 empty] | 1
PTO Service Delivery (Acting) | Sharon Young | [8 empty] | 1
PTO Torres (temp) | TBA | [11 empty] | 1 |  |  | 1
PTO Cape (temp) | Ian Ross |  |  |  | 1 | [10 empty] | 1
Storage Administrator EBM | Tony Whitchurch | [8 empty] | 1
Site Manager | Peter Bombardieri | [11 empty] | 1
Total - 17 staff | [15 empty] | Total staff requiring travel
8
|  | Townsville Based Training | [7 empty] | HP ServDsk | Cairns Based Training
|  | Proc Trg | Proc Trg | HP ServDsk | Proc Trg | Proc Trg | HP ServDsk | Proc Trg | Proc Trg | Proc Trg | Proc Trg | HP ServDsk | Proc Trg | Proc Trg | HP ServDsk
TOWNSVILLE (9PC) | 2006-08-01 | Mon 31 | Tue 1 | Wed 2 | Wed 9th | Thur 10th | Frid 11th | Mon 14th | Tue 15th | Wed 16th | Thur 17th | Frid 18th | Mon 21st | Tues 22nd | Wed 23rd
Technology Officers | Staff Member | [14 empty] | Requires Travel
Technology Officers | Jodee Koppe | [8 empty] | 1 | [5 empty] | 1
Technology Officers | Matthew Fox | 1
Technology Officers | Position Vacant
Technology Officers (Currently working for District IT) | Maria Ambler | [6 empty] | 1
Technology Officers (Asset Manager) | Kelly Cameron | [6 empty] | 1
Technology Officer (Longreach) | Position Vacant
Technology Officers | Peter Frisken | 1
Technology Officers | Michael Foley |  |  |  | 1
Technology Officers (Mt Isa) | Tanya Gower | [8 empty] | 1 | [5 empty] | 1
Senior Technology Officers | Staff Member
Senior Technology Officers | Tom Earl |  |  |  | 1
Senior Technology Officers | Trevor Dunstan | [8 empty] | 1 | [5 empty] | 1
Senior Technology Officers | Gareth Wensley | [6 empty] | 1
Senior Technology Officer (Longreach) | Calen Little | 1
Telecommunication Officers | Staff Member
Senior Telecommunication Officer | Danny Brierley | [6 empty] | 1
Senior Telecommunication Officer | Greg Wiszniewski | 1
Senior Telecommunication Officer (Currently on Project) | Jeff Singleton | 1
Senior Telecommunication Officer (Mt Isa) | Ian Heuschele |  |  |  | 1
Principle Technology Officers | Staff Member
PTO - Servers | Adrian Gori |  |  |  | 1
PTO - Networks | Position Vacant
PTO - Servers | Paul Groth | 1
PTO - Mt Isa | Jeff Downing | [11 empty] | 1 |  |  | 1
PTO - Longreach | David K |  |  |  | 1 | [10 empty] | 1
PTO - CT/Bow | Nick Exarhos | [6 empty] | 1
Admin Support Officer/Management | Staff Member
Senior Admin Officer | Kelleigh Hall |  |  |  | 1
Cluster Manager | Ian Kiely | [11 empty] | 1 |  |  | 1
Site Manager | Chris Crooks | [6 empty] | 1
Trainee - TSV | Adam Grigolato | [6 empty] | 1
Trainee - Longreach | Ash Hughes | 1 | [13 empty] | 1
A/Site Manager | Janiece Stark | [6 empty] | 1
Total staff - 30 | [15 empty] | Total staff requiring travel
7
| Townsville | 10 |  |  | 10 |  |  | 8
| Cairns | [8 empty] | 8 |  |  | 7

## Rooms
INFORMATION ON BRISBANE BASED TRAINING ROOM & FACILITIES
Please contact Melinada Vilches on 3636 2024 (SMIP project coordinator) for collection of laptop & datapro where they have been booked
| WEEK 1: 17 - 21 July 2006 |  |  |  |  | WEEK 2: 24 - 28 July 2006 |  |  |  |  | WEEK 3: 31 July - 4 August 2006 |  |  |  |  | WEEK 4: 7 - 11 August 2006 |  |  |  |  | WEEK 5: 14 - 18 August 2006 |  |  |  |  | WEEK 6: 21 - 25 August 2006
| Mon 17 | Tue 18 | Wed 19 | Thu 20 | Fri 21 | Mon 24 | Tue 25 | Wed 26 | Thu 27 | Fri 28 | Mon 31 | Tue 1 | Wed 2 | Thu 3 | Fri 4 | Mon 7 | Tue 8 | Wed 9 | Thu 10 | Fri 11 | Mon 14 | Tue 15 | Wed 16 | Thu 17 | Fri 18 | Mon 21 | Tue 22 | Wed 23 | Thu 24 | Fri 25
Computer Training Centre Block 7 Level 9 Laptop & datapro in room | CTC 1 | CTC 1 |  | CTC 1 | CTC 1 | CTC 1 | CTC 1 | CTC 1 | CTC 1 | CTC 1 | CTC 1 | CTC 1 | CTC 1 | CTC 1 | CTC 1 | CTC 1 | CTC 1 | CTC 1 | CTC 1 | CTC 1 | CTC 1 | CTC 1 |  | CTC 1 | CTC 1 | CTC 1 | CTC 1 |  | CTC 1
Block 7 Level 11 | WEEK 2: 24 - 28 July 2006 Wed 26: room 101 Laptop & data pro is booked; WEEK 2: 24 - 28 July 2006 Thu 27: room 101 Laptop & data pro is booked
James Mayne Building Laptop & datapro are either in the room or are booked and need to be collected
James Mayne Building Laptop & datapro are either in the room or are booked and need to be collected | WEEK 1: 17 - 21 July 2006 Mon 17: room 1061. Data pro in room Laptop is booked; WEEK 1: 17 - 21 July 2006 Tue 18: room 1061. Data pro in room Laptop is booked; WEEK 2: 24 - 28 July 2006 Mon 24: room 1061. Data pro in room Laptop is booked; WEEK 4: 7 - 11 August 2006 Thu 10: room 1061. Data pro in room Laptop is booked; WEEK 5: 14 - 18 August 2006 Mon 14: room 1061. Data pro in room Laptop is booked; WEEK 5: 14 - 18 August 2006 Tue 15: room 1061. Data pro in room Laptop is booked
James Mayne Building Laptop & datapro are either in the room or are booked and need to be collected | WEEK 1: 17 - 21 July 2006 Mon 17: room 1062. Laptop & SMIP data pro is booked; WEEK 1: 17 - 21 July 2006 Tue 18: room 1062. Laptop & SMIP data pro is booked; WEEK 2: 24 - 28 July 2006 Mon 24: room 1062. Laptop & InfoSolutions Data pro is booked; WEEK 2: 24 - 28 July 2006 Tue 25: room 1062. Laptop & SMIP Data pro is booked; WEEK 5: 14 - 18 August 2006 Mon 14: room 1062. Laptop & SMIP Data pro is booked; WEEK 5: 14 - 18 August 2006 Tue 15: room 1062. Laptop & SMIP Data pro is booked
James Mayne Building Laptop & datapro are either in the room or are booked and need to be collected | WEEK 2: 24 - 28 July 2006 Mon 24: room 2043. Laptop & SMIP Data pro is booked; WEEK 2: 24 - 28 July 2006 Tue 25: room 2043. Laptop & InfoSolutions data pro is booked
James Mayne Building Laptop & datapro are either in the room or are booked and need to be collected | WEEK 2: 24 - 28 July 2006 Tue 25: room 2200 Laptop & Block 7 Data pro is booked
TPCH Education Centre, Ground Floor, Building 14 | WEEK 2: 24 - 28 July 2006 Thu 27: room 9 PC and Data pro in room; WEEK 2: 24 - 28 July 2006 Fri 28: room 6 PC and Data pro in room; WEEK 3: 31 July - 4 August 2006 Mon 31: room 6 PC and Data pro in room; WEEK 3: 31 July - 4 August 2006 Tue 1: room 6 PC and Data pro in room; WEEK 3: 31 July - 4 August 2006 Wed 2: room 6 PC and Data pro in room; WEEK 3: 31 July - 4 August 2006 Thu 3: room 6 PC and Data pro in room
Citilink Building Lobby 2 Level 2 | WEEK 1: 17 - 21 July 2006 Tue 18: Conference room 2. Laptop & SMIP Data pro is booked; WEEK 1: 17 - 21 July 2006 Wed 19: Conference room 2. Laptop & SMIP Data pro is booked; WEEK 1: 17 - 21 July 2006 Thu 20: Conference room 2. Laptop & SMIP Data pro is booked; WEEK 1: 17 - 21 July 2006 Fri 21: Conference room 2. Laptop & SMIP Data pro is booked; WEEK 3: 31 July - 4 August 2006 Fri 4: Conference room 2. Laptop & InfoSolutions Data pro is booked; WEEK 4: 7 - 11 August 2006 Mon 7: Conference room 2. Laptop & SMIP Data pro is booked; WEEK 4: 7 - 11 August 2006 Thu 10: Conference room 2. Laptop & SMIP Data pro is booked; WEEK 4: 7 - 11 August 2006 Fri 11: Conference room 2. Laptop & SMIP Data pro is booked; WEEK 6: 21 - 25 August 2006 Wed 23: Conference room 2. Laptop & SMIP Data pro is booked
Citilink Building Lobby 2 Level 2 | WEEK 1: 17 - 21 July 2006 Wed 19: Conference room 3. Laptop & InfoSolutions Data pro is booked; WEEK 1: 17 - 21 July 2006 Thu 20: Conference room 3. Laptop & InfoSolutions Data pro is booked; WEEK 4: 7 - 11 August 2006 Thu 10: Conference room 3. Laptop & Block 7 L8 Data pro is booked; WEEK 4: 7 - 11 August 2006 Fri 11: Conference room 3. Laptop & Block 7 L8 Data pro is booked
Citilink Building Lobby 1 Level 3 | WEEK 3: 31 July - 4 August 2006 Thu 3: Conference room 1 & 2. Laptop & SMIP Data pro is booked; WEEK 3: 31 July - 4 August 2006 Fri 4: Conference room 1 & 2. Laptop & SMIP Data pro is booked; WEEK 5: 14 - 18 August 2006 Mon 14: Conference rooms 1 & 2. laptop & InfoSolutions Data pro is booked; WEEK 5: 14 - 18 August 2006 Tue 15: Conference rooms 1 & 2. laptop & InfoSolutions Data pro is booked
PAH Training room 2, Lower Ground floor, Building 15. Collect key from ground floor reception. Ask for key to tea room. | WEEK 1: 17 - 21 July 2006 Wed 19: room 2. Laptop & datapro & PCs in room; WEEK 5: 14 - 18 August 2006 Tue 15: room 2. Laptop & datapro & PCs in room

## Catchup
CATCH UP TRAINING
Please put names on this list of people who has missed the training sessions pre go-live
Name | Area | Comments
Catherine Fox | SIM | She works parttime on Mon and Tue. Training schedule could not accommodate a tool session on these dates. Hiske has agreed with her that she will attend process training on 21 and 22 Aug, she will obtain a tool manual from her colleague and do self study once the system goes live. She would like the opportunity to attend a catch up session once we have enough attendants.
Special Tool Training Session
1 |  | Peter Nicholls
2 |  | Jenni McCarthy
3 |  | Graham Friederich
4 |  | Gary Penrose
5 |  | Alison McCall
6 |  | Brenda Ball
7 |  | Donna Knox
8
9

## SuperUsers
Super User Sessions |  |  | On Leave
Tue 12 Sep | Tue 19 Sep
Peter Eberle | Chris Carrall | 1 | David Lowe
Corey Nussey | John Peel | 2 | Colin McCrow
Robbie Brescia | Scott Cybulski | 3
Pallavi Mohan | Peter Imecs | 4
Joy Jorgensen | Lee Newton | 5 | Joy Jorgensen
Peter Douwes | David Maiden | 6 | Adam Dixon
Paul Cox | Tanya Davis | 7 | Andrew Lambton
Glenn Hazeldine | Marie-Louise Samundsett | 8 | Carl Brown
Scott Catterall | David Lowe | 9 | Cathi Ryan
Wynita Bode | Mike Ball - Pathology | 10 | Chris Carrall
Kris Johns | Sonja Toogood - Telehealth 64831 | 11 | Chris Wright
Andrew Lambton | 1 Change Control Coordinator | 12 | Colin McCrow
Steve Jorgensen | John Williams | 13 | Corey Nussey
1 Change Control Coordinator | Johan Malherbe | 14 | David Lowe
| Cathi Ryan | 15 | David Maiden
|  | 16 | Glen Turvey
|  | 17 | Glenn Hazeldine
Peter Locke |  |  | Johan Malherbe
Lisa Carter |  |  | John Williams
Glen Turvey |  |  | Jon Peel
Kris Johns
Lee Newton
Lisa Carter
Marie-Louise Samundsett
Pallavi Mohan
Paul Cox
Peter Douwes
Peter Eberle
Peter Imecs
Peter Locke
Robbie Brescia
Scott Catterall
Scott Cybulski
Steve Jorgensen
Tanya Davis
Wynita Bode

## Attendance
| CODE | DATE | TOOL | S/U | HP | ATT | EVAL | NUMBERS
1 | SERV1 | 2006-07-17 | 2006-07-18 | Pallavi/Peter
2 | SERV2 | 2006-07-19 | 2006-07-26
3 | SERV3 | 2006-07-20 | 2006-07-27
4 | SERV4 | 2006-07-21 | 2006-07-28
5 | SERV5 | 2006-08-02 | 2006-08-09
6 | SERV6 | 2006-07-31 | 2006-08-10
7 | SERV7 | 2006-08-01 | 2006-08-11
8 | SERV8 | 2006-08-15 | 2006-08-30
9 | SERV9 | 2006-08-17 | 2006-08-24
10 | SERV10 | 2006-08-18 | 2006-08-25
11 | TO1 | 2006-07-17 | 2006-07-19
12 | TO2 | 2006-07-20 | 2006-07-25
13 | TO3 | 2006-07-24 | 2006-07-27
14 | TO4 | 2006-07-26 | 2006-07-28
15 | TO5 | 2006-07-31 | 2006-08-02
16 | TO6 | 2006-08-03 | 2006-08-08
17 | TO7 | 2006-08-10 | 2006-08-15
18 | TO8 | 2006-08-14 | 2006-08-21
19 | TA1 | cancelled | cancelled
20 | TA2 | 2006-07-28 | 2006-08-01 | Carl |  |  | x
21 | TA3 | 2006-08-03 | 2006-08-07
22 | TA4 | ? | ?
23 | BCC1 | 2006-08-07 | 2006-08-10 | Glen Turvey |  | x |  | 8
24 | BCC2 | 2006-08-14 | 2006-08-21
25 | BCC3 | 2006-08-17 | 2006-08-22
26 | GOLD1 | 2006-07-24 | 2006-07-26 | Paul Cox |  |  | x
27 | GOLD2 | 2006-07-31 | 2006-08-03
28 | GOLD3 | 2006-08-07 | 2006-08-09
29 | B SOUTH1 | 2006-08-02 | 2006-08-04
30 | B SOUTH2 | 2006-08-10 | 2006-08-14
31 | B SOUTH3 | 2006-08-14 | 2006-08-17
32 | B SOUTH4 | 2006-08-21 | 2006-08-23
33 | SI1 | 2006-07-17 | 2006-07-19 | Chris Carrall |  | x | x | 6
34 | SI2 | 2006-07-20 | 2006-07-24 | Tanya |  |  | x
35 | SI3 | 2006-07-26 | 2006-08-01
36 | SI4 | 2006-08-02 | 2006-08-04 | David Lowe |  | x | x | 8
37 | SI5 | 2006-08-04 | 2006-08-08 | David Lowe |  | x | x | 7
38 | SI6 | 2006-08-09 | 2006-08-11
39 | SI7 | 2006-08-10 | 2006-08-11 | David Lowe |  | x | x | 7
40 | SI8 | 2006-08-14 | 2006-08-18
41 | SI9 | 2006-08-21 | 2006-08-23
42 | SI10 | 2006-08-23 | 2006-08-25
43 | OC1 | 2006-07-24 | 2006-07-28 | Peter Eberle |  |  | x
44 | OC2 | 2006-08-14 | 2006-08-22 | Peter Eberle
45 | B NORTH1 | 2006-07-18 | 2006-07-20 | Johan/John | x | x | x | 8
46 | B NORTH2 | 2006-07-24 | 2006-07-26 | Johan/John | x | x | x | 7
47 | B NORTH3 | 2006-08-27 | 2006-07-31
48 | B NORTH4 | 2006-08-01 | 2006-08-03
49 | B NORTH5 | 2006-08-07 | 2006-08-09
50 | B NORTH6 | 2006-08-10 | 2006-08-14
51 | B NORTH7 | 2006-08-14 | 2006-08-17
52 | B NORTH8 | 2006-08-17 | 2006-08-21
53 | SW1 | 2006-07-25 | 2006-07-27
54 | SW2 | 2006-07-31 | 2006-08-02
55 | SW3 | 2006-08-08 | 2006-08-15
56 | SW4 | 2006-08-14 | 2006-08-18
57 | SUN1 | 2006-08-03 | 2006-08-07
58 | SUN2 | 2006-08-10 | 2006-08-16
59 | SUN3 | 2006-08-17 | 2006-08-24
60 | SUN4 | 2006-08-22 | 2006-08-25
61 | CENT1 | 2006-07-19 | 2006-07-21 | Chris | x | x | x | 5
62 | CENT2 | 2006-07-24 | 2006-07-26 | Chris |  | x | x | 5
63 | CENT3 | 2006-07-26 | 2006-08-04 | Chris |  | x | x | 6
64 | CENT4 | 2006-07-31 | 2006-07-28
65 | CENT5 | 2006-08-02 | 2006-08-04
66 | NORTH1 | 2006-07-31 | 2006-08-02 | Wynita |  | x |  | 10
67 | NORTH2 | 2006-08-09 | 2006-08-11
68 | NORTH3 | 2006-08-14 | 2006-08-16
69 | NORTH4 | 2006-08-16 | 2006-08-18
70 | NORTH5 | 2006-08-21 | 2006-08-23
77