Description

for the

PMP

Copyright© itsm IP 2009

Document Information:

| Prepared By: | Anthony Symons |
| --- | --- |
| Title: | ITSM Consultant |
| Document Version: | 0.1 |
| Document Version Date: |  |

Document Distribution List:

| To | Action | E-Mail |
| --- | --- | --- |

Version History:

| Version | Version Date | Author | Description |
| --- | --- | --- | --- |
| 0.1 | 11-Mar-09 | Anthony Symons | Initial Draft |

Proprietary Notice

This document is the property of itsm Partnership Pty Ltd. All copyright is pursuant to the license by itsm Partnership Pty Ltd accompanying this document.

COPYRIGHT

All information contained in this document which relates to itsm Partnership Pty Ltd shall be kept absolutely confidential.

All {Client Field} employees and their representatives shall not communicate, release or permit the communication of any information or data provided, collected and or developed for the purpose of or in connection with this document except, for the purpose of or in connection with the performance of evaluating the document.

The information contained in this document constitutes trade secrets and/or information that is commercial or financial and confidential or privileged. It is provided to {Client Field} in confidence with the understanding that it cannot, without permission of itsm Partnership Pty Ltd be used or disclosed for any purpose.

©Copyright 2009 itsm Partnership Pty Ltd. All rights reserved.

Table of Contents

1	PMP	5

1.1	Project Plan	5

1.2	Work Breakdown Structure	5

1.3	Risk Management Plan	5

1.4	Quality Plan	5

1.5	Communication Plan	6

# PMP

The Project Plan and its associated documents should be approved by a steering committee, then considered by the governing authority for final approval.

## Project Plan

The Project Plan is a document that describes and brings together the components of a project. In effect, the Project Plan is the guidebook for all to the project. Work Breakdown Structure

A Work Breakdown Structure diagram is necessary.

## Work Breakdown Structure

The Work Breakdown Structure (WBS) is a foundation document in project management and all projects should contain at least a high level WBS that shows the main project products or phases with the main tasks. Then, the WBS can provide the basis for planning and managing the key areas of the project. Risks and costs may be referenced against the WBS, as well as time frames and milestones. MS Project is recommended as a support tool to develop a high level work breakdown structure.

Project plans for larger projects should develop multi-level WBSs. The extent depends on the size of the project. Very large projects may have as many as five levels in the WBS, rarely more, because each level requires the corresponding amount of extra work. Adding a level to a WBS increases workload, as each activity in each level must be tracked and recorded.

A graphical representation of the work breakdown structure can be used in reports to management and steering committees as a visual means of showing the status of the project.

## Risk Management Plan

A separate risk management plan is required for all but very small or limited scope projects, using the iPM Risk Management Plan (RMP) template. Small or limited scope projects may use the RMP template or embed a limited risk table in the Project Plan, as judged by the project manager and governing authorities. It should be noted that the risks identified in the template are IT generic and must be reviewed, augmented and updated to fit all risks specific to the project.

An important factor is that projects are dynamic and risks, as well as their ratings, will change as the project progresses. New risks, unidentified in the early stages, often emerge over time. Therefore, the project manager should review the RMP regularly and make changes and additions, using the Version Control table as a Change Log. The evolving RMP through the execution of a major project should be included as part of steering committee meeting papers. For all projects, a review of high risks, otherwise notable risks and changed risks should be specified in the Project Status Report.

iPM risk components are in line with the Risk Management Standard (AS/NZS 4360:2004).

## Quality Plan

A separate quality plan may be provided, using the Quality Plan template, as appropriate.

Both the quality of the management of the project and the “product” of the project must be addressed. Quality is the “totality of features and characteristics of a product or service that bear on its ability to satisfy stated or implied needs” (ISO8402) . Three aspects of quality are taken into consideration: quality planning and standards, quality assurance and quality control. Each aspect is addressed in the quality plan specific categories.

As a minimum, the Project Plan should include the quality measures and acceptance criteria.

If problems occur with quality, changes in other areas of the project may need to take place, according to the integrated nature of projects.

## Communication Plan

Communication strategies to address stakeholders previously identified in the Project Proposal and any new stakeholders subsequently determined must be formed.

A separate communication plan may be provided, using the Communication Plan template, as appropriate. The template comprises tables for training strategies, and marketing and communication strategies. A well-developed and comprehensive Communication Plan using both tables meets the change management needs for most projects. Keep in mind that managing change is required in all projects to some degree because change is embedded in all projects.

In fact communication is a critical component of every project plan because it provides the vital link between the project, the client and success. When developing a communication plan it is essential to answer the following questions:

Who will be impacted by this project?

What type of change does this project represent, is it only going to affect one department, or the entire customer organisation?

When is this change scheduled to occur?

Where will this change occur, and finally how will those impacted by this change be notified?

By answering these questions it will help you to identify the most appropriate target audience to be communicating with and this will in turn determine the most effective communication mechanisms you need to use in order to convey your message. A communication plan is not static, but rather will develop as the project progresses therefore it is imperative to continually revisit the communication plan and update it as needed.