Monthly Report

for the

Title Field

Copyright© itsm IP 2009

Document Information:

| Prepared By: | Anthony Symons |
| --- | --- |
| Title: | ITSM Consultant |
| Document Version: | 0.1 |
| Document Version Date: |  |

Document Distribution List:

| To | Action | E-Mail |
| --- | --- | --- |

Version History:

| Version | Version Date | Author | Description |
| --- | --- | --- | --- |
| 0.1 | 11-Mar-09 | Anthony Symons | Initial Draft |

Proprietary Notice

This document is the property of itsm Partnership Pty Ltd. All copyright is pursuant to the license by itsm Partnership Pty Ltd accompanying this document.

COPYRIGHT

All information contained in this document which relates to itsm Partnership Pty Ltd shall be kept absolutely confidential.

All {Client Field} employees and their representatives shall not communicate, release or permit the communication of any information or data provided, collected and or developed for the purpose of or in connection with this document except, for the purpose of or in connection with the performance of evaluating the document.

The information contained in this document constitutes trade secrets and/or information that is commercial or financial and confidential or privileged. It is provided to {Client Field} in confidence with the understanding that it cannot, without permission of itsm Partnership Pty Ltd be used or disclosed for any purpose.

©Copyright 2009 itsm IP All rights reserved.

Table of Contents

1	Project/Program Overview	5

1.1	Project/Program Status Summary	5

2	Risk Management	6

2.1	Risk Log	6

2.1.1	Open Risks	6

3	Change Request Log	7

4	Project/Program Milestones	8

5	Project/Program Payment Schedule	9

6	Project/Program Effort Report Summary	10

6.1	Milestone Summary	10

6.2	Resource Plan  (Insert hours and costs in this table directly from the baselined Project Schedule (MS Project Plan)).	10

7	Project/ Program Organisation	11

8	Issues	12

9	Project Financial Report	13

# Project/Program Overview

| Reporting Period: | Eg. March 2009 | Account Manager: | Eg. Gavin McKee |
| --- | --- | --- | --- |

Project/Program Description: (What solution is being delivered)

Eg. Queensland Health, Service Management Implementation Project (SMIP Phase2 Project) AUD$285K with a duration of 12 months: including the ITIL Process Analysis, Design & implementation for Problem, Release & Service Level Management Process Workflows and Automations, and the Implementation of the HP Service Desk & Asset Management software solutions.

## Project/Program Status Summary

| Status | This Reporting Period (Red, Yellow, or Green) | Last Reporting Period (Red, Yellow, or Green) | Comments |
| --- | --- | --- | --- |
| Overall |  |  | Eg. Unit Testing (WBS 4.1) was completed ahead of time to compensate for a planned delay in User Acceptance Testing |
| Customer Satisfaction |  |  |  |
| Financial |  |  |  |
| Schedule |  |  |  |
| Technical Performance |  |  |  |
| Resource |  |  | Eg. Customer Resources weren’t available to sign-off User Acceptance Test Plan |
| Contract/Legal |  |  |  |
| Risk |  |  |  |

Key Accomplishments This Reporting Period

Eg. Unit Testing (WBS 4.1) was completed

Key Planned Activities Next Reporting Period

Eg. User Acceptance Testing (WBS 4.2) will be completed

# Risk Management

## Risk Log

Insert the latest version of the Risk Log as an embedded object.

### Open Risks

Insert the latest version of the Risk Response Plans as embedded objects.

# Change Request Log

Insert the latest version of the Change Request Log as an embedded object.

# Project/Program Milestones

| Project Milestone Description | Dates |  | Revenue |  | Cost |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Planned | Forecast/ Actual | Planned | Forecast/ Actual | Planned | Forecast/ Actual |
| Eg. MIL1.0 Project Statement of Work Signed | 23-Jan-09 | 30-Jan-09 | $18,000 | $16,500 | $15,000 | $17,500 |
| MIL2.0 Project Management Plan Signed | 23-Feb-09 | 28-Feb-09 | $25,000 | $23,500 | $15,000 | $17,500 |
| MIL3.1 Requirements Traceability Matrix Signed | 23-Mar-09 | 30-Mar-09 | $18,000 | $16,500 | $15,000 | $17,500 |
| MIL3.2 Detailed Design Signed | 23-Apr-09 | 30-Apr-09 | $25,000 | $23,500 | $15,000 | $17,500 |
| MIL3.3 Test Plan Signed | 23-May-09 | 30-May-09 | $18,000 | $16,500 | $15,000 | $17,500 |
| MIL4.0 Production RFC Accepted/Signed | 23-Jun-09 | 30-Jun-09 | $25,000 | $23,500 | $15,000 | $17,500 |
| MIL5.0 PIR Report Signed | 23-Jul-09 | 30-Jul-09 | $18,000 | $16,500 | $15,000 | $17,500 |

All dollar amounts detailed within the table are in AUD$ ex-GST.

# Project/Program Payment Schedule

| Payment Milestone # | Invoice Date |  | Payment Date | Payment Amount |  |
| --- | --- | --- | --- | --- | --- |
|  | Planned | Actual |  | Planned | Actual |
| Eg. MIL1.0 Project Statement of Work Signed | 23-Jan-09 | 30-Jan-09 | 28-Feb-09 | $22,000 | $22,000 |
| MIL2.0 Project Management Plan Signed | 23-Feb-09 | 28-Feb-09 | 30-Mar-09 | $32,000 | $32,000 |
| MIL3.1 Requirements Traceability Matrix Signed | 23-Mar-09 | 30-Mar-09 | 30-Apr-09 | $22,000 | $22,000 |
| MIL3.2 Detailed Design Signed | 23-Apr-09 | 30-Apr-09 | 30-May-09 | $32,000 | $32,000 |
| MIL3.3 Test Plan Signed | 23-May-09 | 30-May-09 | 30-Jun-09 | $22,000 | $22,000 |
| MIL4.0 Production RFC Accepted/Signed | 23-Jun-09 | 30-Jun-09 | 30-Jul-09 | $32,000 | $32,000 |
| MIL5.0 PIR Report Signed | 23-Jul-09 | 30-Jul-09 | 30-Aug-09 | $22,000 | $22,000 |

All dollar amounts detailed within the table are in AUD$ ex-GST.

# Project/Program Effort Report Summary

Fill out tables below or attach similar effort plan as an embedded object.

## Milestone Summary

| Phase/Milestone | WBS | Original Hours Planned | Actual Hours (ITD) “Inception To Date” | Remaining Hours (ETC) “Estimate To Complete” | Total Hours (EAC) “Estimate At Complete” | EAC Variance From Last Forecast |
| --- | --- | --- | --- | --- | --- | --- |
| INITIATE PHASE Eg. SoW Signed | WBS 1.0 | 125 | 85 | 75 | 160 | 35 |
| PLAN PHASE Eg. Project Management Plan Signed | WBS 2.0 | 250 | 20 | 240 | 260 | 10 |
| EXECUTE PHASE Eg. Detailed Design Signed | WBS 3.1 | 575 | 0 | 595 | 595 | 20 |
| MONITOR PHASE Eg. Test Plan Signed | WBS 3.3 | 145 | 0 | 145 | 145 | 0 |
| CLOSE PHASE Eg. PIR Report Signed | WBS 5.0 | 75 | 0 | 65 | 65 | -10 |

Insert effort estimates in this table directly from the baselined Project Schedule (MS Project Plan). Baseline the Project Schedule at the end of every reporting period with updated effort estimates from the Team members working on each WBS.

## Resource Plan  (Insert hours and costs in this table directly from the baselined Project Schedule (MS Project Plan)).

| Resource Source | Hours for this Reporting Period | Delivery Costs for this Reporting Period | Hours for this Reporting Period + 1 | Hours for this Reporting Period + 2 | Hours for this Reporting Period + 3 |
| --- | --- | --- | --- | --- | --- |
| Consulting | Eg. 125 | $6,500 | 125 | 125 | 125 |
| Product | 25 | $2,500 | 25 | 25 | 25 |
| Support Services | 15 | $1,000 | 15 | 15 | 15 |
| Contractors | 85 | $5,000 | 85 | 85 | 85 |
| Total | 250 | $15,000 | 250 | 250 | 250 |

# Project/ Program Organisation

| Customer Name & Title | itsm Partnership Counterpart Name & Title |
| --- | --- |

# Issues

Insert the latest version of the Issue Log as an embedded object.

List any specific help needed from Management.

# Project Financial Report

Insert the financial report as an embedded object.