## Slide 1: Presentation/Customer Name
Gavin McKee
Solutions & Services
TRAINING STRATEGY
Catch phrase (if required)

## Slide 2: DOCUMENT CONTROL & DISTRIBUTION
Version | Date | Prepared by | Comments
0.1 | 18/01/06 | Hiske den Boer | Reviewers had no additional comments
V1.0 | 25/01/06 | Hiske den Boer | 
Name | Title | Function
Wendy Balanchandran | InfoService Centre – Director / QH Sponsor | Approve
Rowan Salt, Martin Hodges-Jones, Michael Ruge, Patricia Burow | InfoService Centre – Customer Services Manager/Team Leaders | Review
Jim Ramsay | InfoOperations – Exec Director | Approve
Graham Stocks, Jennifer McCarthy, David Fogden, Antonio Padilha, Phil Lingard | InfoOperations – Directors | Review
Sharon McKinnon | QH Project Manager | Approve
Gavin McKee | HP Project Manager | Approve
Karen Scott | QH Implementation Manager | Review
Glenn Spicer | HP Education Services | Review
SMIP Team |  | For Information
SMIP Steering Committee |  | For Information
HP Trainers |  | For Information
ID Super Users |  | For Information

## Slide 3: APPROVALS
Signature: |  | Business Area: | InfoOperations
Name: | Jim Ramsay | Date: | 
Position: | InfoOperations Executive Director | Contact No: | 3636 9525
Signature: |  | Business Area: | SMIP Project
Name: | Sharon McKinnon | Date: | 
Position: | Project Manager | Contact No: | 3131 1619
Signature: |  | Business Area: | InfoService Centre
Name: | Wendy Balanchandran | Date: | 
Position: | InfoService Centre Director | Contact No: | 3636 4965

## Slide 4: TABLE OF CONTENTS
INTRODUCTION……………………………………..5
TRAINING SCOPE…………………………………...6
STUDENTS……………………………………………7
COURSES……………………………………………11
LEARNING PATHS………………………………….19
TRAINING DELIVERY APPROACH………………21
RESOURCES………………………………………..22
MATERIALS………………………………………….24
ROOMS & FACILITIES……………………………..25
DRAFT TRAINING SCHEDULE…………………...27
CERTIFICATION…………………………………….28
EVALUATION………………………………………..29
ESTIMATED COSTS………………………………..30
ESTIMATED EFFORT………………………………31

## Slide 5: INTRODUCTION
The Queensland Health Information Division via the Transformation Program has invested significant effort in the redesign of a number of key IT Service Management Processes in order to improve service delivery.
The Service Management Implementation Project (SMIP) has been initiated to implement the processes with supporting technology in the areas of Incident, ICT Change & Configuration Management in order to achieve savings through improved efficiency and effectiveness in the delivery of service to ID’s Customers.
HP Open View Service Desk will be used State-Wide:
To log ALL user incidents, advice requests, service requests, compliments and complaints
To log and manage requests for change to the production environment
As the forward schedule of change
As the single repository for our configuration items (at the level defined in the state-wide CMDB)
This document outlines the proposed training strategy for future users of these redesigned processes and new tool.
Training will be aimed at:
Introducing culture of working in a end-to-end service delivery organisation
Educating people in working according to the new processes
Building capability in using the new tool
Supporting team building and cooperation between the different ID Branches and Business Units

## Slide 6: TRAINING SCOPE
PROCESS TRAINING
End-to-end service delivery
Incident Management
Configuration Management
Change Management
TOOL TRAINING
HP Open View Service Desk
InfoService Centre
InfoOperations
HP Trainers
QH/ID Super Users

## Slide 7: STUDENTS
TOTAL of 472 students
The following groups and individuals have been identified as participants in SMIP training.
INFOSERVICE CENTRE (37)
Managers (5)
Customer Services Officers (32)
INFOOPERATIONS (435)
Managers (48)
Key Senior Staff (31)
Technical Staff (356)
Additional Roles
Amongst these students additional roles are required:
Champions (84)
Managers & Key Senior Staff who provide leadership to staff and therefore will communicate and reinforce the ‘new way of working’
Super Users (24)
Selected staff who will become process trainers and tool experts to deliver process training to their colleagues, provide user support, and be involved in refresher/on-going training
System Administrators (8)
Selected staff who undertake system administration and application coordination activities
InfoOperations (2 dedicated, 2 Windows Support, 2 Database Administrators)
InfoService Centre (2 dedicated)

## Slide 8: STUDENTS InfoService Centre
InfoService Centre: “serving customers”
call receipt, logging, and classification
first line support
resolution and closure
Managers and Customer Services Staff have been identified as student categories.
Please note: The role of Administration Officer is excluded from training.
Managers (Champions) | No of People
Director | 1
Customer Services Manager | 1
Customers Services Officers (AO5) | 3
Total | 5
Customer Services Staff | No of People
Customers Services Officers (AO4) | 8
Customers Services Officers (AO3) | 24
Total | 32

## Slide 9: STUDENTS InfoOperations
Managers (Champions) | Business Unit | No of People
Directors | All | 9
Cluster Managers | Area Management | 8
Site Managers | Area Management | 6
Team Leaders | Area Management | 14
Technical Operations Managers | Service Integration | 3
Applications Managers | Service Integration | 3
Manager Access Operations | Technical Operations | 1
Manager Processing and Storage Operations | Technical Operations | 1
Manager Network Operations | Technical Operations | 1
Manager Data Centre Facilities | Technical Operations | 1
Manager Production Control | Technical Operations | 1
Key Senior Staff (Champions) | Business Unit | No of People
Principal Technology Officers (Primary Site) | Area Management | 10
Senior Applications Specialists | Service Integration | 8
Principal Technical Specialists | Technical Assurance | 4
Senior Technical Specialists | Technical Assurance | 3
Security Assurance Manager | Technical Assurance | 1
Principal Operations Consultants | Operations Consulting | 5
 | Total | 79
InfoOperations: “end-to-end service delivery of enterprise infrastructure”
Service Integration
Technical Operations
Technical Assurance
Operations Consulting
Clusters
Please note: Administration Officers and staff in the Business Services Unit are excluded from training.

## Slide 10: STUDENTS InfoOperations
Technical Staff | Business Unit | No of People
Principal Technology Officers | Area Management Service Integration Technical Operations | 61 15 28
Senior Technology Officers | Area Management Technical Operations | 72 6
Technology Officers | Area Management | 58
Infrastructure Coordinator | Area Management | 1
Senior Applications Specialists | Service Integration | 2
Applications Specialists | Service Integration | 20
Principal Applications Officers | Service Integration | 8
Applications Officers | Service Integration | 10
Senior Operations Specialists | Service Integration Technical Operations | 9 3
Operations Specialists | Service Integration Technical Operations | 10 11
Process Officers Change Administration | Technical Operations | 2
Senior Technical Specialists | Technical Assurance | 7
Technical Specialists | Technical Assurance | 14
Senior Operations Consultants | Operations Consulting | 11
Operations Consultants | Operations Consulting | 8
 | Total | 356 (incl. temp roles)

## Slide 11: COURSES Overview
The following courses will be provided:
No | Course Name | Content Overview | Provider | Duration
1 | ITIL Foundations | Introduction of the concepts of IT Service Management (ITSM) based on the industry standard IT Infrastructure Library (ITIL) | Hewlett- Packard | 3 days
2 | ITIL Teaming Workshop | Introduction of all 10 key ITIL processes High Performance ITSM Simulation (Teaming Game) | Hewlett- Packard | 1 day
3 | Key ITIL Processes | End-to-end Service Delivery Management Incident Management and/or Configuration Management and/or Change Management and/or | Information Division (Super Users) | 1 or 2 days
4 | HP Open View Service Desk (tool) | Introduction to ITIL End User Basics Incident, Configuration, and/or Change Management | Hewlett- Packard | 1 day

## Slide 12: COURSES ITIL Foundations
Prerequisite for 84 Champions (Managers & Key Senior Staff) and 24 Super Users
At least 44 people have already attended an ITIL Foundation Course (3 days) in 2001/2002
The 3-day course is 80 percent lecture and 20 percent interactive
Courses for 40 students will be scheduled in March/April 2006
Proposed Course Content
Introduction of the concepts of IT Service Management (ITSM) based on the industry standard IT Infrastructure Library (ITIL)
Set of processes involved in developing an IT framework
Optional "Foundation Certificate in IT Service Management" examination

## Slide 13: COURSES ITSM Teaming Workshop
Prerequisite for 84 Champions (Managers & Key Senior Staff) and 24 Super Users
This course will support the culture change to a service delivery organisation and draw staff’s attention on improving business performance across the organisation
Courses will be scheduled in May/June 2006
Proposed Course Content
Introduction of all 10 key ITIL processes (Refresh of ITIL Foundations)
High Performance ITSM Simulation – F1 Racing Competition (Teaming Game)
  Sim Round 1 (Chaos)
    Service Desk
    Incident Management
    Problem Management
  Sim Round 2 (Using formal processes to restore services and fix problems)
    Configuration Management
    Change Management
    Release Management
  Sim Round 3 (Achieving control of the Infrastructure)
    Service Level Management
    Financial Management
  Sim Round 4 (Agreeing on services with the business)
    Capacity Management
    Availability Management
    IT Service Continuity Management
  Sim Round 5 (Managing technology to meet the agreed business requirements)

## Slide 14: COURSES Incident Management Process
InfoService Centre students will receive 1 day extensive training in this process
InfoOperations students will receive a tailored version of this process as part of their 2 day Key ITIL Processes course
Courses will be scheduled in June/July 2006
Proposed Course Content
Introduction to end-to-end service delivery management
  Why e2e?
  Moving to a Service Delivery Organisation
  Key players in e2e and process owners
  How the Incident, Configuration, and Change Management processes integrate
  Benefits for our customers, the ID organisation and you
Key Concepts of Incident Management
  Objective
  Impacts
  Definitions
  Functions & Roles
Step-by-step walk through
  INC1.0 Register and Assign Contacts
  INC2.0 Identify & Resolve Incidents
  INC3.0 Manage Service Requests
Links to Problem Management
Fundamentals of Service Level Management
State wide business rules and policies that will underpin the process
Team building activities
User scenarios (exercises)

## Slide 15: COURSES Configuration & Change Management Processes
InfoOperations students will receive training in these processes as part of their 2 day Key ITIL Processes course
InfoService Centre Managers will also attend this course
Courses will be scheduled in June/July 2006
Proposed Course Content
Introduction to end-to-end service delivery management
  Why e2e?
  Moving to a Service Delivery Organisation
  Key players in e2e and process owners
  How the Incident, Configuration, and Change Management processes integrate
  Benefits for our customers, the ID organisation and you
Key Concepts of Configuration Management
  Objective
  Impacts
  Definitions
  Functions & Roles
  CMDB
Step-by-step walk through
  CFG1.0 Maintain a Configuration Item (CI)
  CFG2.0 Audit the (CMDB)
State wide business rules and policies that will underpin the processes
Team building activities
User scenarios (exercises)
Key Concepts of Change Management
  Objective
  Impacts
  Definitions
  Functions & Roles
  CMDB
Step-by-step walkthrough
  CHG1.0 Prioritise & Control Request for Change
  CHG2.0 Assess Request for Change
  CHG3.0 Plan Request for Change
  CHG4.0 Prepare for Change Implementation

## Slide 16: COURSES Service Desk Tool InfoService Centre
Module 1 Introduction to ITIL | Module 2 End User Basics
Module 3 Help Desk / Service Desk | Module 4 Specialist
Module 5 Problem Management for End Users | Module 6 Configuration Management for End Users
Module 7 Change Management with Work Orders and Projects for End Users | Module 8 Service Level Management for End Users
Module 9 Organisation Management for End Users | Module 10 End User Advanced
Module 11 Service Pages for Specialists | Module 12 Web Console for IT Staff
Additional for
Champions
and Super Users
All InfoService Centre Staff
Additional for
Champions
and Super Users

## Slide 17: COURSES Service Desk Tool InfoOperations
Module 1 Introduction to ITIL | Module 2 End User Basics
Module 3 (basics only) Help Desk / Service Desk | Module 4 Specialist
Module 5 Problem Management for End Users | Module 6 Configuration Management for End Users
Module 7 Change Management with Work Orders and Projects for End Users | Module 8 Service Level Management for End Users
Module 9 Organisation Management for End Users | Module 10 End User Advanced
Module 11 Service Pages for Specialists | Module 12 Web Console for IT Staff
Additional for
Super users
All InfoOperations Technical Staff

## Slide 18: COURSES Application Coordinator
2 System Administrators from InfoService Centre and 6 System Administrators from InfoOperations will receive this training course
This course provides knowledge and skills necessary to use and manage the HP OpenView Service Desk 4.5 product. Emphasis is on application-level configuration. This 4-day course is 50 percent lecture and 50 percent hands-on
Course will be scheduled in June 2006
Proposed Course Content
Use HP OpenView Service Desk 4.5 to manage service calls, incidents, configuration items, work orders, problems, changes, persons, organizations, workgroups, service level agreements and services
Use the administrator console to modify the environment to your suit needs
Create customized forms, views, and templates

## Slide 19: LEARNING PATHS InfoService Centre
CS Manager & Team Leaders (Champions) | Customer Services Officers | Super Users (Trainers) | System Administrators
ITIL Foundations (3 days) as required |  | ITIL Foundations (3 days) as required | 
ITSM Teaming Workshop (1 day) |  | ITSM Teaming Workshop (1 day) | 
Key ITIL Processes (2 days) Incident, Configuration, & Change Mgmt | Key ITIL Processes (1 day) Incident Mgmt | Key ITIL Processes (2 days) Incident, Configuration, & Change Mgmt | Key ITIL Processes (2 days) Incident, Configuration, & Change Mgmt
HP Open View Service Desk (1 day) Incident Mgmt | HP Open View Service Desk (1 day) Incident Mgmt | HP Open View Service Desk (1 day) Incident Mgmt | 
HP Open View Service Desk (1 day) Configuration & Change Mgmt |  | HP Open View Service Desk (1 day) Configuration & Change Mgmt | 
HP Open View Service Desk (1 day) Advanced User |  | HP Open View Service Desk (1 day) Advanced User | HP Application Coordinator (4 days)
TOTAL 9 days max | TOTAL 2 days | TOTAL 9 days max | TOTAL 6 days

## Slide 20: LEARNING PATHS InfoOperations
Management / Senior Staff (Champions) | Technical Staff | Super Users (Trainers) | System Administrators
ITIL Foundations (3 days) as required |  | ITIL Foundations (3 days) as required | 
ITSM Teaming Workshop (1 day) |  | ITSM Teaming Workshop (1 day) | 
Key ITIL Processes (2 days) Incident, Configuration, & Change Mgmt | Key ITIL Processes (2 days) Incident, Configuration, & Change Mgmt | Key ITIL Processes (2 days) Incident, Configuration, & Change Mgmt | Key ITIL Processes (2 days) Incident, Configuration, & Change Mgmt
HP Open View Service Desk (1 day) Incident, Configuration, & Change Mgmt | HP Open View Service Desk (1 day) Incident, Configuration, & Change Mgmt | HP Open View Service Desk (1 day) Incident, Configuration, & Change Mgmt | 
 |  | HP Open View Service Desk (1 day) Advanced User | HP Application Coordinator (4 days)
TOTAL 7 days max | TOTAL 3 days | TOTAL 8 days max | TOTAL 6 days

## Slide 21: TRAINING DELIVERY APPROACH
SYSTEM ADMINISTRATORS
USERS
HP Trainers
Process
Courses
HP Tool
Coordinators
Course
HP Tool
Courses
Process Instructional Designer
HP Trainers
SUPER USERS
CHAMPIONS
ITIL Foundations &
Teaming Workshops

## Slide 22: RESOURCES
Champions (84)
Management and Senior Staff
Communicate and reinforce ‘new way of working’
Support the Super Users
Super Users (24)
22 SU from InfoOperations, representing each location in Qld
2 SU from InfoService Centre
Input and review of training materials
Participant in User Acceptance Testing
Delivery of process training to End Users
Coordination of training schedule
User support before and after Go-Live
Refresher/On-going training
A detailed role description for Super Users will be developed to support the selection process
ID Training Manager (1)
Implementation and coordination of training plan
Development of training schedule
ID Instructional Designer (1)
Training materials development for process training
Delivery of process training to Super Users
Training evaluation
HP Education Services (1)
Preparation and support of HP Trainers
Customisation and production of tool student guide
Design and production of quick reference cards
HP Trainers (3)
Setup of training rooms
Delivery of ITIL foundations and ITSM teaming workshop to Champions
Delivery of tool training to End Users
Delivery of application coordinators course to System Administrators

## Slide 23: SMIP PROJECT TEAM Training Resources
SMIP Steering Committee
Wendy
Balachandran
(Chair)
Jim Ramsay
Rowan Salt
Steve
Shackcloth
Roque
De Souza
Gavin McKee
Sharon McKinnon
Rachel
Seaniger
Michael
Drahiem
Project Sponsor
Wendy
Balachandran
Project Manager
Sharon McKinnon
Solution Architect
Brett Daley/Anne Davis
Implementation Co
-
Ordinator
Karen Scott
Project Officer
TBA
Testing Manager
TBA
ITSM Architect
Mark Carroll
Business Change Manager
Hiske
den Boer
HP Delivery Manager
Gavin McKee
Interface Specialist
TBA
Data Conversion Analyst
TBA
Development Team
System Test
Analyst(s
)
TBA
System
Analyst(s
)
Sharon Rowland
Peter Nicholls
Instructional Design
TBA
Organisational Change
& Communications
TBA
User Acceptance Test
Analyst(s
)
TBA
SMIP Steering Committee
Wendy
Balachandran
(Chair)
Jim Ramsay
Rowan Salt
Steve
Shackcloth
Roque
De Souza
Gavin McKee
Sharon McKinnon
Rachel
Seaniger
Michael
Drahiem
Project Sponsor
Wendy
Balachandran
Project Manager
Sharon McKinnon
Solution Architect
Brett Daley/Anne Davis
Implementation Co
-
Ordinator
Karen Scott
Project Officer
TBA
Testing Manager
TBA
ITSM Architect
Mark Carroll
Business Change Manager
Hiske
den Boer
HP Delivery Manager
Gavin McKee
Interface Specialist
TBA
Data Conversion Analyst
TBA
Development Team
System Test
Analyst(s
)
TBA
System
Analyst(s
)
Sharon Rowland
Peter Nicholls
Instructional Design
TBA
Organisational Change
& Communications
TBA
User Acceptance Test
Analyst(s
)
TBA
TBA
ID Super Users
TBA
Instructional Design
TBA
HP Education Services
Glenn Spicer
TBA
HP Trainers
TBA

## Slide 24: MATERIALS
The following training materials will be developed and provided to students:
Process training
User Guide covering the three processes
Electronic/hardcopy process slides and handouts
Content for the Key ITIL Processes Course will be developed by the SMIP Instructional Designer.
Tool training
Hardcopy HP tool student guide
Desk quick reference card
Handout with HP tool exercises with realistic QH/ID data
Training system with relevant examples of business data (copy of production system), available during training courses and afterwards on individual work stations for further practice opportunities
HP will customise the content of their training materials to address ID specific requirements.

## Slide 25: ROOMS & FACILITIES
Process training rooms need:
8 – 12 desks
Whiteboard
Instructor PC
Data projector
Tool training rooms need:
8 – 12 PCs
Instructor PC
Whiteboard
HP virtual rooms are available for remote delivery of training (only as back-up option since face-to-face is preferred)
Location | Course | Number | Duration (weeks)
Brisbane – Edu Centre | Process | 2 | 4
Brisbane – Block 7 | Process | 1 | 6
Brisbane – Block 7 | Tool | 1 | 7
Brisbane – PAH | Process | 1 | 1.5
Brisbane – HP Office | Tool | 1 | 4
Toowoomba | Process/tool | 1 | 1.5
Gold Coast | Process/tool | 1 | 1.5
Redcliffe | Process/tool | 1 | 1.5
Mackay | Process/tool | 1 | 1
Rockhampton | Process/tool | 1 | 1
Wide Bay/Burnett | Process/tool | 1 | 1
Cairns | Process/tool | 1 | 1
Townsville | Process/tool | 1 | 1

## Slide 26: SCHEDULING
The following points have been taken into consideration when drafting the draft training schedule (see next page):
Training will take 5 weeks
Approx 450 InfoOps staff and 40 InfoService Centre will be trained
ITIL Foundations and ITSM Teaming Workshops are a prerequisite and need to be completed before user training starts
Students will attend process training in one week, tool training in the following week, and doing exercises in the week after (time permitting)
Staff will be scheduled together with their colleagues and their Managers will attend the first training sessions to be able to answer any questions from staff
Courses hold between 8 and 12 staff
InfoService Centre staff will only be trained on Thursdays and Fridays
The majority of the training will take place in Brisbane area
Training in the clusters will be organised around the most suitable location and venue
Trainers will travel and therefore travel for staff is kept to a minimum
InfoService Centre Managers will attend 2 day process courses for InfoOperations’ students
SMIP Training Manager will develop training schedule:
  Managers and/or Super Users will schedule their staff using this training schedule
  SMIP will maintain changes to the schedule
  Managers confirm training with each student
School holidays may impact on the schedule:
  26 June till 10 July 2006 (2 weeks)
A detailed training schedule is available.

## Slide 27: DRAFT TRAINING SCHEDULE
Mar06 | Apr 06 | May 06 |  | June 06 |  |  |  | July 06 |  |  |  | Aug 06
2 weeks |  | 2 weeks |  | 3 weeks |  |  | 5 weeks |  |  |  |  | GO-LIVE
ITIL Foundations |  |  |  |  |  |  |  |  |  |  |  | 
 |  | ITSM Teaming Workshops |  |  |  |  |  |  |  |  |  | 
 |  |  |  | Process |  |  |  |  |  |  |  | 
 |  |  |  | Tool |  |  |  | Tool |  |  |  | 
 |  |  |  | Advanced Tool |  |  |  |  |  |  |  | 
 |  |  |  |  | Training Delivery Practice |  |  |  |  |  |  | 
 |  |  |  |  |  | Appl Coor |  |  |  |  |  | 
Champions Super Users |  | Champions |  | Super Users System Administrators |  |  | Users |  |  |  |  | 

## Slide 28: CERTIFICATION
Students will be able to sit an exam and be awarded a certificate in:
ITIL Foundations
Application Coordinator
Users will receive “certificate of attendance” for HP Service Desk tool training.

## Slide 29: EVALUATION
The SMIP Instructional Designer will develop evaluation objectives and tools.

## Slide 30: ESTIMATED COSTS
Course Title | Duration | Unit Price | Participants | Sessions | Cost (excl. GST)
H1846S – ITIL Foundations | 2.5 Days | $1,500 | 40 | 4 | $ 60,000
UC580S – ITSM Executive Workshop | 1 Day | $3,800 | 84 | 8 | $ 30,400
U1612S – Service Desk Super User | 2 Days | $700.00 | 24 | 3 | $ 16,800
H7084S – Service Desk Application Co-ordinator | 4 Days | $2,800 | 8 | 1 | $ 22,400
U1612S – Service Desk End User training | 1 Day | $350.00 | 448 | 45 | $156,800
Content Development | 10 Days | $1,350 | 10 | - | $ 13,500
Total |  |  |  |  | $299,900*
* Includes student guides, handouts, and quick reference cards for all students, training facilities, instructor travel and accommodation for remote training. |  |  |  |  | 
Travel and Accommodation
To attend training sessions a number of Super Users will be required to travel once or more.
10 Super Users * 3 travel events = $30,000 (Airfares and accommodation)
Costs for dedicated training environment and QH rooms are to be advised.

## Slide 31: ESTIMATED EFFORT
Super Users
ITIL Foundations (24 * 3 days) 72
Train-the-trainer (24 * 5 days) 120
Practice (24 * 5 days) 120
Training Delivery 108
Champions
ITIL Foundations (40 * 3 days) 120
ITSM Workshops (84 * 1 day) 84
Process + Tool (84 * 3 days) 252
Users
Training InfoOperations Staff (356 * 3 days) 1068
Training InfoService Centre Staff (32 * 2 days) 64
System Administrators
Training (8 * 4 days) 32
Total effort 2040 work days