## Cover Page
Change Management
RACI Matrix

## Roles
CHG RACI Matrix
| Role | Abbreviation
| Change Requestor | CRQ
| Change Manager | CHM
| Change Owner | CO
| Change Domain Experts | CDE
| Planning CAB | PCAB
| Technical CAB | TCAB
| Deployment CAB | DCAB
| Emergency CAB | ECAB
| Escalation Team | ESTM
| L2 Domain Analyst | L2
| L3 Engineering Support Analyst | L3
| CI Owner | CIOW
| Configuration Data Analyst | CDA
| Build & Test Manager | BTM
| Release Manager | RM
| Incident Manager | IM
* These terms are referenced throughout the Change Management process model

## 5.1-5.2
CRQ = Change Requestor CHM = Change Manager CO = Change Owner CDE = Change Domain Expert
CIOW = CI Owner CDA = Configuration Data Analyst BTM = Buld & Test Manager RM = Release Manager
L2 = L2 Domain Analyst L3 = L3 Engineering Support Analyst IM = Incident Manager
# | Activities | IT
|  | CRQ | CHM | CO | CDE | PCAB | TCAB | DCAB | ECAB | IM | L2 | L3 | CIOW | CDA | BTM | RM
5.1 | Log & Categorize RFC
5.1.1 | Log RFC | R | A,R
5.1.2 | Initial Review of RFC |  | A,R
5.1.3 | Reject RFC? | C | A,R
5.1.4 | Notify Requestor RFC Rejected | I | A,R
5.1.5 | Review RFC for Completeness & Accuracy |  | A,R
5.1.6 | RFC complete & Accurate? |  | A,R
5.1.7 | Work with Requestor to Complete RFC | R | A,R
5.2 | Emergency Change? |  | A,R

## 5.3-5.4
CRQ = Change Requestor CHM = Change Manager CO = Change Owner CDE = Change Domain Expert
CIOW = CI Owner CDA = Configuration Data Analyst BTM = Buld & Test Manager RM = Release Manager
L2 = L2 Domain Analyst L3 = L3 Engineering Support Analyst IM = Incident Manager
# | Activities | IT
|  | CRQ | CHM | CO | CDE | PCAB | TCAB | DCAB | ECAB | IM | L2 | L3 | CIOW | CDA | BTM | RM
5.3 | Perform Emergency Change
5.3.1 | Convene ECAB |  | A,R | [5 empty] | C,R
5.3.2 | Identify & Assign Change Owner |  | A,R | C
5.3.3 | Assess Urgency, Risk & Impact of Emergency Change | [7 empty] | A,R
5.3.4 | Emergency Change Approved? | [7 empty] | A,R
5.3.5 | Notify Requestor Emergency Disapproved | [7 empty] | A,R
5.3.6 | Plan Emergency Change
5.3.6.1 | Identify & Assign Resources |  |  | A,R
5.3.6.2 | Plan Emergency Change Solution |  |  | R | A,R
5.3.7 | Emergency L3 Engineering Change? |  | I | A,R | [7 empty] | C
5.3.8 | Coordinate Emergency Change Design & Development |  | I | A | [7 empty] | R
5.3.9 | Coordinate Emergency Change Build & Test Activities |  | I | A | R | [5 empty] | C,I | C,I
5.3.10 | Schedule Emergency Change | C | C | A,R
5.3.11 | Coordinate Emergency Change Implementation Activities |  | I | [7 empty] | C,I | C,I
5.3.12 | Conduct Formal Turnover of Emergency Change to Support |  | I | A,R | [5 empty] | I
5.3.13 | Conduct Post-Emergency Change Review
5.3.13.1 | Review Emergency Change Results & Signoff |  | A,R | C | [6 empty] | C | C
5.3.13.2 | Signoff Achieve? | R | A,R
5.3.13.3 | Resolve Open Issues | C,I | A,R | C | [6 empty] | C | C
5.3.14 | Close Emergency Change RFC |  | A,R
5.4 | Standard Change? |  | A,R

## 5.5-5.6
CRQ = Change Requestor CHM = Change Manager CO = Change Owner CDE = Change Domain Expert
CIOW = CI Owner CDA = Configuration Data Analyst BTM = Buld & Test Manager RM = Release Manager
L2 = L2 Domain Analyst L3 = L3 Engineering Support Analyst IM = Incident Manager
# | Activities | IT
|  | CRQ | CHM | CO | CDE | PCAB | TCAB | DCAB | ECAB | IM | L2 | L3 | CIOW | CDA | BTM | RM
5.5 | Perform Standard Change
5.5.1 | Identify Standard Change Model |  | A,R
5.5.2 | Assign Resources to Standard Change |  |  | A,R
5.5.3 | Schedule Standard Change
5.5.3.1 | Determine Standard Change Schedule |  |  | A,R
5.5.3.2 | Notify Interested Parties of the Schedule for Standard Change |  |  | A,R
5.5.3.3 | Schedule Conflicts? |  |  | A,R
5.5.3.4 | Publish FSC for Standard Change |  |  | A,R
5.5.4 | Issue Work Orders to Execute Standard Change Implementation |  |  | A,R
5.5.5 | Coordinate Standard Change Implementation |  |  | A,R | [8 empty] | I | I |  | I
5.5.6 | Update & Close Standard Change Work Orders |  |  | A,R | [9 empty] | I
5.5.7 | Standard Change Successful? |  |  | A,R
5.5.8 | Conduct Formal Turnover of Standard Change to Support |  |  | A,R | [5 empty] | I
5.5.9 | Review Standard Change |  |  | A,R
5.5.10 | Notify Requestor of Change Results | I |  | A,R
5.5.11 | Update and Close RFC |  |  | A,R
5.6 | Minor Change? |  | A,R

## 5.7-5.8
# | Activities | IT
CRQ = Change Requestor CHM = Change Manager CO = Change Owner CDE = Change Domain Expert
CIOW = CI Owner CDA = Configuration Data Analyst BTM = Buld & Test Manager RM = Release Manager
L2 = L2 Domain Analyst L3 = L3 Engineering Support Analyst IM = Incident Manager
|  | CRQ | CHM | CO | CDE | PCAB | TCAB | DCAB | ECAB | IM | L2 | L3 | CIOW | CDA | BTM | RM
5.7 | Perform Minor Change
5.7.1 | Review Minor Change Risk, Impact and Resource Requirements |  | A,R
5.7.2 | Risk, Impact & Resource Requirements Known? |  | A,R
5.7.3 | Perform Minor Change Risk & Impact Analysis
5.7.3.1 | Estimate Minor Change Work Effort |  |  | A,R | C
5.7.3.2 | Assess Risk & Impact of Minor Change |  |  | A,R | C
5.7.3.3 | Risk & Impact Acceptable? |  |  | A,R
5.7.3.4 | Document Reasons for Rejecting Minor Change |  |  | A,R
5.7.3.5 | Notify Change Requestor Minor Change Rejected | I |  | A,R
5.7.3.6 | Close RFC |  |  | A,R
5.7.4 | Approve Minor Change |  | A,R
5.7.5 | Notify TCAB of Approved Minor Change |  | A,R |  |  |  | I
5.7.6 | Identify Resources for Minor Change |  |  | A,R | I
5.7.7 | Validate Minor Change Schedule
5.7.7.1 | Validate Schedule |  |  | A,R
5.7.7.2 | Notify Interested Parties of Schedule for Minor Change |  | I | A,R
5.7.7.3 | Schedule Conflicts? |  |  | A,R
5.7.7.4 | Determine Schedule for Minor Change |  |  | A,R
5.7.7.5 | Publish FSC for Minor Change |  |  | A,R
5.7.8 | Coordinate Minor Change Build & Test Planning |  |  | A,R | [10 empty] | I
5.7.9 | Coordinate Minor Change Build & Test |  |  | A,R |  |  |  | I | [5 empty] | I | I
5.7.10 | Coordinate Minor Change Implementation
5.7.10.1 | Review Minor Change Build & Test Results | [6 empty] | A,R
5.7.10.2 | Build & Test Results Acceptable? | [6 empty] | A,R
5.7.10.3 | Abandon Minor Change B&T? | [6 empty] | A,R | [6 empty] | C
5.7.10.4 | Notify Requestor Minor Change Abandoned | I | [5 empty] | A,R
5.7.10.5 | Approve Minor Change Implementation | [6 empty] | A,R | [7 empty] | I
5.7.10.6 | Prepare and Issue Minor Implementation Work Orders |  |  | A,R | [11 empty] | I
5.7.10.7 | Review Backed out Minor Change |  |  | A,R | [11 empty] | C
5.7.10.8 | Authorize Minor Remediation Planning? |  |  | A,R | [11 empty] | C,I
5.7.10.9 | Notify RTP Remediation Planning Not Authorized |  |  | A,R | [11 empty] | I
5.7.10.10 | Review Minor Remediation Plan |  |  | A,R
5.7.10.11 | Minor Remediation Plan Approved? |  |  | A,R
5.7.10.12 | Minor Change Implementation Successful? |  |  | A,R
5.7.10.13 | Review Minor Implementation Results |  |  | A,R
5.7.11 | Update and Close Minor Execution WO(s) |  |  | A,R | [9 empty] | I
5.7.12 | Minor Change Successful? |  |  | A,R
5.7.13 | Conduct Formal Turnover of Minor Change to Support |  |  | A,R | [5 empty] | I
5.7.14 | Review Minor Change |  |  | A,R
5.7.15 | Notify Requestor of Change Results | I |  | A,R
5.7.16 | Close Minor Change RFC |  |  | A,R
5.8 | Significant or Major Change? |  |  | A,R

## 5.9
CRQ = Change Requestor CHM = Change Manager CO = Change Owner CDE = Change Domain Expert
CIOW = CI Owner CDA = Configuration Data Analyst BTM = Buld & Test Manager RM = Release Manager
L2 = L2 Domain Analyst L3 = L3 Engineering Support Analyst IM = Incident Manager
# | Activities | IT
|  | CRQ | CHM | CO | CDE | PCAB | TCAB | DCAB | ECAB | IM | L2 | L3 | CIOW | CDA | BTM | RM
5.9 | Perform Significant/Major Change
5.9.1 | Evaluate Major Change Impact & Dependencies |  |  | A,R
5.9.2 | Identify and Notify PCAB Members for Major Change |  |  | A,R
5.9.3 | Approve Major Change Preliminary Schedule
5.9.3.1 | Review Major Change Impact & Dependencies |  |  |  | C | A,R
5.9.3.2 | Review Requested Schedule |  |  |  |  | A,R
5.9.3.3 | Schedule Approved? |  |  |  | I | A,R
5.9.3.4 | Resolve Preliminary Significant/Major Change Schedule Issues |  |  |  | C | A,R
5.9.3.5 | Notify Requestor Major Change Date Approved | I |  | A,R
5.9.3.6 | Publish FSC for Major Change |  |  | A,R
5.9.4 | Evaluate Significant Change Impact & Dependencies
5.9.5 | Assess Risk & Impact of Sig/Maj Change
5.9.5.1 | Identify TCAB Members |  |  | A,R |  |  | C,I
5.9.5.2 | Scope & Estimate Work Effort |  | C | A,R | C
5.9.5.3 | Child RFC(s) Needed? |  | C | A,R
5.9.5.4 | Generate and Link Child RFC(s) |  |  | A,R
5.9.5.5 | Assess & Document Risk & Impact of Change | [5 empty] | A,R
5.9.5.6 | Risk & Impact Acceptable? | [5 empty] | A,R
5.9.5.7 | Review Impact & Priority |  |  | A,R
5.9.5.8 | Impact & Priority Valid? |  |  | A,R
5.9.5.9 | Update Impact & Priority |  |  | A,R
5.9.5.10 | Review Category |  |  | A,R
5.9.5.11 | Category Valid? |  |  | A,R
5.9.5.12 | Update Category and Forward RFC |  |  | A,R
5.9.6 | Approve Sig/Maj Change
5.9.6.1 | Evaluate All Related RFCs |  | A,R
5.9.6.2 | Review & Discuss TCAB Findings |  | A,R | C |  |  | C
5.9.6.3 | Resolve Any Open Issues |  | C | A,R |  |  | C
5.9.6.4 | Approve RFC | [5 empty] | A,R
5.9.6.5 | TCAB Approved? | [5 empty] | A,R
5.9.6.6 | CHM - Notify Requestor Sig/Maj Change is Accepted | I |  | A,R
5.9.7 | Reject Sig/Maj Change
5.9.7.1 | Document Reasons for Rejection |  |  | A,R
5.9.7.2 | Notify Change Requestor Significant/Major Change Rejected | I |  | A,R
5.9.7.3 | Update and Close RFC |  |  | A,R
5.9.8 | Perform Sig/Maj Change Scheduling
5.9.8.1 | Identify Required Resources |  |  | A,R | C
5.9.8.2 | Major Change? |  |  | A,R
5.9.8.3 | Review Preliminary Schedule |  |  | A,R
5.9.8.4 | Schedule Conflicts? |  |  | A,R
5.9.8.5 | Update FSC with Significant/Major Change Schedule |  |  | A,R
5.9.8.6 | Determine Schedule for Significant/Major Change |  | C | A,R
5.9.8.7 | Forward Proposed Schedule to PCAB |  |  | A,R |  | I
5.9.8.8 | Review Schedule |  |  |  |  | A,R
5.9.8.9 | Schedule Approved? |  |  |  |  | A,R
5.9.8.10 | Inform Change Owner that Schedule Not Approved |  |  | I |  | A,R
5.9.8.11 | Resolve Schedule Issues |  | C | A,R |  | C
5.9.8.12 | Inform Change Owner Schedule Approved |  |  | I |  | A,R
5.9.9 | Coordinate Sig/Maj Build & Test
5.9.9.1 | Identify and Assign Sig/Maj B&T and Implementation Staff |  |  | A,R
5.9.9.2 | Coordinate Sig/Maj Change B&T Planning |  |  | A,R | [10 empty] | C,I
5.9.9.3 | Coordinate & Monitor Major Change Build & Test Activities |  |  | A,R | [9 empty] | I | C,I
5.9.9.4 | Review B&T Results and Notify DCAB |  | A,R |  |  |  |  | I
5.9.9.5 | Send Major Change RTP Instructions to CDEs |  |  | A,R | I | [10 empty] | I
5.9.10 | Review Sig/Maj B&T Results and Authorize Implementation
5.9.10.1 | Review Sig/Maj Build & Test Results | [6 empty] | A,R
5.9.10.2 | Build & Test Results Acceptable? | [6 empty] | A,R | [6 empty] | C
5.9.10.3 | Abandon Sig/Maj B&T? | [6 empty] | A,R
5.9.10.4 | Validate Sig/Maj Schedule and Staffing Plan | [6 empty] | A,R
5.9.10.5 | Valid Schedule and Staffing Plan? | [6 empty] | A,R
5.9.10.6 | Request Modification of Sig/Maj Schedule and Staffing Plan |  |  | C,I |  |  |  | A,R
5.9.10.7 | Modify Sig/Maj Schedule and Staffing Plan |  |  | A,R |  |  |  | C,I
5.9.10.8 | Update FSC and Authorize Sig/Maj Implementation |  |  | A,R
5.9.11 | Review Sig/Maj B&T Results and Authorize Implementation
5.9.11.1 | Prepare and Issue Sig/Maj Implementation Work Orders |  |  | A,R | [11 empty] | C,I
5.9.11.2 | Review Backed Out Sig/Maj Change |  |  | A,R | [11 empty] | C
5.9.11.3 | Authorize Sig/Maj Remediation Planning? |  |  | A,R | [11 empty] | C,I
5.9.11.4 | Notify RTP Remediation Planning Not Authorized |  |  | A,R | [11 empty] | I
5.9.11.5 | Review Sig/Maj Remediation Plan |  |  | A,R | [11 empty] | C
5.9.11.6 | Sig/Maj Remediation Plan Approved? |  |  | A,R | [10 empty] | I | C
5.9.11.7 | Review Sig/Maj Implementation Results |  |  | A,R
5.9.11.8 | Sig/Maj Change Implementation Successful? |  | C | A,R
5.9.12 | Update and Close Sig/Maj Execution WO(s) |  |  | A,R | [9 empty] | I
5.9.13 | Sig/Maj Change Successful? |  |  | A,R
5.9.14 | Conduct Formal Turnover of Sig/Maj Change to Support |  |  | A,R |  |  |  |  | I
5.9.15 | Perform PIR of Sig/Maj Change
5.9.15.1 | Review Sig/Maj Change Implementation |  |  | A,R
5.9.15.2 | Verify & Signoff Sig/Maj Change |  | A,R | C
5.9.15.3 | Signoff Achieved? |  | A,R
5.9.15.4 | Resolve Open Issues |  | C | A,R
5.9.15.5 | Document Sig/Maj Change Improvement Recommendations |  |  | A,R
5.9.16 | Notify Requestor of Change Results | I |  | A,R
5.9.17 | Close Significant/Major Change RFC |  |  | A,R