|  | Testing Strategy |
| --- | --- |
|  | Service Level Management Implementation Project (SLMIP) |

Testing Strategy

for

SLM Implementation Project

Version 1.0

16th May 2007

DOCUMENT ACCEPTANCE

I accept this testing strategy for the SLMIP solution and the responsibilities for test entry and test exit defined within.

|  | Approved by: | John Crouch Project Manager, SLMIP | Date: |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Signature: |  |  |  |  |
|  | Approved by: | Gavin McKee Delivery Manager, SLMIP | Date: |  |  |
|  | Signature: |  |  |  |  |
|  | Approved by: | Chris Hughes SIM3 Application Specialist | Date: |  |  |
|  | Signature: |  |  |  |  |
|  | Approved by: | John Moylan ITMS Manager, ITMS | Date: |  |  |
|  | Signature: |  |  |  |  |
|  | Approved by: | Peter Lloyd Principal Operations Consultant, QH | Date: |  |  |
|  | Signature: |  |  |  |  |

Document History

| Version | Date | Prepared by | Comments |
| --- | --- | --- | --- |
| 0.1 | 14-May-07 | Gavin McKee | Initial Draft |
| 1.0 | 16-May-07 | Gavin McKee | Updated with review comments from the SLM team |

This is a managed document.  This document has not been released for use until authorised by the last signatory.

Document Distribution List

| Date Issued | Issued To | Role |
| --- | --- | --- |
| 16th May 2007 | John Crouch, Anthony Symons, Muthu Raju, Chris Hughes, John Moylan, Peter Lloyd | Peer Reviewer |

Table of Contents

1	Document Purpose	6

2	Test Goal	6

3	Definitions	7

4	Background	8

5	System Overview	9

6	Application Overview	10

7	Testing scope, EXCLUSIONS & ASSUMPTION	11

7.1	Scope	11

7.2	Scope Exclusions	11

7.3	Scope Assumptions	12

8	KEY DATES	13

9	TEST PROGRESS COMMITTEE	14

10	Test Methodology	15

10.1	Test and Acceptance	15

10.2	Test Phases	15

11	Suspending and resuming testing	21

11.1	Suspend Testing	21

11.2	Resume Testing	21

12	entry and exit CRITERIA	22

12.1	Unit Testing entry and exit criteria	22

12.2	System testing entry criteria	22

12.3	System testing exit criteria	23

12.4	System Integration testing entry criteria	23

12.5	System Integration testing exit criteria	24

12.6	User Acceptance Testing entry criteria	24

12.7	User Acceptance Testing exit criteria	25

12.8	Production Acceptance testing entry criteria	25

12.9	Production Acceptance testing exit criteria	26

13	Test REPORTING	28

14	TEST Environment	29

14.1	Test Location(s)	29

14.2	Hardware	29

14.3	Networks & Communications	30

14.4	Software	30

14.5	Test Support Software Tools	30

15	TESTING Resources	31

16	Defect Management	33

16.1	Defect Registration	33

16.2	Defect Management Cycle	35

16.3	Defect Definitions - Severity Classifications	36

16.4	Defect Definitions - Priority Classification	36

16.5	Pass/Fail Criteria	37

17	Risks Management	38

Figures

Figure 1 - SLMIP OpenView Service Desk System Overview	9

Figure 2 - SLMIP OpenView Service Desk Process Flow	10

Figure 3 – SLMIP OpenView Service Desk Test Phases	16

Figure 4 - Screenshot of 'Add Defect' Page in Mercury Quality Center	34

Figure 5 - Defect Life Cycle	35

Tables

Table 1 - List of Definitions	7

Table 2 - List of Abbreviation	8

Table 3 - List of References	8

Table 4 - Testing Activities Scope	11

Table 5 - Testing Scope Exclusions	12

Table 6 - Testing Scope Assumptions	12

Table 7 - Testing Key Dates	13

Table 8 - Suspend testing exit meeting support groups	21

Table 9 - System testing entry criteria	22

Table 10 - System testing exit criteria	23

Table 11 – System Integration entry criteria	23

Table 12 – System Integration testing exit criteria	24

Table 16 – User Acceptance Testing exit criteria	25

Table 17 – Production Acceptance Testing entry criteria	26

Table 18 – Production Acceptance Testing exit criteria	26

Table 19 – System, System Integration and UAT Test Site	29

Table 20 - Production Acceptance Test Site	29

Table 21 - Hardware Requirement for System, System Integration and UAT	29

Table 22 - Production Acceptance Test hardware requirements	30

Table 23 - List of Testing Support Groups	31

Table 24 - Support Group Contact Details	32

Table 26 - Defect Priority Classification	37

Table 27 - Risks Management	38

# Document Purpose

This document outlines the test strategy for the initial release of the Service Level Management solution implementation.

This Test Strategy document:

- Defines the testing methodology.

- Defines the testing scope.

- Describes how testing will be managed to ensure a quality outcome.

- Defines the resources and support required to conduct testing.

- Outlines what test documentation will be used for the Project.

- Ensures the Project Manager, project team leaders, stakeholders and project team members understand their responsibilities and involvement in the project test activities.

- Describes the process used to communicate the testing status, defects and issues raised during testing to the interested parties.

# Test Goal

Verification of Service Level Management Implementation Project (SLMIP) OpenView Service Desk system including the vendor supplied solution and platform infrastructure so that the system meets both technical requirements and business-defined operating requirements and is fit for purpose by the implementation date.

# Definitions

The following definitions will be used throughout the project and they have been aligned to the definition used in Mercury Quality Center Test Management when appropriate.

Table 1 - List of Definitions

| Term | Definition |
| --- | --- |
| Production Acceptance Certificate | Details the formal acceptance of a specified deliverable’s compliance to acceptance criteria and constitutes a quality record for the project. Production Acceptance Certificate is issued if all Production Acceptance test criteria have been met. Production Acceptance Test Team is the only authority body to grant such certificate. |
| ITF Acceptance Certificate | Details the formal acceptance of a specified deliverable’s compliance to acceptance criteria and constitutes a quality record for the project. ITF Acceptance Certificate is issued if all exit criteria for operational and UAT have been met. ITMS is the only authority body to grant such certificate. |
| Test Plan | A Mercury Quality Center terminology. It is a test scenario with details of steps to be undertaken by testers in conducting a test. |
| Test Sets | A Mercury Quality Center terminology. It is a set containing one or more tests to be executed either in manual or automatic mode to satisfy a specific test goal. E.g.: Build Sanity Test, Regression Test, etc. |
| Test Defects | Details any failure or non-conformance discovered during a test. |
| Test Infrastructure/Environment Specification | Specifies all equipment, both hardware and software, needed to build the test environment. |
| Test Phase | A distinct phase in the entire testing activities. It has its own testing objectives, testing agenda and activities, entry and exit criteria. Example of a test phases are Unit Testing and system testing. |
| Test Cycle | One complete test runs on a build. |
| Test Record | Provides a detailed record of relevant issues about the execution of a test plan. Only tests executed in Mercury Quality Center Test Management System will be stored in the Mercury Quality Centre Management System. |
| Test Report | A report outlining the outcome of the test execution. Such report will cover test progress, analysis and test statistics. |
| Test Strategy document | This document. It describes the strategy, methodology and high level goals of testing. It also covers risks and defect management, roles and responsibility. |

Table 2 - List of Abbreviation

| Abbreviation | Definition |
| --- | --- |
| SLMIP | Service Level Management Implementation Project |
| ITMS | Integrated Test Management Service |
| ITF | Integrated Testing Facility |
| TBA | To Be Advised |
| CTech | ctechnology solutions Pty Ltd |
| QH | Queensland Health |
| RBWH | Royal Brisbane and Women Hospital |
| SDLC | System Development Life Cycle |
| SOE | Standard Operating Environment |
| OVSD | OpenView Service Desk |
| UAT | User Acceptance Tests |

Table 3 - List of References

- QH SLA Service Desk Design - v1.5 070402

- QH SLM SD Requirements Traceability Matrix v1.0, 21st Feb 2007

- QH ID CI Upload Spreadsheet Import Work Instructions v0.1

Background

Please refer to QH SLMIP OpenView Service Desk Design document [1].

# System Overview

Figure 1 - SLMIP OpenView Service Desk System Overview

Please note that Web Console Cluster implementation has been removed from the work scope.

Please refer to the Detailed Design document [1] for further detail on the overview of the application.

# Application Overview

Figure 2 - SLMIP OpenView Service Desk Process Flow

Please refer to the Detailed Design document [1] for further detail on the overview of the application.

Please note Access Suite 4.0 has been replaced by Access Suite 3.5 as the QH production environment at go-live is expected to be Access Suite 3.5 (the approved design specified Access Suite 4.0).

# Testing scope, EXCLUSIONS & ASSUMPTION

## Scope

The scope of acceptance testing for this SLMIP Test Strategy will include (but may not be limited to) the following areas:

Table 4 - Testing Activities Scope

| Activity | Scope |
| --- | --- |
| Unit Testing | Unit testing program logic. |
| System Testing | - Build confidence testing. - Functionality testing. - Data Load & Migration testing. - Business Process testing. - OpenView Service Desk security testing. |
| System Integration Testing | Testing the interfaces between OVSD, GroupWise and TelAlert for notification |
| User Acceptance Testing | Subset of functional and business process testing. |
| Production Acceptance Testing | - Install - Failover - Data Load & Migration Testing - Backup and restore - Wan worthiness - Basic Smoke Tests (e.g., high level functionality such as printing, etc). - Check sociability - Check capacity is in line with expectations |

Change to the scope of testing can only be approved by the Test Progress Committee.

Details of the test activities mentioned above including test environment for each of these tests are described in the “Test Phases” section of this document.

## Scope Exclusions

The following table shows the tasks and outputs which are specifically excluded from the SLMIP Test Team testing scope (these exclusions confirm the boundaries of the scope of work of the Project):

Table 5 - Testing Scope Exclusions

Exclusions from Scope

Production Acceptance’s core infrastructure testing such as OS, patches related to OS, network connectivity between servers, database integrity and third party applications.

ITF’s core infrastructure testing such as OS, patches related to OS, network connectivity between servers, database integrity and third party applications.

Web Server and console testing

TelAlert system testing

Citrix system testing

OVO system and connectivity to OVSD testing

Proof of concept testing

Network security testing

Technology testing (eg. Operating system, hardware, database application)

The system testing mentioned above is specifically referring to functionalities testing of the system i.e. Tel Alert and Citrix to make sure these systems function according to their functional specifications.

## Scope Assumptions

The following table shows the assumptions that have been made to allow the Project Testing to proceed:

Table 6 - Testing Scope Assumptions

| Scope Assumptions | Basis for the assumption |
| --- | --- |
| No new functionality will be introduced during the testing planning and test execution phase | Detailed design document has been signed off by all relevant parties. |
| Only functionalities listed in the traceability matrix [2] and Detailed Design document [1] will be tested | ITMS testing guideline. |
| Crystal Reporting functionalities are included in the testing estimation, planning and execution. | Requirement document for OVSD Crystal Reporting. |

# KEY DATES

Table 7 - Testing Key Dates

| Start Date | End Date | Duration | Testing Activities |
| --- | --- | --- | --- |
| 4th May 07 | 21st May 07 | 12 days | Unit Testing |
| 28th May 07 | 5th June 07 | 8 days | System, System Integration & User Acceptance Testing |
| 5th June 07 | 26th June 07 | 12 days | Production Acceptance Testing |

# TEST PROGRESS COMMITTEE

The Test Progress Committee is formed as part of this project process improvement initiative. The committee is made up of SLMIP OpenView Service Desk project’s members.

The following are Test Progress Committee main responsibilities:

- Attending Test Progress Report meeting to discuss the following:

- Determine the existing open defects if they are genuine defects, change requests or neither.

- Review the severity classifications on existing open defects.

- Review the priority classifications on existing open defects.

- Discuss resolution strategy and resolution schedule on the existing open defects.

- Approving the strategy to exit ‘testing suspension’ state.

- Approving the final build at the end of each of the testing phases.

- Approving the reclassification of test plans from active into out of scope or deferred and vice versa.

Test Report Progress meeting will be scheduled within 5 days after a completion of test cycle on a new build.

The following SLMIP OpenView Service Desk project members are included in the committee:

- Project Manager

- Test Coordinator

- CTech Delivery Manager

- ITMS Manager

- InfoOperations Representative

- SIM3 Application Specialist

# Test Methodology

## Test and Acceptance

Testing and acceptance of deliverables will be undertaken on a continuous basis throughout the project.  Testing of documentation and supporting deliverables will be performed against the acceptance criteria.

Test planning and execution will be conducted using Mercury Quality Centre test management system as part of ITMS test policy. Only tests executed and recorded in Quality Centre test management system will be recognised as official tests.

The test requirements, plans, test runs conducted and perceived discrepancies will be recorded under the domain Information Directorate and project-name SLMIP project in the Mercury Quality Center test management system.

Mercury Quality Center test management system is accessible through the Queensland Health Intranet URL http://qualitycenter.health.qld.gov.au

Login access to Mercury Quality Center test management system can be provided by the ITMS manager.

## Test Phases

The SLMIP OpenView Service Desk testing strategy is to divide the testing activities into several distinct phases. Each test phase has its specific testing objectives, testing activities and entry and exit criteria. The following test phases have been adopted for this project.

Please refer to “Criteria” section for entry and exit criteria on each of the testing phase.

Change SLM Module

Unit Testing

Change SLM Module

System Testing

SYSTEM TESTING

COMPLETE MODULES

USER ACCEPTANCE TESTING

PRODUCTION ACCEPTANCE TESTING

SYSTEM INTEGRATION TESTING

Figure 3 – SLMIP OpenView Service Desk Test Phases

### Unit Testing

| Objective | To evaluate the application readiness for integration in ITF environment |
| --- | --- |
| Test Activities | Modular unit testing. |
| Support Group | CTech Delivery Team |
| Test Site | CTech Development Environment |

Test plans executed in unit testing phase will not be executed in Mercury Quality Center test management system. The CTech Delivery Team is responsible for completing the unit tests.

Test plans written by the CTech Delivery Team will be integrated into Mercury Quality Center test management system where appropriate so they can be used in system testing.

### System Testing

| Objective | - To verify solutions satisfy the requirements - To verify business process logic |
| --- | --- |
| Test Activities | - Functional Testing - Business Process Testing |
| Support Group | SLMIP Test Team, CTech Delivery Team, Technical Support Team, Project Manager, SIM3 Application Specialist and, ITMS Test Team. |
| Test Site | ITF |

The testing strategy is to deliver SLMIP OpenView Service Desk application into the ITF environment as a module. A complete system testing will then be executed on the complete systems consisting previously tested HP OpenView Service Desk modules.

This approach has the following advantages:

- System testing can commence as soon the first software module is available in ITF environment.

- Incremental baseline is possible for rollback purposes.

- Allows any defects to be discovered early.

- Regression testing can be conducted on the previous module.

Only SLMIP test team and ITMS personnel are allowed access to the test environment in ITF unless permission is granted by the ITMS manager. Build installation and configuration must be performed by a member of the ITMS team.

### System Integration Testing

| Objective | To verify that the application works according to the specification when it is integrated with external system. |
| --- | --- |
| Test Activities | - Functional Testing - Business Process Testing - Connectivity to External System Testing |
| Support Group | SLMIP Test Team, CTech Delivery Team, Technical Support Team, Project Manager, SIM3 Application Specialist and, ITMS Test Team. |
| Test Site | ITF |

The System Integration Testing will focus on connectivity testing between the SLMIP solution and the following external systems (not limited to):

- TelAlert

- GroupWise

Only SLMIP test team and ITMS personnel are allowed access to the test environment in ITF unless permission is granted by the ITMS manager. Build installation and configuration must be performed by a member of the ITMS team.

### User Acceptance Testing

| Objective | Provide end users with an opportunity to work through the business processes in a hands-on test environment. To Seek business acceptance of the application. |
| --- | --- |
| Test Activities | - An agreed selection of functional testing - An agreed selection of Business Process testing |
| Support Group | SLMIP Test Team, CTech Delivery Team, ITMS Team, End Users |
| Test Site | ITF |

Prior to the commencement of UAT, the users participating in the UAT will be provided with a document containing a selection of functional and business process test plans.

The following support groups will be involved in making these selections:

- Project Manager

- SIM3 Applications Specialist

- ITMS Manager

- Test Coordinator

- End Users

Prior to the commencement of UAT, a testing activities schedule document will be provided to the participating end user. The schedule will be approved by the same support groups as above.

UAT will not be performed in Mercury Quality Test Center test management system unless stated otherwise. Defects will still be recorded and managed in the Mercury Quality Test Center test management system.

Only SLMIP test team and ITMS personnel are allowed access to the test environment in ITF unless permission granted by the ITMS manager. Build installation and configuration must only be performed by a member of ITMS team.

UAT participating end users access to the ITF test environment will be restricted to the OpenView Service Desk User Interface only unless permission granted by  the ITMS manager.

### Production Acceptance Testing

| Objective | High level functionalities testing, focusing on the integrity and performance of the OpenView Service Desk application in the production model environment under various conditions. |
| --- | --- |
| Test Activities | - Application Install (ie load/build process) - Data Load ( - Backup - Failover - Build Confidence Tests (eg. confirm a subset of functional tests such as high level functionality such as creating records, ad hoc reporting, printing etc). - Wan worthiness - Check sociability - Check capacity is in line with expectations - Restore |
| Support Group | SLMIP Test Team, CTech Delivery Team, Production Acceptance Testing Team, Technical Assurance, SIM3 Application Specialist and ITMS Test Team. |
| Test Site | EDC - Block 7 Production |

Details of Production Acceptance testing are still being discussed between the support groups mentioned above and will be included in this document when they become available.

The SLMIP Team Testing Analyst will be responsible for documenting the “Actual Results” for all testing phases.

Prior to the commencement of the Production Acceptance testing, a document with a list of test plans must be submitted by the Production Acceptance test team and reviewed by the following support group:

- Project Manager

- SIM3 Application Specialist

- ITMS Manager

- Test Coordinator

- CTech Delivery Manager

Prior to the commencement of the Production Acceptance testing, the Production Acceptance Test plans must be approved by the following:

- Director of Tech Ops

- Director of Tech Assurance

- Director of SIM3

Prior to the commencement of the Production Acceptance testing, a testing activities schedule document will also be submitted by the Production Acceptance test team and reviewed by the above support groups.

Prior to the Production Acceptance Testing, the Production Acceptance testing activities schedule must be approved by the following:

- Director of Tech Ops

- Director of Tech Assurance

- Director of SIM3

Only the Production Acceptance test team is allowed access to the Production Acceptance test environment unless permission is granted by the Production Acceptance test team. Build installation and configuration must only be performed by a member of the Production Acceptance test team.

# Suspending and resuming testing

## Suspend Testing

The following are examples of instances that may cause a decision for suspension of testing.

- Major Defect(s) detected which can not be repaired in the scheduled testing period;

- Major change proposed which will void all testing underway;

- Failure in critical program – voids downstream testing;

- Software Builds fail;

- Environment not ready yet;

- Network issues;

- Imminent release of new hardware / software that will impact the environment to be tested;

- The System is determined to be so unstable that viable testing is impossible.

If testing is to be suspended for any reason, all stakeholders will be informed by email immediately and a meeting will be held to discuss strategy to exit the suspension state.

Please refer to the table below for the list of support groups who would be involved in such meeting.

Table 8 - Suspend testing exit meeting support groups

| Test Phase | Participating Support Groups |
| --- | --- |
| Unit Testing | Test Progress Committee |
| System Testing | Test Progress Committee |
| System Integration Testing | Test Progress Committee |
| Operational Testing | Test Progress Committee |
| Production Acceptance Testing | Test Progress Committee and the Production Acceptance test team |

## Resume Testing

Once a suspension is declared, resumption is directed by the support groups listed above for the SLMIP OpenView Service Desk solution after the issues causing the suspension are resolved.

If a decision to resume testing is made, all stakeholders will be informed by email.

# entry and exit CRITERIA

Strict requirements are defined for entering and exiting each of the test phases described above. If non-conforming, testing is suspended and will not resume until suspension reasons are corrected.

If Test Entry passes the review, all stakeholders will be informed by email that the system has entered testing and is in “lock down” – no changes should be made to the system under test.

If Test Exit passes the review, all stakeholders will be informed by email that the system has exit the testing phase.

The OpenView Service Desk will not be allowed to be release into production if the following certificates are not issued:

- ITF Acceptance Certificate, and

- Production Acceptance Certificate

## Unit Testing entry and exit criteria

There are no official entry and exit criteria for the unit testing phase.

## System testing entry criteria

The following are a list of criteria which must be met before entering this testing phase. Exemption on any of these criteria can only be granted by the Test Progress Committee.

Table 9 - System testing entry criteria

| Criteria and Deliverables | Ownership |
| --- | --- |
| - Test Package delivered to ITF containing: - Build installation and configuration instructions - CTech unit test progress report - Defect status report - The build package (binary and config files) | CTech Delivery Team |
| Test Planning and Analysis report containing: - Requirements established in Mercury Quality Center - Test plans established in Mercury Quality Center - Requirements test coverage established in Mercury Quality Center - Test lab test sets coverage established in Mercury Quality Center | SLMIP Test Team |
| ITF Test Environment Acceptance Form with the following attachments: - Hardware architecture assembled all platforms - Software environment established all platforms - Software environment proven all platforms - ITF test environment diagram and details - Approved build is installed and configured in the test environment | ITMS Team |
| Required data is available in the test environment (if applicable) | SLMIP Test Team and ITMS Team |

## System testing exit criteria

The following are a list of criteria which must be met before exiting this testing phase. Exemption on any of these criteria can only be granted by the Test Progress Committee.

Table 10 - System testing exit criteria

| Criteria and Deliverables | Ownership |
| --- | --- |
| System Test Progress Report. | SLMIP Test Team |
| Defect resolution agreement document outlining all existing open defects, their resolution and their resolution schedule. This document must be approved by the Test Progress Committee before exiting this test phase. | CTech Delivery Team |
| 100% of assigned test plans executed unless they have been classified as ‘out of scope’ or ‘deferred’ by the Test Progress Committee. This information would be included in the System Test Progress Report | SLMIP Test Team |
| The final build candidate must meet the following criteria: 70% of all current open defects are fixed and 30% of all current open defects are a combination of level 2, 3 and 4 severities with agreed defect resolution and timeframe. | SLMIP Test Team & CTech Delivery Team |
| Approved build baseline and archived. | ITMS Team |
| Test data backed up. | ITMS Team |

There are no defect severity criteria for intermediate builds.

If the final build candidate in this test phase failed then a new candidate build must be submitted and installed in the ITF environment along with defect report status. The build will then be subjected to the following tests:

- New test plans if applicable.

- Regression test plans if applicable.

- Defect verification if applicable

The new build is then subjected to the exit criteria described above.

## System Integration testing entry criteria

The following are a list of criteria which must be met before entering this testing phase. Exemption on any of these criteria can only be granted by the Test Progress Committee.

Table 11 – System Integration entry criteria

| Criteria and Deliverables | Ownership |
| --- | --- |
| ITF Test Environment Acceptance Form with the following attachments: - External system connectivity to OpenView Service Desk application proven. - Updated ITF test environment diagram and details with the external systems which are going to be connected to the OpenView Service Desk application. - Approved build is installed and configured in the test environment | ITMS Team |
| Required test data is available in the test environment | SLMIP Test Team and ITMS Team |

## System Integration testing exit criteria

The following are a list of criteria which must be met before exiting this testing phase. Exemption on any of these criteria can only be granted by the Test Progress Committee.

Table 12 – System Integration testing exit criteria

| Criteria and Deliverables | Ownership |
| --- | --- |
| System Integration Test Progress Report. | SLMIP Test Team |
| Defect resolution agreement document outlining all existing open defects, their resolution and their resolution schedule. This document must be approved by the Test Progress Committee before exiting this test phase. | CTech Delivery Team |
| 100% of assigned test plans executed unless they have been classified as ‘out of scope’ or ‘deferred’ by the Test Progress Committee. This information would be included in the System Test Progress Report | SLMIP Test Team |
| The final build candidate must meet the following criteria: 80% of all current open defects are fixed and 20% of all current open defects are a combination of level 3 and 4 severities only with agreed defect resolution and timeframe. | SLMIP Test Team & CTech Delivery Team |
| Approved build baseline and archived. | ITMS Team |
| Test data backed up. | ITMS Team |

There are no defect severity criteria for intermediate builds.

If the final build candidate in this test phase failed then a new candidate build must be submitted with defect report status. The build will then be subjected to the following tests:

- New test plans if applicable.

- Regression test plans if applicable.

- Defect verification if applicable

The new build is then subjected to the exit criteria described above.

## User Acceptance Testing entry criteria

The following are a list of criteria which must be met before entering this testing phase. Exemption on any of these criteria can only be granted by the Test Progress Committee.

Table 13 - User Acceptance Testing entry criteria

| Deliverables | Ownership |
| --- | --- |
| A document listing test plans to be executed in UAT. | Test Progress Committee |
| A testing schedule document outlining day to day testing activities in UAT | Test Progress Committee |
| ITF Test Environment Acceptance Form with the following attachments: - Test environment readiness report. - Approved build is installed and configured in the ITF environment. | ITMS Team |
| Required data is available in the ITF environment | SLMIP Test Team and ITMS Team |

## User Acceptance Testing exit criteria

The following are a list of criteria which must be met before exiting this testing phase. Exemption on any of these criteria can only be granted by the Test Progress Committee.

Table 14 – User Acceptance Testing exit criteria

| Criteria and Deliverables | Ownership |
| --- | --- |
| User Acceptance Testing Progress Report. | SLMIP Test Team |
| Defect resolution agreement document outlining all existing open defects, their resolution and their resolution schedule. This document must be approved by the Test Progress Committee before exiting this test phase. | CTech Delivery Team |
| 100% of assigned test plans executed unless they have been classified as ‘out of scope’ or ‘deferred’ by the Test Progress Committee. This information would be included in the System Test Progress Report | SLMIP Test Team and End Users |
| The final build candidate must meet the following criteria: 80% of all current open defects are fixed and 20% of all current open defects are a combination of level 3 and 4 severities only with agreed defect resolution and timeframe. | SLMIP Test Team & CTech Delivery Team |
| Approved build baseline and archived. | ITMS Team |
| Test data backed up. | ITMS Team |
| ITF Acceptance Test Certification | ITMS Manager |

There are no defect severity criteria for intermediate builds.

If the final build candidate in this test phase failed then a new candidate build must be submitted with defect report status. The build will then be subjected to the following tests:

- New test plans if applicable.

- Regression test plans if applicable.

- Defect verification

The new build is then subjected to the exit criteria described above.

## Production Acceptance testing entry criteria

The following are a list of criteria which must be met before entering this testing phase. Exemption on any of these criteria can only be granted by the Test Progress Committee.

Table 15 – Production Acceptance Testing entry criteria

| Deliverables | Ownership |
| --- | --- |
| A document listing test plans to be executed in Production Acceptance. | Production Acceptance Team (InfoOperations) |
| A testing schedule document outlining day to day testing activities in Production Acceptance. | Production Acceptance Team (InfoOperations) |
| Production Acceptance Test Environment Acceptance Form with the following attachments: - Test environment readiness report. - Approved build is installed and configured in the Production Acceptance environment. | Production Acceptance Team (InfoOperations) |
| Required data is available in the Production Acceptance environment | SLMIP Team |
| Final Application Software confirmed | SLMIP Team |
| Implementation packages delivered – build/install & backup processes including documentation and configuration parameters | SLMIP Team |
| UAT sign off | SLMIP Team |

## Production Acceptance testing exit criteria

The following are a list of criteria which must be met before exiting this testing phase. Exemption on any of these criteria can only be granted by the Test Progress Committee.

Table 16 – Production Acceptance Testing exit criteria

| Criteria and Deliverables | Ownership |
| --- | --- |
| Production Acceptance Testing Progress Report. | SLMIP Test Team |
| Defect resolution agreement document outlining all existing open defects, their resolution and their resolution schedule. This document must be approved by the Test Progress Committee before exiting this test phase. | CTech Delivery Team |
| 100% of assigned test plans executed unless they have been classified as ‘out of scope’ or ‘deferred’ by the Production Acceptance Team (Info Operations). This information would be included in the System Test Progress Report | Production Acceptance Team (InfoOperations) |
| The final build candidate must meet the following criteria: 80% of all current open defects are fixed and 20% of all current open defects are a combination of level 3 and 4 severities only with agreed defect resolution and timeframe. | Production Acceptance Team (infoOperation) & CTech Delivery Team |
| Approved build baseline and archived. | Production Acceptance Team (InfoOperations) |
| Test data backed up. | Production Acceptance Team (InfoOperations) |
| Production Acceptance Test Certification | Production Acceptance Team (InfoOperations) |

There are no defect severity criteria for intermediate builds.

If the final build candidate in this test phase failed then a new candidate build must be submitted with defect report status. The build will then be subjected to the following tests:

- New test plans if applicable.

- Regression test plans if applicable.

- Defect verification

The new build is then subjected to the exit criteria described above.

# Test REPORTING

Test report will be presented to management and development team at the end of each test execution cycle.

This report will include (but not limited to) the following information:

Information such as testing objective, current testing phases and test issues.

Summary of new defects grouped by severity and priority.

Summary of open defects grouped by severity and priority.

Summary of closed defects grouped by severity and priority.

Summary of rejected defects grouped by severity and priority.

Summary of re-opened defects grouped by severity and priority.

Summary of defect resolution turn around grouped by severity and priority.

Defect Analysis – Test Procedure Error

Defect Analysis – Test Data Error

Defect Analysis – Tester/User Errors

Defect Analysis – Test Environment or Configuration Errors

Defect Analysis – Code/Implementation Errors (code bugs)

Defect Analysis – Design Errors (system logic errors)

Defect Analysis – Misinterpreted Requirement

Defect Analysis – New Requirement (not previously stated)

Defect Analysis – Enhancements (Nice-to-haves)

The test report will report the testing progress in a snapshot and cumulative format.

Test report will be distributed to members of the Test Progress Committee.

# TEST Environment

Details of the testing environments to be assembled follow.

## Test Location(s)

Testing will be conducted at these locations: Citilink building and Block 7 of RWBH.

Table 17 – System, System Integration and UAT Test Site

| Location |  | Contact |  |
| --- | --- | --- | --- |
| RBWH Block 7 Citilink Building. |  | SLMIP Test Co-ordinator / ITMS Manager |  |
| Business Hrs | Access | Phone | Facsimile |
| 8am-6pm (business working day) | Swipe card | Refer to table 24 | Not available |

Table 18 - Production Acceptance Test Site

| Location |  | Contact |  |
| --- | --- | --- | --- |
| RCH Block 7, Level 10 (EDC) |  | Production Acceptance Test Co-ordinator |  |
| Business Hrs | Access | Phone | Facsimile |
| 8am-6pm (business working day) | Swipe card | Refer to table 24 | Not available |

## Hardware

The Test and Production Acceptance environments will attempt to replicate the production environment on a smaller scale.  These environments are described below.

Table 19 - Hardware Requirement for System, System Integration and UAT

| Hardware Devices For System, Operational and UAT | Capacity |
| --- | --- |
| Sun servers – itfsu01, itfsu02 -Clustered | Oracle (OVSD DB), FTP Server, Reporting Data Warehouse |
| 2xWintel servers | Primary and secondary Service Desk Servers |
| Wintel server | Primary TelAlert Servers |
| ~5 Windows desktops | OV Service Desk clients |
| Wintel server | GroupWise Server |
| Wintel server | MessageNet Connectivity |
| Citrix server | Primary Citrix Gateway |

Table 20 - Production Acceptance Test hardware requirements

| Hardware Devices For Pre Production Acceptance | Capacity |
| --- | --- |
| Sun 15k Frame – 3xdomain (DB server) - Clustered | Oracle (OVSD DB), FTP Server, Reporting Data Warehouse |
| 2xWintel servers | Primary and secondary Service Desk Servers |
| 2xWintel servers | Primary TelAlert Servers |
| 5xWindows desktops | OV Service Desk clients |
| Citrix server | Primary Citrix Gateway |

## Networks & Communications

The network will be established to cater for groups and individuals testing in the ITF and Production Acceptance environments.

## Software

The Test environment will best replicate the production software environment, whilst the Production Acceptance environment will attempt to match as closely as possible to the production software environment for the system or service under test using the available resources.

## Test Support Software Tools

The testing methodology is supported by the Mercury Quality Center Test Management System.

Details of test support software tools are still being reviewed.

# TESTING Resources

The following table defines the roles and responsibilities of the support groups during the testing period.

Table 21 - List of Testing Support Groups

| Role | Support Group/Person | Responsibilities |
| --- | --- | --- |
| Project Manager | John Crouch | - Provide technical direction - Approve test resources, plan and schedule |
| SIM3 Application Specialist | Chris Hughes | - Provide technical direction - Ensuring a successful entry to Production Acceptance testing. - Ensuring a successful completion of Production Acceptance testing. |
| CTech Delivery Team | Anthony Symons, Muthu Kumar Raju | - Execute unit testing - Provide report on unit testings - Provide defects resolution |
| CTech Delivery Team Manager | Gavin McKee | - Manage the development effort - Provide technical direction |
| Test Coordinator (part of SLMIP Test Team) |  | - Leads and manages the testing - Manages resources and interface issues - Manages reporting - Develops test documentations - Identifies and develops test specifications - Provides training in testing techniques - Provides training in test tools |
| Test Analysts (part of SLMIP Test Team) | Jill Perkins, Linda Stubbins | - Write test plans and steps - Executes the tests - Records results - Assists developer with defect resolution - Assist test coordinator with testing effort - Assists with developing test documentation |
| Technical Support Team | Anthony Symons, Jill Perkins | - Provide technical assistance with regards of system solution. |
| ITMS Team | TBA | - Create and maintain automated test scripts when required - Load, fail over and performance testing in ITF environment - Provide technical support such as backing up data and build. |
| ITMS Manager | John Moylan | - Approve test effort - Provide project test certification on the completion of the test. - Provide guideline and policy with regards to testing. |
| Technical Assurance | TBA | - TBA |
| Production Acceptance Test Team | TBA | - TBA |
| Production Acceptance Test Coordinator | TBA | - TBA |
| Business stakeholders | TBA | - Participate in User Acceptance Testing when required |

Table 22 - Support Group Contact Details

| First Name | Surname | Phone | Mobile | Email Address |
| --- | --- | --- | --- | --- |
| John | Crouch | (07) 3131 1619 |  | John_Crouch@health.qld.gov.au |
| Gavin | McKee | (07) 3131 1638 | 0432 564 526 | Gavin.mckee@health.qld.gov.au |
| Muthu | Raju |  | 0401 800 435 | Muthu_kumar_raju@health.qld.gov.au |
| Anthony | Symons |  | 0411 285 871 | Anthony.symons@health.qld.gov.au |
| John | Moylan | (07) 3131 1568 |  | John_Moylan@health.qld.gov.au |
| Chris | Hughes | (07) 3636 4723 |  | chris_hughes@health.qld.gov.au |
| Jill | Perkins | (07) 3636 4888 |  | jill_perkins@health.qld.gov.au |

# Defect Management

## Defect Registration

All defects must be registered in Quality Center Test Management tool, and for each defect the minimum information listed below will be recorded:-:

ID: The ID allocated to each defect (unique key) automatically by Quality Center;

Modified: Date defect status modified;

Reproducible: Is defect reproducible or not;

Subject: A reference to test plan

Project: A reference to project

Summary: A title or brief summary of the defect (a sentence or heading outlining the subject of the defect);

Description: A detailed defect description (a description of the symptoms of the problem, where possible providing examples of data used and the scenario or test condition as a reference);

Detected By: The User ID of the person who raised the defect;

Detected on Date: Date defect detected/raised;

Detected in Version: The version of the deliverable in which the defect was detected;

Assigned To: A nominated person to analyse and resolve the defect;

Severity: The level of severity allocated to the defect (see below for severity details);

Priority: The urgency for resolution allocated to the defect (see below for priority details);

Status: The status of the defect (eg New, Open, Fixed, Rejected, Reopen)

Attachements: An attachment of supporting documents and screenshot may be included in the defect registration form.

Defects will be stored in the Mercury Quality Center Test Management system for archiving and reporting.

Figure 4 - Screenshot of 'Add Defect' Page in Mercury Quality Center

## Defect Management Cycle

The following approach will be applied to defect management:

Figure 5 - Defect Life Cycle

## Defect Definitions - Severity Classifications

These codes have been setup to indicate the severity of a problem based on the impact that it would have in a production environment. These codes will be used for the raising of defects found during testing phases.

Table 23 - Defect Severity Classifications

| Severity Rating | Classification/Description |  |  |
| --- | --- | --- | --- |
|  | Business Impact | Testing Impact | Technical Impact |
| 1 - Critical | The failure causes a system crash or unrecoverable data loss or causes impairment of critical system functions. The customer cannot continue using the software. No acceptable work-around exists. Business risk is high | Testing cannot continue or the majority of test cases would be invalidated if testing continued. | The failure prevents deployment of the system into production or deployment of the system would severely impact stability of the production environment. |
| 2 - High | The failure causes impairment of system function. The customer can still use the software but cannot perform a critical task and no acceptable workaround solution exists for that task. Business risk is moderate. | Testing can continue. Testing of impaired function and related functions/areas is impacted. | Would impact implementation of system into production or would impact production stability of system and/or other systems. |
| 3 - Medium | The failure causes impairment of system function or component. The customer can use the software (an acceptable workaround exists) but the defect is very annoying. Business risk is low. | Testing can continue. Invalidates a localised group of test cases. | Localised impact on implementation of system into production or localised impact on production stability of system and/or other systems. |
| 4 - Low | The failure causes inconvenience or cosmetic in nature. Long-term work-around for use in production is acceptable to the customer. Business risk is negligible | All testing can continue. No testing invalidated. | No impact on implementation of system into production and no impact on production stability of system and/or other systems. |

Defect Definitions - Priority Classification

Following assignment of a severity level, each defect will be allocated a priority for resolution. The turn-around time required for fixing a problem, based on the potential impact to the testing schedule, will be used in allocating priority codes.  The following table shows the priority codes and their meanings:

Table 24 - Defect Priority Classification

| Priority | Definition |
| --- | --- |
| 1 | Urgent Major impact to testing schedule – resolution required as soon as possible. |
| 2 | High Significant impact to testing schedule – resolution required within 24 hours. Other test cases may be run until resolution completed. |
| 3 | Medium Moderate impact – resolution required within 48 hours. Linked test cases may be run but with alternative path to achieve the same outcome. |
| 4 | Low Minimal impact – resolution required within timeframe agreed between Test Manager and solution provider, post-implementation resolution might be an option. |

## Pass/Fail Criteria

Every test step in the test plans will state the expected result. Test Plans will be developed in the Test Planning phase.

### Pass Test

During test execution, if the actual result matches the expected result, the test passed.

### Fail Test

During test execution, if the actual result does not match the expected result, the test failed.

# Risks Management

The following table details the risks identified to date associated with the Project Testing scope defined above:

Table 25 - Risks Management

| Risks | Risk Management |
| --- | --- |
| New functionalities introduced during the test planning and execution phase. | Project Impact report must be provided to the test coordinator and a meeting must be conducted to determine if the functionalities can be included in the current timeframe. |
| Test environment not ready for testing. | Submit test environment request to the support group as early as possible. Have visibility on the progress of setting up the test environment. Alternative test environment can be used provided it is approved by the ITMS Manager. |
| Support Group not available | Appoint personnel in each of the support group as soon as possible. Whenever possible, appoint extra personnel in each of the support group as backup. |
| Test environment is not stable | Conduct confidence test on the environment prior to the commencement of testing. |
| Interfaces not available | Identify this early in the testing phase and develop simulator as a replacement of the interface. |
| Testing delayed due to high level of defects | A meeting must be conducted between management team, test team and the development team on strategy to minimize the high level of defects. Instead have a “big bang” drop approach, have multiple drops to have a progressive baseline on the application. Make weekend as an allowance in the testing schedule to meet the testing deadline. |