PIR Report

for the

Post Implementation Review

Copyright© itsm IP 2009

Document Information:

| Prepared By: | Anthony Symons |
| --- | --- |
| Title: | ITSM Consultant |
| Document Version: | 0.1 |
| Document Version Date: |  |

Document Distribution List:

| To | Action | E-Mail |
| --- | --- | --- |

Version History:

| Version | Version Date | Author | Description |
| --- | --- | --- | --- |
| 0.1 | 11-Mar-09 | Anthony Symons | Initial Draft |

Proprietary Notice

This document is the property of itsm Partnership Pty Ltd. All copyright is pursuant to the license by itsm Partnership Pty Ltd accompanying this document.

COPYRIGHT

All information contained in this document which relates to itsm Partnership Pty Ltd shall be kept absolutely confidential.

All {Client Field} employees and their representatives shall not communicate, release or permit the communication of any information or data provided, collected and or developed for the purpose of or in connection with this document except, for the purpose of or in connection with the performance of evaluating the document.

The information contained in this document constitutes trade secrets and/or information that is commercial or financial and confidential or privileged. It is provided to {Client Field} in confidence with the understanding that it cannot, without permission of itsm Partnership Pty Ltd be used or disclosed for any purpose.

©Copyright 2009 itsm Partnership Pty Ltd. All rights reserved.

Table of Contents

1	Heading 1	5

1.1	Heading 2	5

1.1.1	Heading 3	5

# Management Summary

## Introduction

This report is the result of the Post Implementation Review (PIR) undertaken for the {Project Name}.

The PIR covers the end to end processes throughout all phases, and incorporates findings from Business, IT, Project Staff and Project Governance groups.

It contains findings and recommendations identified as a result of the investigation.

## Organisation Context

It is important to note that at the time of this project being run the {Client Field} was undergoing significant change.  This included ...

Sample text: On initiation of the project several key stakeholders had not yet been appointed to their roles.  Most staff required to contribute to the implementation of this change had (at best), not yet come to terms with the change in organisation structure and the new approach to service delivery.

In parallel, work was being undertaken internally to understand each department’s responsibilities at an operational level and their interactions between departments.  This created a moving target where some decisions were only tentative and subject to change as the organisation stabilised.

## Conduct

Overall, the project conduct was rated as average.

## Key recommendations

The Key recommendations are:

| # | Description |
| --- | --- |
|  | Sample text: Ability for end users to have a play pen prior to implementation would have assisted with building user confidence. |
|  | Sample text: Planning for project team review of the HP training content prior to training commencement would have improved the relevance to the QH environment. |
|  | Sample text: Early engagement with a broader/lower level of stakeholders would have assisted with the change uptake (eg. Middle management layer/team leaders etc). |
|  | Sample text: Provision of more clarity on the process to move through the development lifecycle into Test & Production environments. |
|  | Sample text: More support for and/or assessment of super user’s ability to ensure they have the capability to act in the change support role. Consider need to backfill during key times (eg. Immediately following implementation). |
|  | Sample text: Education of end users was overview based. Consider altering to focus on the operational impacts of the change (ie. A day in the life of a person providing desktop support services). Look at connecting the change to the person’s role not a generic function. |
|  | Sample text: Ensure test environment(s) enables distributed environment issues to be identified and that it is scalable to enable performance and load testing to be undertaken. |
|  | Sample text: Obtain more input from {Client Field} during the design phase to recommend any deviations from the vendor approved architecture to the Steering Committee to ensure ongoing supportability requirements are assessed. |
|  | Sample text: Factor some recurrent costs into the project budget & ensure co-location of resources to enable the scale up & knowledge transfer to the support team (both application and technical). |
|  | Sample text: Introduce a mechanism for measuring performance of management communications to staff or alternatively (less desirable) fund and recruit a dedicated communications officer within the project. |
|  | Sample text: An estimation/costing model needs to be put in place to facilitate accurate budgeting at business case development stage. |
|  | Sample text: A documented process needs to be established detailing what the handover requirements are for projects to support mode. |

# Introduction

## Purpose

The purpose of this PIR is to

- Review the Service Management Implementation Project to understand what was successful and what was unsuccessful.

- Recommend changes to the {Client Field} standard processes.

## Scope

The PIR covers the phases of:

- Project Initiation;

- Project Management;

- Vendor Management;

- Product/System Engineering;

- Testing:

- Implementation;

- Support and Maintenance;

- Organisational Change Management and

- Provides findings and recommendations identified as a result of the investigation.

## PIR Approach

The PIR was conducted using the following approaches:

- Workshops with Vendors, Key IT Areas, and Steering Committee members.

- Super users were surveyed using a PIR Questionnaire via email;

- One on one meetings held with Key Business Representatives;

- Training evaluation;

- Review of Risks, Issues and Changes raised during project; and

- Project team members were also surveyed for their contribution towards this report.

Note:  People unable to attend workshops or one on one meeting’s were requested to contribute via the PIR Questionnaire.

All findings and recommendations have been consolidated and documented as follows:

- Key Recommendations (see Section 1.4 - Key recommendations)

- Summary of successes and issues raised (see section 5.2 - Project Activities Table)

- Consolidated findings and recommendations (see section 6 - Detail of Findings and Recommendations)

- Individual raw responses (see Appendix).

## Follow-Up Process

The Project Sponsor & Delivery Office will be provided with this report to enable them to address the key recommendations and ensure that appropriate follow up is performed as required.

## Constraints

At the time of completion of the PIR:

- Some project team members had left and were unavailable to input into this PIR; and

- The Vendor Application training evaluation material was not available.

# Project Overview

## Summary of {Project Name}

Under the Transformation Program the a chartered has been created with developing and designing a number of new Information Technology Service Management (ITSM) processes based upon greatest business need as determined by the ‘Current State Assessment’ and ratified with the {Project Name} Sponsor & Steering Committee.

The following ITSM process designs were completed in Mth 20xx with handover to the respective Process Owners by the end of Mth 20xx:

- Incident Management

- ICT Change Management

- Configuration Management

On 20 September 2005 the ISIB approved funding to perform a detailed design study to implement these processes across Queensland Health which established the Service Management Implementation Project.  They also provided “in principle” approval for the implementation costs which were subsequently confirmed following completion of the detailed design study.

The Service Management Implementation Project encompasses three areas:

- The implementation of the ITSM processes for Incident, Change and Configuration Management as developed by the Transformation Program.  In addition the project would implement standard service levels that are required in order to support these processes.

- The establishment of state wide business rules and policies that underpin the processes, such as incident categorisation and prioritisation, resolver groups, standard change and work request lists, change approval boards and standardisation of configuration item naming conventions etc. which will enable standardisation and consistency in service delivery.

- The implementation of a Service Management application that is interoperable with existing and proposed infrastructure, is “fit for purpose” but scaleable, thus positioning the {Client Field} for planned improvements to service delivery.

## Project Major Deliverables

### Scope of SMIP was limited to:

- Project Management: Planning, coordinating and controlling the overall delivery of the project;

- Implement the following Processes to support Enterprise Applications and Infrastructure only:

- Incident Management;

- ICT Change Management;

- Configuration Management (including population of the Configuration Management Database (CMBD));

- A partial implementation of operational service levels for the Incident and Change Management processes to function;

- Interim process for the updating of PC & Printer configuration items from and to the Asset Management tool with the ultimate goal to minimise impact to the users with regard to new Configuration Item (CI) data entry;

- Configure, customise, test and implementation of the ITSM tool to support the above processes;

- Development of the business rules, standards and operational lists of services required to support the processes;

- Purchase, installation & set up of associated infrastructure for Development, Test & Production environments;

- Definition and development of standard reports and provision for ad hoc reporting;

- Development of the following interfaces:

- Email to Support Officers;

- Short Message Service (SMS) to Support Officers;

- Management escalation;

- Data migration and cleansing limited to those fields as identified in the Data Migration Strategy being completed as part of the Detailed Design phase.

- Establishment of the Change Approval Authorities & decommissioning of any old ones.

- Production Rollout / implementation: Implementation planning and the design/establishment of support, installation instructions and handover documentation;

- Publishing of processes & procedures.

- Organisational Change Management: Planning & delivery of the change management aspects for the project;

- User Training: development and delivery of application & process training material.

# Business Benefits

In addition to having 3 benefits directly associated with the project, the Service Management Implementation project was required to be performed in order to harvest a number of the benefits identified by the Transformation Program as they relate to efficiencies.

The following sections identify not only those benefits directly associated with the project delivery but also those where a strong dependency exists for the achievement of Transformation benefits.

## Non-Financial Benefits

Non-financial benefits directly associated with the project are listed in the following table.

| Outcome # & Name | Benefit Description | Business Owner |
| --- | --- | --- |
| Provision of a single source of truth for service delivery reporting. | Improvement to decision-making will be achieved by using a standard set of information which is consistent across the state |  |

Non-financial benefits that have a high dependency on this project for their achievement are listed below:

- Zero Unscheduled Impact on {Client Field} Business - The current ICT Change Management process is complex, resource intensive and inconsistently applied.  This process encourages the taking of shortcuts or improper classification, facilitates duplication of effort and poor planning, and does not consider risk appropriately.  Implementation of a best practice based ICT Change Management process that is repeatable, that is efficient and effective, where emergency ICT change is quick and accurate and driven by business need, and services are protected will facilitate a benefit of zero unscheduled impact on QH business.

- Efficiency Of Processes Dependent On Configuration Management Increased - The current state-wide process for Configuration Management is not fully adopted or supported, and no one Configuration Management database provides {Client Field} with a single source of truth, accurate Configuration Item data or the relationships that exist between these Configuration Items.  Introducing a best practice Configuration Management process will assure data integrity, increase the accuracy of Configuration Item information and establish an essential and accurate Service Impact Analysis capability.  The flow on effect of this process is that dependant processes experience an increase in efficiency.

- Service Centre is Single Point of Contact for All Products & Services Offered by {Client Field} - The {Client Field} is proactively moving to consolidate the disparate Service Desk locations, processes & tools into a single Service Centre.  Ultimately, this consolidation will provide the significant benefit to both the customer and the {Client Field} of a single point of contact for all {Client Field} products and services.

- Disruption to {Client Field} Business through Incidents is Decreased - The {Client Field} currently does not have a defined end-to-end service delivery model that monitors IT service Incidents holistically.  Establishment of the consolidated Service Centre with best practice processes, trained staff & ‘fit for purpose’ tools will provide an ongoing Benefit of decreasing the disruption to {Client Field} business through Incidents.

- Customer Satisfaction & User Confidence in Relation to Incident Management Increased - The {Client Field} is proactively moving to consolidate the disparate Service Desk locations, processes & tools into a single Service Centre.  The achievement of this initiative will have a number of flow-on benefits, most significantly that customer satisfaction and user confidence in relation to Incident Management is increased.

## Financial Benefits

Financial benefits directly associated with the project are listed in the following table.

| Outcome # & Name | Benefit Description | Business Owner |
| --- | --- | --- |
| Saving on Infra Maintenance Costs. | Due to the capabilities provided by the new Service Management tool, there will be a decreased requirement for licenses in the Service Desk. It is expected that 20% of licenses will need to remain in operation to support asset management and procurement management activities. This benefit is expected to be in the order of $xxxK over three years. |  |

Financial benefits that have a high dependency on this project for their achievement are listed below:

- Decreased Cost of Operational Maintenance through Review of Support & Carriage Contracts - By reviewing the current carriage and support contracts maintained by {Client Field}, an annual saving of up to $xM per annum can be made through renegotiation or contract termination.

- Decrease Cost of Labour through Process Efficiencies Achieved in Implementation of Problem Management Process - A decrease in the cost of labour is experienced through the implementation of the new Problem Management process, developed as part of the Transformation Program.  The value of this savings is estimated to be ...

# Project Milestones & Activities

## Project Plan

The timeline presented in the following table represents the baseline, the deviation from the project plan, the cause for any discrepancies provided by the project contributors and the writers findings during document perusal and investigation.  It should be noted that there was a need to rebaseline the schedule mid way through the project.

| Baseline Date Due | Date Complete | Description | Comments |
| --- | --- | --- | --- |
| dd/mm/yyyy | dd/mm/yyyy | Project Start | Complete on schedule |
| dd/mm/yyyy | dd/mm/yyyy | Detailed Design Complete (includes {Client Field} funding approval) | Although all deliverables were ready and submitted on the due date, the milestone completed 1 week behind schedule due to the {Client Field} meeting being delayed by 1 week. |
| dd/mm/yyyy | dd/mm/yyyy | Service Desk to Email Design Document | Complete on schedule |
| dd/mm/yyyy | dd/mm/yyyy | Configuration Management Module Configuration complete | Complete on schedule |
| dd/mm/yyyy | dd/mm/yyyy | Change Management Module Configuration Complete | Complete on schedule |
| dd/mm/yyyy | dd/mm/yyyy | Service Call Module Configuration Complete | Complete on schedule |
| dd/mm/yyyy | dd/mm/yyyy | System/Integration & UAT Testing Complete | Slippage caused by the need to issue a new build which was required to fix a defect that the business were not prepared to accept in production. |
| dd/mm/yyyy | dd/mm/yyyy | UAT Infrastructure build complete | Complete on schedule |
| dd/mm/yyyy | dd/mm/yyyy | UAT Application install complete | Complete on schedule |
| dd/mm/yyyy | dd/mm/yyyy | Production Acceptance Testing Complete | Complete on schedule |
| dd/mm/yyyy | dd/mm/yyyy | Production Infrastructure build complete | Complete on schedule |
| dd/mm/yyyy | dd/mm/yyyy | Production Application Install Complete | Although this has been completed previously & tested, due to the data migration approach being taken a final application install is scheduled for dd/mm/yyyy. |
| dd/mm/yyyy | dd/mm/yyyy | Deploy to Production | Complete on schedule |
| dd/mm/yyyy | dd/mm/yyyy | Project Closure | Expected to complete on schedule |

## Project Activities Table

The following matrix presents the Project activities undertaken, the Level of confidence reported by the contributors of how well each activity was undertaken, the successes and issues raised regarding the activities during interviews and questionaries and also recommendations made during the interviews. The findings presented provide the view of the project contributors and are backed by the documents surrounding the project as contained in the Appendix.

The rating scale is as follows: Poor, Average, and Good

| Project Activities | Rating | Successes | Issues Raised / Comments |
| --- | --- | --- | --- |
| Project Initiation |  |  |  |
| Initial Cost/Benefit Analysis at or prior to Approval Stage | Good | Project was piloted through the Investment Office process for development of the business case and submission to {Client Field} for funding approval. | Some confusion existed between funding sources for Capital and Operational/Recurrent Funds. |
| Approval of Business Case | Good | Managed formally via {Client Field}. |  |
| Project Governance Structure | Good | Steering Committee established with documented Terms of Reference. Active and strong support received from Project Sponsor and Process Owners. | {Client Field} role unclear. SC membership evolved throughout the project phases (ie. Design to Implementation) resulting in some SC members not fully understanding the history of decisions or their specific role – previous members should ensure a clear handover is given to new members. |
| Project Management Structure | Good | Overall Project Manager acted as system integrator (hence held responsibility for all aspects of the project). This allowed the vendor project manager to concentrate on delivery of the product. Assisted with development of a good partnership. | May have assisted to have earlier engagement with the Operations area at this level to streamline the dependant activities for build of the UAT and Production environments however it is noted that {Client Field} was not yet operational. |
| Project Team Structure/Initiation | Good | Role and responsibilities were documented and inductions performed for all project team members. |  |
| Project Management |  |  |  |
| Development and Approval of detailed business requirements | Average | Signed off processes were used to drive the business requirements supplemented with additional workshops to elicit lower level functional requirements. | Non functional requirements/expectations not gathered. Level of stakeholders involved did not necessarily understand the operational impacts of the requirements. |
| Project Plan/ Statement of Work finalised | Good | Project plan completed and approved by Sponsor to set the scope and approach for project delivery. |  |
| Schedule/Time Management | Average | Project delivered according to the baseline schedule. | Required to raise a change request to move the baseline by one month as a result of resource constraints affecting the ability for the UAT and Production environments to be built as per the original schedule. Earlier engagement & planning with a lower level of stakeholders within {Client Field} could have prevented this. |
| Scope Management | Good | Agreed scope was met. | Scope should have included Load/Performance testing. |
| Budget and Cost Management | Good | Project was appropriately funded and closed less than 10% under budget. |  |
| Monitoring/management of Interdependencies | Average |  |  |
| Quality Management | Average | Quality plan existed. | Product testing did not consider distributed deployment. |
| People management | Good | Regular meetings held. Staff understood roles and delivery deadlines. |  |
| Communication Management | Average |  | There was confusion over {Client Field} versus {Project Name} and who should be facilitating the communications. Team briefings not effective. |
| Stakeholder Management (Incl Districts) | Poor | Regular workshops held through design phase. Regular sponsor/process owner meetings ensured the project maintained focus. | Organisational flux made this a moving target as many key positions remained vacant for much of the project life. Should look at including a broader/lower level of stakeholders to assist with delivery of the change (eg. Middle Management/Team leads level). {Client Field} staff should have been engaged earlier. |
| Risk and Issues Management | Good | All risks were documented and managed within the project team. Only very high risks were raised for Steering Committee attention. | Some decisions taken to accept certain risks have resulted in post implementation issues being felt. |
| Benefits Management | Average | Results chains were completed and key benefits documented within the Business Case. | Inability to take a baseline prior to implementation due to the varying processes following throughout the state may make it difficult to measure benefit achievement. It is not apparent how the ongoing benefits management will be performed. |
| Procurement |  |  |  |
| Resources | Average | Early identification on resource requirements ensured procurement timings were taken into account. Ability to use resources from Transformation assisted with knowledge transfer and ability to commence delivery aspects immediately. | Long lead time to obtain resources has the ability to jeopardise the project timelines if not catered for during planning. No pool of technical resources exists to perform short term activities such as the build & support of environments (eg. Within the Test Environment). |
| Hardware | Average |  | No strategic thought around hardware requirements results in a need to purchase from scratch. |
| Software | Average |  | Vendor contract should have been written such that {Client Field} did not own licenses until go-live |
| Organisational Change Management |  |  |  |
| User Training | Poor | Use of {Client Field} staff (super users) to deliver training. Project funded all training expenses including travel for remote areas. An ongoing training strategy has been developed and agreed (eg. E-learning, super user support etc) and included in the new staff induction package. | Training focussed on theory, not operational impact. Gap between when training was undertaken and implementation was too large. Access to a realistic play pen would have assisted with user confidence. Application training did not align with {Client Field} processes. Not all super users were capable of delivering effective training. |
| Communication Management | Poor | Multiple channels used for communication: - Super Users - Website - Steering Committee - Team Briefings - Sneak Preview - e-mails - E-learning | Key messages/decision were not disseminated. Team briefings not effective. Staff too busy focussing on new organisation structure and roles. Impact of the change wasn’t understood/felt until late in the project. |
| Job Design | n/a |  |  |
| Vendor Management (if applicable) |  |  |  |
| Selection Process | Average | Strategy taken for selection ensured the ability for a quick implementation. Product developed against ITIL framework meant close fit to business requirements resulting in no need for customisation. | Strategy to select from products already owned by {Client Field} limited the choice of product (ie. No comparison was done with other available products). |
| Negotiation and contract finalisation | Average |  | Lack of skill with contract negotiation exists within {Client Field}. |
| On-going Vendor management | Good | Partnership model was developed through the project. |  |
| Resource Management | Average |  | Vendor experienced issues with resource continuity mid way through the project however they ensured this did not affect {Client Field} by securing a third party and working to gain skills transfer. |
| Vendor Performance | Good |  |  |
| Product Engineering |  |  |  |
| Requirements | Good | Significant effort went into the process design & subsequent workshops which drove the definition of the finalised business requirements. Workshops run professionally with documented agendas, decisions & minutes. | No documented requirements existed for system performance. |
| Design | Poor | Design is able to be traced back to business requirements. | Whilst the design was fully documented and achieved sign-off before the implementation stage of the project was entered, it was apparent during the build phase that additional stakeholders should have been engaged to review the technical aspects of the design at an earlier stage so as to confirm its supportability. Deviations were made from the vendor recommended architecture which has caused post implementation issues. |
| Code and unit tests | Good | Zero Severity 1 – critical defects raised. No significant downtime observed during test phases. | More rigour to be applied to who is communicated to about product changes to understand downstream impacts (ie. Testers). |
| Integration and Systems testing | Average | Formal test cases were documented and stored within Test Director for future reuse. Test coverage was confirmed via traceability to business requirements within Test Director. Formal test reporting & defect management was performed. | Test environments did not fully support the ability to replicate integration (eg. Lack of Email test environment). |
| User Acceptance Testing | Average | Formal test cases were documented and stored within the Test Environment for future reuse. Formal test reporting & defect management was performed. Formal test sign off was achieved from the Service Desk and {Client Field} representatives. Super users were used to perform the testing however there would have been benefit in extending the test participants. | Testing was confined to one location and therefore did not highlight any issues with distributed areas. Performance & load testing was out of scope but should have been in scope. UAT focussed on functionality of the system but should have extended to useability. |
| Development/Change Mgmt Process | Average | Formal change management processes were followed for any changes identified to the agreed business requirements. | The translation of the processes into how they would be used ‘operationally’ was not detailed sufficiently. |
| Development and Testing environment | Average | Test Environment was flexible with housing of development environment(s) due to not being operational in the project’s required timeframe. | Environments were not sufficient to allow Load/Performance testing to be replicated. |
| Implementation |  |  |  |
| Preparation (planning) | Average | Documented implementation plan with all required certification was available. Technical dress rehearsal performed. | It was unclear as to the entry criteria into the CAB process resulting in additional effort being required to gathered information than expected. |
| Data Migration | Average | Ability to make use of the freeze to migrate a large portion of data prior to cut-over reduced the risk and time for implementation. | Late change to scope to include migration of Open Service Calls from the old Service Desk system (without extending schedule to perform detailed analysis) introduced some minor post implementation issues. Cleansing of duplicate person records in Infra was not performed. |
| Execution of plan/schedule | Good | Implementation completed within the agreed change outage window. |  |
| Support and Maintenance |  |  |  |
| Problem Management |  | A user support model was documented and agreed prior to go-live. | User support model was ineffective. |
| Handover | Average | Support budget and positions were created by the project well in advance of go-live. Project funded application support positions for x months and deployed them onto the project to enable skills transfer to be achieved prior to go-live. Project funded training for system administrators prior to go-live. | Appointment of new staff into the support areas bought different needs. No documented process exists for handover of projects into support areas. |

### Project Changes

The following table represents all changes that were raised, the reason for the change and what impact if any was felt on the scope of the project.  The Change Request register is available within the Appendix.

| CR# | Description | Reason for Change | Impact on Scope |
| --- | --- | --- | --- |
| 1 | Design for Integration between the Service Desk & the Email System | The integration of Service Desk-Email would allow the Customer Support Office (CSO) to know what alerts have been sent and for which event. The current scope of the Service Desk design does not consider this integration of Service Desk-Email. | Work completed by Vendor staff. Funding providing by {Project Name} project. Minor impact. |
| 2 | Include interim process for problem management in {Project Name} training deliverables | User confusion between incident and problem management meant a need to ensure they were trained in the handoff processes between incident and problem management. | Work completed by {Client Field} – increase to scope occurred in the development of the training materials. Scope change identified well in advance of when training materials were due to be completed. Minor impact. |
| 3 | Development of a release strategy for enhancements to the Service Desk application | Obtain funding from {Project Name}. Transformation was to provide governance over the activity. Outcome was to document a road map for future service management activities. | Change was accepted – additional resources were bought on to complete the work within the Transformation governance. Funding was all that the {Project Name} project contributed. Minor impact. |
| 4 | Inclusion of exception processing for the CMDB | To ensure: - Integrity of CMDB CI system fields increased due to automated CI exception monitoring and reporting process. - No loss of CI exceptions via email (or other communication medium). - {Client Field} CMDB Audit Schedule template ready for handover to {Client Field} Auditor | Increase to scope. Required additional analysis, development and test effort. |
| 5 | Email notifications Work Instruction | No documented operational work instruction existed for modifications to the Email escalation groups. This needed to be completed to enable contract staff to make the changes due to operational resource constraints. | Vendor contracted to perform the work. Minor impact. |
| 6 | Asset Templates and Forms | In order to reduce the need for duplication of work in two separate systems, a change was made to the Service Desk Application to streamline the asset administration functions. This meant that only procurement and disposal activities were required to be processed in the old Service Desk system. | This increased the scope in that there was a requirement to analyse and design the process (& supporting end user documentation) and application customisations to support this change, along with ensure appropriate testing (including regression was performed). Major impact. |
| 7 | ICT Change Tool Configuration | Automate aspect of the change process – change was raised late due to internal resource issues being experienced. | Major impact. Causing down stream impacts on training. |
| 8 | Reporting Descope | Reports that were excluded were not able to be produced given the information captured by the system. They required other processes to be implemented first. | Reduction in scope. |
| 9 | Exclusion of CMDB Data Sources | At the time of scoping the data migration some data sources existed but on execution these sources had ceased to exist or had been replaced by others. | Reduction in scope. |
| 10 | Rebaseline Project Schedule due to accepted delay to implementation | Schedule rebaseline required due to resource constraints preventing the UAT and Production infrastructure to be built in line with the original schedule | No impact to scope. |
| 11 | Remove population of Document CI's from the scope of the {Project Name} implementation | A change to the {Client Field} strategy for document management meant that the document repository was not going to be available in time for go-live. Rather than delay go-live as a result of this dependency, the business sponsors agreed to reduce the scope and include in a subsequent release. | Reduction in scope. |
| 12 | Increase scope of migration to bring across open Service Calls from old Service Desk system to new Service Desk system | In order to reduce the number of systems to be used by {Client Field} staff on go-live it was requested to migrate Open Service Calls into the Service Desk system. | This increase to scope caused some minor post implementation issues as a result of the lack of time factored in to performed detailed analysis & testing prior to the migration. |
| 13 | Obtain handover from Data Migration analyst | Required due to the slippage as the Data migration specialist contract was ending and he was unavailable to extend. | Vendor contracted to perform the work. Minor impact. |
| 14 | Extension of the Vendor warranty support | Extended warranty support to mitigate the risk of post implementation issues | HP contracted to perform the work. Minor impact. |

# Detail of Findings and Recommendations

## Project Budget (Schedule and Cost)

### Findings

- Project completed on time

- Project completed within budget

- Infrastructure quotation process doesn’t kick in until implementation phase.

### Recommendations

- Ensure costing model is put in place to enable projects to accurately estimate at business case stage.

## Project Initiation

### Findings

- The estimates and the cost baseline identified in the business case were sufficient.

- Active involvement in the project by senior stakeholders was excellent.

- Resource planning for the project phases was appropriate.

- The project team understood their roles and responsibilities

- The sponsor was committed to the project schedule and the level of sponsorship was correct.

- The phased approach of design and then implementation was the correct one for budgeting purposes. The vendor aligned successfully with this approach.

### Recommendations

- The ongoing membership of the Steering Committee should be clearly defined and documented.

- A standard handover process from a project to BAU teams should be developed and understood at project initiation to enable activities to be catered for during project planning.

- A better means of communication between the delivery office and the investment office needs to be devised to ensure the benefits management approach post project is understood.

- A risk assessment of the organisational changes and the impact on all areas of the business should be conducted and any risk mitigation identified and agreed. Hold workshops to assess and communicate the impacts.

## Project Management

### Findings

- The balance of the team structure of {Client Field}, vendor and contractors was right. The whole team had a clear definition of roles and responsibilities. The vendor was able to concentrate on delivery of the product and not get involved with internal {Client Field} politics.

- An Operations Consultant should have been involved at the beginning of the project to clarify the process to be followed and assist with planning for the build and handover of infrastructure components however this function did not exist at the time.

- The partnership approach worked well with the vendor.

- The steering committee’s quick actioning and resolution of escalated risks was good.

- There was mutual respect within the team.

- The flexibility shown by the Testing Manager to provide an environment allowed the project to move forward.

- The high level milestones were understood and accepted by the project team.  Detailed planning was not performed for the infrastructure build aspects of the solution until late in the implementation phase.

- Engagement with the Service Desk was good and provided continuity through the life of the project.

- Engagement with {Client Field} should have extended to the middle management layer.

- Lack of buy-in was achieved with the {Client Field}.

- Confusion was felt on who had responsibility for communications (the project or {Client Field}?)

### Recommendations

- Engage and communicate earlier with key stakeholders.

- Engage Ops Consultants earlier in the process to plan the resources and effort required for provisioning and commissioning of supplied environments.

- A standard model for effort estimation of standard builds should be developed to assist with planning.

- Develop a single communication channel for all project related information and communication.

- Develop an engagement model between the project and {Client Field}.

- The Path to Production Testing model needs to be endorsed and formalised.

## Procurement

### Findings

- The budget forecasting was adequate.

- The resource planning undertaken took into account the procurement process and timeframes.

- Lack of capacity planning meant the need for all required infrastructure to be purchased on demand resulting in a need to factor in lead times with planning.

- Preferred supplier arrangements existed for recruitment of medium-long term appointments however appeared to be nonexistent for short term requirements (eg. 1-3 months).

- Market buoyancy affected ability to attract & retain skilled staff in operational areas.

### Recommendations

- The quoting process needs to be reviewed to allow estimates to be achieved earlier in the project lifecycle.

- {Client Field} should have input or review the design of the solution.

- Develop a strategic plan of the {Client Field} infrastructure capacity.

- A plan or model needs to be developed for the allocation of human resources to build Production Infrastructure.

## Organisational Change Management

### Findings

- The processes were pitched at too high a level for the general end user to understand the impact on their day to day role.

- The concept of having the Super Users – to provide on-the-spot and on-going support to staff, rather than having trainers who fly in, train, and are never seen again mostly worked well and provided the basis for ongoing support post go-live.

- Separating process training and tool training was not an optimal approach for end users.  It did not allow end users to see how the process integrated with the tool.

- The gap between when training was undertaken and go-live was too big.  If a realistic training environment was available this would have assisted with user confidence on go-live.

- Bringing Super Users back together just before Go-Live provided a refresher and ability for questions to be raised.

- A review of each super users capability to act as the support person for their respective areas should have been performed to identify whether a replacement would be required or if additional support would be sufficient.

- Having face-to-face sessions, and all the support material, Student Guide, Quick Reference Cards, e-Learning provided varying methods for different learning styles.

- A number of different communication channels were used however not all were effective (eg. Team briefings).

### Recommendations

- Allocation of additional time between the Super User training and the start of the end-user training to review the material and make improvements is required.

- Review of the application training material should have been performed by project staff.

- Ensure that there is a free flow of information on the vendor side between their designers and their trainers to ensure that {Client Field} customisation are accounted for in the vendor training materials.

- For end user training, there cannot be overlap between sessions at all, as some sites do not have enough staff to have everyone out at once.

- Access to a realistic practice database/training database for at least the Super Users (with real data entered) would have assisted with user confidence.

- More integration of the process components and the tool in the training

- Either ensure there is a feedback mechanism from Managers that confirms they have communicated important information back to their teams or employ dedicated communications specialists to travel the state communicating to all staff.

- Engage the process champions (middle management layer) earlier to aid in the dissemination of information.

## Vendor Management

### Findings

- Partnership negated an ‘us and them’ culture.

- Having the vendor team on site was beneficial.

- Attendance of the vendor at the Steering Committee assisting with developing the partnership.

- The vendor project manager managed all aspects of vendor engagement which meant {Client Field} didn’t have to contend with the vendor politics and different lines of business.

### Recommendations

- Ensure a vendor representative is on site at all times.

- Employ a more rigorous change management process to control product changes and to communicate these changes to the developers and the test team.

## Product Engineering

### Findings

- The data gathering exercise & tool presentations to stakeholders helped set expectations of the product.

- The processes were finalised at the start of design phase.

- There was a lack of clarity on how the project should engage with {Client Field} to validate the design and also to perform the build of the Production and UAT environments.

- The ‘as built’ product deviated from the agreed design.  These changes were made during the build of the infrastructure due to {Client Field} needing to alter the documented design for supportability reasons. This caused subsequent post go-live issues.

- The ‘out of the box’ approach with minimal customisation aided in keeping to schedule and ensures the upgrade path is not jeopardised.

- Upfront agreement of the version of the tool ensured less regression issues were experienced.

- Use of test director provided for a single repository for all test cases and defects mapped back to original business requirements and enables future reuse.

- Agreed release and testing cycles helped keep development on track.

- Following a structured test methodology assisted in ensuring appropriate focus & control was placed on the agreed test phases.

- Test environments did not contain the same infrastructure as used in Production.

- Late introduction of the requirement for performance testing, did not allow for controlled testing to be performed.

- Testing did not cater for the distributed deployment.

- User acceptance testing was performed by super users from across the state.

### Recommendations

- The risks and impacts for any deviations from the vendor recommended design should be appropriately understood and accepted by technical support areas in addition to project team & business sponsors.

- Testers, analysts and organisational change staff to be trained in the application early in the project lifecycle.

- Performance/Load testing should not be excluded from scope and should be planned and executed in a controlled manner.

- Test environments should be scaled appropriately to enable performance and load testing to be undertaken.

- Clarity to be provided on touch points between Projects and {Client Field}.

- Tests should be undertaken in various locations to ensure any issues due to locality are uncovered and rectified early.

- Testing should be performed against differing WAN links.

## Implementation

### Findings

- The strategy used for implementation of the production infrastructure worked well (ie. Prod infrastructure used for UAT).

- Ability to perform multiple refreshes into UAT assisted with data migration and deployment tasks.

- All documentation was produced and prepared for presentation at the CAB.

- Having the business sponsor at the CAB stages assisted with provision of the context of the change.

- The change was made within the scheduled window.

- Having a change freeze on the old and new tool aided deployment.

- Performing the bulk of the data migration during the freeze and prior to the go live date was beneficial.

- Quick and confident support from the Asset Management group was great.

- Being able to perform dress rehearsals in UAT was key in producing a successful implementation plan.

### Recommendations

- An audit of all stages of the implementation should be performed immediately post completion to ensure no mistakes were made (ie. install instructions are followed correctly).

- Presence of sponsor at the CAB meetings.

- Provide a backup for all identified technical resources.

- Provide support for all applications that are impacted by the implementation.

- Secure and enforce a change freeze.

## Support & Maintenance

### Findings

- A support model was agreed and in place prior to go live.

- Confusion remains around the difference in processes/support for Enterprise versus Local services.

- No formal handover process was evident.

- Establishing the application support positions by the project aided easier transition to {Client Field} application specialists.

- Having the application support personnel involved in project delivery and go live assisted with knowledge transfer.  This should also have been considered for Technical Staff.

- Funding and training of the applications specialists by the project assisted in the transition to the BAU support role.

- Some post implementation issues were identified and it took some time to understand the process for how to raise these with the vendor (ie. There was a lack of clarity around the vendor support model to follow post implementation).

- Additional warranty was purchased from the Service Desk system vendor.

- {Client Field} have proactively taken ownership of the ongoing support for the new application.

### Recommendations

- More clarity is required around enterprise versus local

- A means of retaining the product knowledge within the support teams needs to be developed.

- The handover process to BAU needs to be formally agreed and documented.

- Support for the district staff should be formalised and agreed.

- The project shutdown/closure was too rapid. Should have stayed open for 6-8 weeks to transition and support the BAU teams.

Appendix

Final Project Status Report

<<insert Project Status Report here>>

Risk & Issue Register

<<insert Project Risk & Issues Register here>>

Training Evaluation

Change Request Register

<<insert Change Request Register here>>

Raw Responses

<<insert Raw Response documents here>>

Stakeholders

The following people were invited to provide input:

| Name | Input Provided | Input Not Provided |
| --- | --- | --- |
| - John Citizen |  | - √ |
| - Wendy Person | - √ |  |

NB:  A number of people declined to provide input in the timeframe allocated as identified above.